## Sheet1
GOEL CONSTRUCTIONS PVT. LTD.
Client : JSW Utkal Steel Limited
Project : Phase-1 Greenfield Expansion
Package : Civil Works - WTP & MHS
Contract No. : JUSL/CIV/2024/117
DAILY PROGRESS REPORT
Data date
11-Sep-2026
Sl. | Description | Location | UOM | Qty as per BOQ | GFC Drawing | Front Handed Over | Progress upto last month | Monthly Target | Daily Target | Progress for the day | Progress this month (till previous day) | % Completion | Manpower | Remarks
1 | Chemical Dosing Building & MCC (200+250) | Water Treatment Plant | Cum | 450 | 250 | 250 | 0 | 60 | 3 | 2 | 8 | 0.018 | 1400%
2 | UF RO Shed | Water Treatment Plant | Cum | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | drawing awaited
3 | Buffer thickner | Water Treatment Plant | Cum | 1700 | 1450 | 1450 | 406 | 250 | 12 | 14 | 40 | 0.27 | 4400%
4 | Pump for thickner | Water Treatment Plant | Cum | 51 | 51 | 51 | 20 | 15 | 1 | 1 | 4 | 0.49 | 300%
5 | RO Feed Tank, waste water and reject tank | Water Treatment Plant | Cum | 775 | 775 | 500 | 0 | 90 | 4 | 3 | 12 | 0.019 | 1800%
6 | Stacker (Filtration Side) 1-8 | Stacker & Reclaimer | Cum | 6836 | 6836 | 6836 | 5283 | 500 | 25 | 22 | 88 | 0.79 | 12800%
Note : quantities are cumulative
| Prepared by |  |  | Checked by