## DPR
MEHER FOUNDATION PVT LTD
Daily Progress Report - Piling Works - JSW Utkal Phase 1
Date | 11.09.2026
Sl No | Area | Description of Structure | Unit | Total Scope | Released |  | Cum. upto 31.08.2026 | Plan |  | Actual |  | Reason for slippage | Remarks
[5 empty] | Drawing | Front |  | Month | Day | Day | Month upto 10.09.26
a | b | c | d | e | f | g | h | i | j | k | l | m | n
1 | Filtration Unit | Filtration Main Building (Part-1) | Nos | 893 | 893 | 893 | 880 | 15 | 2 | 3 | 10
2 |  | Filtration Main Building (Part-2) | Nos | 659 | 659 | 659 | 650 | 10 | 1 | 2 | 7
3 |  | Intermediate slurry agitator tank (Part-2) | Nos | 34 | 34 | 34 | 34 | - | - | NIL | - |  | Completed
|  | Sub Total : Filtration Unit |  | 1586
5 | Material Handling Facilities | Conveyor gallery J1C1 & J1C2 | Nos | 1,188 | 1,188 | 1,188 | 1,100 | 60 | 4 | 6 | 22 | rebar shortage
6 |  | JH7C1C2 | Nos | 2,214 | 2,214 | 2,214 | 1,890 | 180 | 12 | 9 | 70 | crane breakdown | watch
7 |  | TT0C1C2 drive house | Nos | 324 | 324 | 324 | 324 | N.A. | N.A. | - | - |  | Completed
8 |  | JH6 | Nos | 1,136 | 1,136 | 1,136 | 1,095 | 25 | 2 | 4 | 15
|  | Sub Total : Material Handling Facilities |  | 4862
|  | GRAND TOTAL |  | 6448
Prepared by : Site Engineer
Signature