## Consolidated
VENSAR CONSTRUCTIONS - CONSOLIDATED DAILY REPORT
Reporting date : 11-Sep-2026
A. CIVIL WORKS (Cum)
S.No | Zone | Name of work | Total Qty | Drg. Released | Front Avl | Upto last month | Target this month | Target today | Achieved today | Achieved this month till yesterday | Constraint
1 | Water Treatment Plant | Pump House with sump & pump | 4400 | 3900 | 3900 | 1853 | 400 | 20 | 18 | 60 | shuttering
2 | Water Treatment Plant | Clarifier 2 | 1350 | 1350 | 1350 | 0 | 200 | 10 | 0 | 0 | front not released
3 | Stacker & Reclaimer | Stacker (Filtration Side) 1-8 | 6836 | 6836 | 6836 | 5283 | 500 | 25 | 30 | 90
4 | Roads & Drains | Road and drains (20mtr width)-2km | 6450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | drawing awaited
|  | Total | 19036 | 12086 | 12086 | 7136 | 1100 | 55 | 48 | 150
B. STRUCTURAL ERECTION (MT)
Sr | Area | Structure | Scope MT | Drawing | Front | Till last month | Plan FTM | Plan FTD | Actual FTD | Actual FTM (prev) | Remarks
1 | Filtration Unit | Filtration Main Building - TS | 636 | 636 | 636 | 220 | 120 | 6 | 5 | 30
2 | Material Handling Facilities | Junction House JH02 - BS | 3622 | 3587 | 2686 | 1200 | 300 | 15 | 12 | 70
3 | Water Treatment Plant | Pipe Rack WTP - TS | 3096 | 3096 | 2872 | 806 | 200 | 10 | 11 | 45