## Read Me
CHILLER PLANT – 4D BIM CONSTRUCTION SCHEDULE
JSW Utkal Steel Ltd – 816 m² Pelletizing Plant-1 (PP-1), Paradeep, Odisha ¦ Chiller Plant (combined for PP-1 & PP-2)
Owner: JSW Utkal Steel Ltd ¦ Technology: Primetals Technologies ¦ Engineering & construction partner: L&T Construction (Minerals & Metals)
GENERAL
P6 reference schedule | NEWPROJ-24_DD_2026-10-02_6.xer (and Schedule Engine export NEWPROJ-24_DD_2026-10-02_3_1.xlsx) – WBS Pellet Plant-1 › Utilities › Chiller Plant (19 activities)
Data Date (input) | 2026-10-02 | ← change for every progress update (all sheets follow)
Next working day (formula) | 2026-10-03
Calendar | JSW USL Calender – Mon–Sat working, Sunday off, 10 h/day, holidays per XER (see Calendar sheet)
SHEETS
4D Schedule | Hierarchy = P6: Lvl 1 Chiller Plant › Lvl 2 Engineering / Procurement / Construction › Lvl 3 GROUP = each of the 18 P6 activities (dates identical to P6 for baseline, actual & current) › Lvl 4 = 126 detailed activities sequenced inside their group (+ 2 groups of additional scope not in P6). Each construction activity carries BIM category, element marks, zone, level, drawing, selection set and TimeLiner task type.
BIM Element Map | 411 model elements (53 piles, 35 pile caps, 29 pile cap beams, 116 column segments, plinth/floor/roof beams & slabs, stairs, trenches, F1/F2 foundations, equipment …) each linked to one 4D activity, with live dates & status.
TimeLiner Import | Flat, CSV-ready task table for Navisworks TimeLiner / Synchro / Fuzor (also delivered as a separate .csv). Planned = current schedule, Actual = site actuals, Baseline = P6 BL.
Gantt | Weekly bar chart of the current schedule with data-date line (conditional formatting – updates automatically).
P6 Roll-up | For every P6 activity: P6 BL / current / actual dates vs the group roll-up in the 4D Schedule (Δ in working days, "✔ Same as P6") + progress summary (activities, elements, RCC quantity).
Calendar | Working-day list (named range WorkDays) and holidays from the XER.
HOW TO UPDATE (monthly / weekly)
1. Set the new Data Date in C7.
2. In 4D Schedule enter Actual Start / Actual Finish / % Complete (yellow cells) from DPR, pour cards and pile register. Replace the blue ASSUMED actual dates with real ones.
3. Current Start/Finish of all remaining activities re-plan automatically (Pred-1/Pred-2 logic, FS/SS + lag in working days, SNET, project calendar). Change durations, logic or SNET in the blue cells if the site sequence differs.
4. Check P6 Roll-up: detailed finish dates should match the updated P6 dates (Δ = 0) – otherwise adjust durations / SNET or report the variance.
5. Re-export TimeLiner Import (File › Save As › CSV) or refresh the Excel/CSV data source in Navisworks / Synchro and re-run the simulation.
HOW TO LINK WITH THE BIM MODEL (4D)
A. Revit / Tekla: create text parameters 4D_Element_ID and 4D_Activity_ID (shared, instance) on all categories used. Fill them from BIM Element Map (columns A & J) – e.g. Dynamo "Data.ImportExcel" + "Element.SetParameterByName", or Tekla UDA import. Split columns at EL -0.300 / +4.000 / +9.150 (construction joints) so each lift is a separate element.
B. Navisworks: append the model (NWC), TimeLiner › Data Sources › Add › CSV Import (TimeLiner Import .csv) – map Display ID, Task Name, Task Type, Planned Start/End, Actual Start/End; Rebuild Task Hierarchy.
C. TimeLiner › Auto-Attach Using Rules › New rule: "Map TimeLiner tasks from column Display ID to items with property 4D_Activity_ID (category Element)". Alternatively create Search Sets named exactly as the Activity ID (column J of 4D Schedule) and use the "Selection Sets with the same name" rule.
D. Simulate › Settings: show Planned vs Actual (Actual dates = site actuals; Planned = current schedule; Baseline columns can be mapped to Planned for BL-vs-actual comparison). Task types: Construct (appear), Demolish (excavation – disappear), Temporary.
E. Synchro 4D / Fuzor: import the same CSV / Excel, link resources by the 4D_Activity_ID user field.
KEY ASSUMPTIONS – PLEASE VERIFY
1. GROUP RULE: each P6 activity is a group whose baseline, actual and current dates equal P6 (checked live in P6 Roll-up col AB). Detailed activities are sequenced inside the group window by logic (FS/SS + lag); the first starts on the group start and the last finishes on the group finish – for baseline (P6 BL window) and for actual / current dates.
2. P6 gives only group-level dates. Detailed ACTUAL dates before the Data Date are ASSUMED (blue text) inside the P6 actual windows: drawings 29-Nov-25 → 07-Jan-26 & 31-Aug → 24-Sep-26, PR→PO Feb–May-26, piling 17-Dec-25 → 19-Jan-26, excavation 18-Feb → 30-Mar-26, concreting from 08-Mar-26 (70% in P6 → substructure, columns, first floor, stairs, roof, cable trenches & 2 grade-slab panels complete; ≈74% by RCC quantity). Replace with DPR / register dates.
3. In-progress groups (E&I drawings, chiller & pump manufacturing, concreting): remaining durations set so each group finishes on its P6 date (11-Dec-26, 31-Dec-26, 31-Dec-26, 25-Nov-26).
4. Work sequence assumed Zone-1 (Grid 1–3) → Zone-2 (Grid 3–5) → Zone-3 (Grid 5–6); piles in pile-number order (row A → E).
5. Chiller foundations F1 ×5 and pump foundations F2 ×10 were on HOLD (vendor GA) – released by "Equipment drawings release" (actual 24-Sep-26); they start 03-Oct-26 and drive the concreting group to its P6 finish 25-Nov-26.
6. Brickwork, lintels, finishes, monorail beams and handrails have no P6 activity – shown in the separate group "ADDITIONAL SCOPE – NOT IN P6" (Oct-26 → Jan-27). Recommend adding them to P6.
7. Construction joints in columns assumed at EL -0.300, +4.000 (also chiller-hall columns) and +9.150 (mumty). Equipment tags CH-01…05 / P-01…10 numbered from Grid 1 (verify).
8. Concrete quantities are approximate (drawing qty boxes split by element proportion) and are used only for progress weighting.
COLOUR LEGEND
Site input cell (Actual Start / Finish / % Complete, Data Date)
Abc | Blue text = input / assumed value (logic, durations, SNET, assumed actuals)
Lvl 3 GROUP row = P6 activity (roll-up = P6 dates)
Lvl 2 phase row (Engineering / Procurement / Construction)
Milestone
Status Completed
Status In Progress
Not Started (Late) – baseline start already passed
DRAWINGS USED
O24091-990-C-B-19530-001 | R0 | Chiller Plant – Layout & detail of pile (P1–P53, 600Ø bored cast-in-situ, L = 26 m)
O24091-990-C-B-19531-001 | R0 | Layout & detail of pile cap (PC1 ×17, PC2 ×18), pile cap beam (PCB1/2/3) & column schedule (C1–C9, SC1)
O24091-990-C-B-19531-002 | R0 | GA & RC detail of plinth beam (PB1–PB10) at EL(-)0.300 TOB
O24091-990-C-B-19531-003 | R0 | GA & RC detail of floor beam (FB1–FB14, TB1) & 150 thk slab at EL(+)4.000 TOC
O24091-990-C-B-19531-004 | R0 | GA & RC detail of roof plan at EL(+)9.150 & EL(+)12.150 TOC (RB1–RB16, monorails MR-1/MR-2)
O24091-990-C-B-19531-005 | R0 | GA & RC detail of staircase ST-1 & ST-2 and sectional elevations
O24091-990-C-B-19531-006 | R0 | GA & RC detail of lintel beams (LB1–LB12) & chajja
O24091-990-C-B-19531-007 | R0 | GA & RC detail of grade slab, chiller foundation F1, pump foundation F2, cable trench & cable pit
O24091-990-C-B-19531-008 | R0 | Sections & details for grade slab / trench / pit / F1 / F2 (read with 19531-007)
ZONES & GRID KEY (column mark / pile cap at each grid intersection)
Z1 | Zone-1 : Grid 1 to 3 (column lines 1, 2, 3 incl. SC1)
Z2 | Zone-2 : Grid 3 to 5 (column lines 4, 5)
Z3 | Zone-3 : Grid 5 to 6 (column lines 5.1, 6)
Row \ Grid | 6 | 5.1 | 5 | 4 | 3 | 2 | 1
E | C1 / PC1 * | C1 / PC2 * | C9 / PC2 | C9 / PC2 | C9 / PC2 | C1 / PC2 * | C1 / PC1 *
D.2 | [5 empty] | C1 / PC2 * | C1 / PC2 *
D.1 | C1 / PC1 * | C1 / PC2 *
D | C2 / PC2 |  | C8 / PC2 | C8 / PC2 | C8 / PC2 | C7 / PC2 | C7 / PC2
C | C3 / PC1 |  | C6 / PC1 | C5 / PC1 | C4 / PC1 | C4 / PC1 | C6 / PC1
B | C3 / PC2 |  | C6 / PC2 | C4 / PC1 | C4 / PC1 | C4 / PC1 | C3 / PC2
A | C3 / PC1 |  | C3 / PC2 | C4 / PC1 | C4 / PC1 | C4 / PC1 | C6 / PC1
SC1 (500×600) on PCB3 at Grid 1, 2400 S of Row B. * = column continues to mumty roof EL +12.150 (ST-1: Grid 6–5.1, ST-2: Grid 2–1).

## 4D Schedule
CHILLER PLANT (Combined for PP-1 & PP-2) – 4D BIM CONSTRUCTION SCHEDULE (detailed, element-linked)
JSW Utkal Steel Ltd – 816 m² Pelletizing Plant-1 (PP-1), Paradeep ¦ P6 reference: NEWPROJ-24 (XER, Data Date 02-Oct-2026), WBS Pellet Plant-1 › Utilities › Chiller Plant ¦ Drawings O24091-990-C-B-19530-001 & 19531-001…008 (R0) | [28 empty] | Data Date: | 2026-10-02
Structure: Lvl 1 project › Lvl 2 phase › Lvl 3 GROUP = P6 activity (dates = P6 BL / actual / current) › Lvl 4 detailed activities sequenced inside the group. Yellow = site input (Actual Start / Finish / % Complete); blue text = assumed / logic inputs. Use outline buttons 1–4 (left margin) to collapse to group level.
ACTIVITY |  |  |  | BIM / 4D LINK | [8 empty] | P6 GROUP & QUANTITY |  |  | LOGIC (working days) | [7 empty] | BASELINE (P6 BL) |  | ACTUAL – SITE INPUT |  |  | CURRENT SCHEDULE |  |  | ANALYSIS
Activity ID / P6 Group | Lvl | Activity Name | Work Package | Zone | Grid / Location | Level / Elevation | BIM Category | Element Marks | No. of BIM Elements | Selection / Search Set (TimeLiner) | TimeLiner Task Type | Drawing Ref. | P6 Group (parent) | Qty (approx) | Unit | Orig Dur (wd) | Pred-1 | Rel-1 | Lag-1 (wd) | Pred-2 | Rel-2 | Lag-2 (wd) | Start No Earlier Than | BL Start | BL Finish | Actual Start | Actual Finish | % Complete | Remaining Dur (wd) | Current Start | Current Finish | Status | Finish Var vs BL (wd, + = late) | Qty Done | Remarks / P6 check
CHP | 1 | CHILLER PLANT (combined for PP-1 & PP-2) – P6 WBS: Pellet Plant-1 › Utilities › Chiller Plant | [6 empty] | 411 | [14 empty] | 2026-01-20 | 2027-05-15 | 2025-10-20 |  | 52.62% |  | 2025-10-20 | 2027-05-03 | In Progress | -11
CHP.E | 2 | ENGINEERING | [6 empty] | 0 | [14 empty] | 2026-01-20 | 2027-01-09 | 2025-10-20 |  | 45.73% |  | 2025-10-20 | 2026-12-11 | In Progress | -23
JSW USL-BE-CHI-1000 | 3 | Basic drawings from TS - Inputs | [6 empty] | 0 | [14 empty] | 2026-01-20 | 2026-01-20 | 2025-10-20 | 2025-10-20 | 100% |  | 2025-10-20 | 2025-10-20 | Completed | -77 |  | P6 check: ✔ Same as P6
CHP-MS-010 | 4 | Basic drawings / technical specification inputs received | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-BE-CHI-1000 |  |  | 0 | [7 empty] | 2026-01-20 | 2026-01-20 | 2025-10-20 | 2025-10-20 | 100% | 0 | 2025-10-20 | 2025-10-20 | Completed | -77 |  | Actual date as per P6.
JSW USL-DE-CHI-1000 | 3 | Pile drawings release | [6 empty] | 0 | [14 empty] | 2026-02-07 | 2026-03-02 | 2025-11-29 | 2025-12-22 | 100% |  | 2025-11-29 | 2025-12-22 | Completed | -57 |  | P6 check: ✔ Same as P6
CHP-ENG-010 | 4 | Pile layout & detail drawing (19530-001) – design & preparation | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct | O24091-990-C-B-19530-001 | JSW USL-DE-CHI-1000 |  |  | 14 | [6 empty] | 2025-11-29 | 2026-02-07 | 2026-02-23 | 2025-11-29 | 2025-12-15 | 100% | 0 | 2025-11-29 | 2025-12-15 | Completed | -57 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-ENG-020 | 4 | Pile drawing – review, client approval & IFC issue | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct | O24091-990-C-B-19530-001 | JSW USL-DE-CHI-1000 |  |  | 6 | CHP-ENG-010 | FS | 0 |  |  |  |  | 2026-02-24 | 2026-03-02 | 2025-12-16 | 2025-12-22 | 100% | 0 | 2025-12-16 | 2025-12-22 | Completed | -57 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-MS-020 | 4 | Pile drawings released (IFC) | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone | O24091-990-C-B-19530-001 | JSW USL-DE-CHI-1000 |  |  | 0 | CHP-ENG-020 | FS | 0 |  |  |  |  | 2026-03-02 | 2026-03-02 | 2025-12-22 | 2025-12-22 | 100% | 0 | 2025-12-22 | 2025-12-22 | Completed | -57 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
JSW USL-DE-CHI-1010 | 3 | Civil drawings release | [6 empty] | 0 | [14 empty] | 2026-01-20 | 2026-02-24 | 2025-12-23 | 2026-01-07 | 100% |  | 2025-12-23 | 2026-01-07 | Completed | -40 |  | P6 check: ✔ Same as P6
CHP-ENG-030 | 4 | Civil GA & RC drawings 19531-001 … 008 – preparation & checking | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct | O24091-990-C-B-19531-001 … 008 | JSW USL-DE-CHI-1010 |  |  | 7 | [6 empty] | 2025-12-23 | 2026-01-20 | 2026-02-10 | 2025-12-23 | 2025-12-31 | 100% | 0 | 2025-12-23 | 2025-12-31 | Completed | -33 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-ENG-040 | 4 | Civil drawings – client review & IFC release | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct | O24091-990-C-B-19531-001 … 008 | JSW USL-DE-CHI-1010 |  |  | 5 | CHP-ENG-030 | FS | 0 |  |  |  |  | 2026-02-11 | 2026-02-24 | 2026-01-02 | 2026-01-07 | 100% | 0 | 2026-01-02 | 2026-01-07 | Completed | -40 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-MS-030 | 4 | Civil drawings released (IFC) | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-DE-CHI-1010 |  |  | 0 | CHP-ENG-040 | FS | 0 |  |  |  |  | 2026-02-24 | 2026-02-24 | 2026-01-07 | 2026-01-07 | 100% | 0 | 2026-01-07 | 2026-01-07 | Completed | -40 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
JSW USL-DE-CHI-1020 | 3 | Equipment drawings release | [6 empty] | 0 | [14 empty] | 2026-08-31 | 2026-10-10 | 2026-08-31 | 2026-09-24 | 100% |  | 2026-08-31 | 2026-09-24 | Completed | -13 |  | P6 check: ✔ Same as P6
CHP-ENG-050 | 4 | Vendor GA drawings (centrifugal chillers & pumps) – receipt & review | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-DE-CHI-1020 |  |  | 13 | [6 empty] | 2026-08-31 | 2026-08-31 | 2026-09-23 | 2026-08-31 | 2026-09-14 | 100% | 0 | 2026-08-31 | 2026-09-14 | Completed | -8 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-ENG-060 | 4 | Equipment layout & foundation loading data – approval & release | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-DE-CHI-1020 |  |  | 9 | CHP-ENG-050 | FS | 0 |  |  |  |  | 2026-09-24 | 2026-10-10 | 2026-09-15 | 2026-09-24 | 100% | 0 | 2026-09-15 | 2026-09-24 | Completed | -13 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-MS-040 | 4 | Equipment drawings released – HOLD on chiller / pump foundations F1 & F2 lifted | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone | O24091-990-C-B-19531-007 | JSW USL-DE-CHI-1020 |  |  | 0 | CHP-ENG-060 | FS | 0 |  |  |  |  | 2026-10-10 | 2026-10-10 | 2026-09-24 | 2026-09-24 | 100% | 0 | 2026-09-24 | 2026-09-24 | Completed | -13 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
JSW USL-DE-CHI-1030 | 3 | Piping drawings release | [6 empty] | 0 | [14 empty] | 2026-10-12 | 2026-12-03 |  |  | 0% |  | 2026-10-03 | 2026-11-19 | Not Started | -12 |  | P6 check: ✔ Same as P6
CHP-ENG-070 | 4 | Piping GA, isometric & pipe-support drawings – preparation | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-DE-CHI-1030 |  |  | 30 | [6 empty] | 2026-10-03 | 2026-10-12 | 2026-11-20 |  |  | 0% | 30 | 2026-10-03 | 2026-11-07 | Not Started | -11 |  | Sequenced to finish on P6 date 19-Nov-26.
CHP-ENG-080 | 4 | Piping drawings – review, comments & IFC release | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-DE-CHI-1030 |  |  | 10 | CHP-ENG-070 | FS | 0 |  |  |  |  | 2026-11-21 | 2026-12-03 |  |  | 0% | 10 | 2026-11-09 | 2026-11-19 | Not Started | -12 |  | Sequenced to finish on P6 date 19-Nov-26.
CHP-MS-050 | 4 | Piping drawings released (IFC) | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-DE-CHI-1030 |  |  | 0 | CHP-ENG-080 | FS | 0 |  |  |  |  | 2026-12-03 | 2026-12-03 |  |  | 0% | 0 | 2026-11-19 | 2026-11-19 | Not Started | -12 |  | Sequenced to finish on P6 date 19-Nov-26.
JSW USL-DE-CHI-1040 | 3 | E&I drawings release | [6 empty] | 0 | [14 empty] | 2026-12-04 | 2027-01-09 | 2026-10-01 |  | 23.27% |  | 2026-10-01 | 2026-12-11 | In Progress | -23 |  | P6 check: ✔ Same as P6
CHP-ENG-090 | 4 | E&I layouts (cable routing, lighting, earthing, instrument locations) – preparation | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-DE-CHI-1040 |  |  | 30 | [6 empty] | 2026-10-01 | 2026-12-04 | 2026-12-15 | 2026-10-01 |  | 38% | 19 | 2026-10-01 | 2026-10-26 | In Progress | -43 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates. In progress at DD; remaining duration set so the group finishes on the P6 date.
CHP-ENG-100 | 4 | E&I drawings – coordination with piping drawings, review & IFC release | Engineering |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-DE-CHI-1040 |  |  | 19 | CHP-ENG-090 | FS | 0 | CHP-MS-050 | FS | 0 |  | 2026-12-30 | 2027-01-09 |  |  | 0% | 19 | 2026-11-20 | 2026-12-11 | Not Started | -23 |  | Sequenced to finish on P6 date 11-Dec-26.
CHP-MS-060 | 4 | E&I drawings released (IFC) | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-DE-CHI-1040 |  |  | 0 | CHP-ENG-100 | FS | 0 |  |  |  |  | 2027-01-09 | 2027-01-09 |  |  | 0% | 0 | 2026-12-11 | 2026-12-11 | Not Started | -23 |  | Sequenced to finish on P6 date 11-Dec-26.
CHP.P | 2 | PROCUREMENT | [6 empty] | 0 | [14 empty] | 2026-02-28 | 2026-12-24 | 2026-02-03 |  | 72.92% |  | 2026-02-03 | 2026-12-31 | In Progress | 5
JSW USL-PR-2440 | 3 | Centrifugal Chillers - PR to PO | [6 empty] | 0 | [14 empty] | 2026-02-28 | 2026-05-12 | 2026-02-03 | 2026-05-20 | 100% |  | 2026-02-03 | 2026-05-20 | Completed | 7 |  | P6 check: ✔ Same as P6
CHP-PRC-010 | 4 | Centrifugal chillers – PR, RFQ, bids & technical evaluation | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2440 |  |  | 58 | [6 empty] | 2026-02-03 | 2026-02-28 | 2026-04-16 | 2026-02-03 | 2026-04-13 | 100% | 0 | 2026-02-03 | 2026-04-13 | Completed | -3 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PRC-020 | 4 | Centrifugal chillers – commercial negotiation & PO placement | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2440 |  |  | 31 | CHP-PRC-010 | FS | 0 |  |  |  |  | 2026-04-17 | 2026-05-12 | 2026-04-14 | 2026-05-20 | 100% | 0 | 2026-04-14 | 2026-05-20 | Completed | 7 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PRC-030 | 4 | PO placed – centrifugal chillers | Procurement |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-PR-2440 |  |  | 0 | CHP-PRC-020 | FS | 0 |  |  |  |  | 2026-05-12 | 2026-05-12 | 2026-05-20 | 2026-05-20 | 100% | 0 | 2026-05-20 | 2026-05-20 | Completed | 7 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
JSW USL-PR-2450 | 3 | Centrifugal Chillers - Manufacturing, Inspection & Delivery | [6 empty] | 0 | [14 empty] | 2026-06-30 | 2026-12-24 | 2026-05-22 |  | 60.1% |  | 2026-05-22 | 2026-12-31 | In Progress | 5 |  | P6 check: ✔ Same as P6
CHP-PRC-040 | 4 | Centrifugal chillers – manufacturing | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2450 |  |  | 165 | [6 empty] | 2026-05-22 | 2026-06-30 | 2026-12-03 | 2026-05-22 |  | 68.48% | 52 | 2026-05-22 | 2026-12-03 | In Progress | 0 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates. In progress at DD; remaining duration set so the group finishes on the P6 date.
CHP-PRC-050 | 4 | Centrifugal chillers – stage inspection & FAT | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2450 |  |  | 8 | CHP-PRC-040 | FS | 0 |  |  |  |  | 2026-12-04 | 2026-12-10 |  |  | 0% | 8 | 2026-12-04 | 2026-12-12 | Not Started | 2 |  | Sequenced to finish on P6 date 31-Dec-26.
CHP-PRC-060 | 4 | Centrifugal chillers – dispatch & transit to site | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2450 |  |  | 15 | CHP-PRC-050 | FS | 0 |  |  |  |  | 2026-12-11 | 2026-12-24 |  |  | 0% | 15 | 2026-12-14 | 2026-12-31 | Not Started | 5 |  | Sequenced to finish on P6 date 31-Dec-26.
CHP-MS-070 | 4 | Centrifugal chillers delivered at site | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-PR-2450 |  |  | 0 | CHP-PRC-060 | FS | 0 |  |  |  |  | 2026-12-24 | 2026-12-24 |  |  | 0% | 0 | 2026-12-31 | 2026-12-31 | Not Started | 5 |  | Sequenced to finish on P6 date 31-Dec-26.
JSW USL-PR-2460 | 3 | Pumps - PR to PO | [6 empty] | 0 | [14 empty] | 2026-02-28 | 2026-05-12 | 2026-02-03 | 2026-04-27 | 100% |  | 2026-02-03 | 2026-04-27 | Completed | -12 |  | P6 check: ✔ Same as P6
CHP-PRC-070 | 4 | Pumps – PR, RFQ, bids & technical evaluation | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2460 |  |  | 46 | [6 empty] | 2026-02-03 | 2026-02-28 | 2026-04-16 | 2026-02-03 | 2026-03-30 | 100% | 0 | 2026-02-03 | 2026-03-30 | Completed | -15 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PRC-080 | 4 | Pumps – commercial negotiation & PO placement | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2460 |  |  | 24 | CHP-PRC-070 | FS | 0 |  |  |  |  | 2026-04-17 | 2026-05-12 | 2026-03-31 | 2026-04-27 | 100% | 0 | 2026-03-31 | 2026-04-27 | Completed | -12 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PRC-090 | 4 | PO placed – pumps | Procurement |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-PR-2460 |  |  | 0 | CHP-PRC-080 | FS | 0 |  |  |  |  | 2026-05-12 | 2026-05-12 | 2026-04-27 | 2026-04-27 | 100% | 0 | 2026-04-27 | 2026-04-27 | Completed | -12 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
JSW USL-PR-2470 | 3 | Pumps - Manufacturing, Inspection & Delivery | [6 empty] | 0 | [14 empty] | 2026-04-30 | 2026-09-18 | 2026-04-29 |  | 63.77% |  | 2026-04-29 | 2026-12-31 | In Progress | 86 |  | P6 check: ✔ Same as P6
CHP-PRC-100 | 4 | Pumps – manufacturing | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2470 |  |  | 187 | [6 empty] | 2026-04-29 | 2026-04-30 | 2026-09-04 | 2026-04-29 |  | 70.59% | 55 | 2026-04-29 | 2026-12-07 | In Progress | 78 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates. In progress at DD; remaining duration set so the group finishes on the P6 date.
CHP-PRC-110 | 4 | Pumps – inspection & performance test | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2470 |  |  | 6 | CHP-PRC-100 | FS | 0 |  |  |  |  | 2026-09-05 | 2026-09-09 |  |  | 0% | 6 | 2026-12-08 | 2026-12-14 | Not Started (Late) | 80 |  | Sequenced to finish on P6 date 31-Dec-26.
CHP-PRC-120 | 4 | Pumps – dispatch & transit to site | Procurement |  |  |  | — (non-BIM) |  | 0 |  | Construct |  | JSW USL-PR-2470 |  |  | 14 | CHP-PRC-110 | FS | 0 |  |  |  |  | 2026-09-10 | 2026-09-18 |  |  | 0% | 14 | 2026-12-15 | 2026-12-31 | Not Started (Late) | 86 |  | Sequenced to finish on P6 date 31-Dec-26.
CHP-MS-080 | 4 | Pumps delivered at site | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-PR-2470 |  |  | 0 | CHP-PRC-120 | FS | 0 |  |  |  |  | 2026-09-18 | 2026-09-18 |  |  | 0% | 0 | 2026-12-31 | 2026-12-31 | Not Started (Late) | 86 |  | Sequenced to finish on P6 date 31-Dec-26.
CHP.C | 2 | CONSTRUCTION | [6 empty] | 396 | [14 empty] | 2026-01-20 | 2027-05-15 | 2025-12-17 |  | 52.02% |  | 2025-12-17 | 2027-05-03 | In Progress | -11
JSW USL-CON-CHI-1000 | 3 | Piling Works | [6 empty] | 53 |  |  |  |  | 53 | [9 empty] | 2026-01-20 | 2026-02-24 | 2025-12-17 | 2026-01-19 | 100% |  | 2025-12-17 | 2026-01-19 | Completed | -30 | 53 | P6 check: ✔ Same as P6
CHP-PIL-010 | 4 | Piles Row A (P1–P7) | Piling | Row A | Row A : Grid 1–6 | Cut-off EL(-)2.425 ; L = 26 m | Structural Foundations (Pile) | P1–P7 | 7 | CHP-PIL-010 | Construct | O24091-990-C-B-19530-001 | JSW USL-CON-CHI-1000 | 7 | Nos | 4 | [6 empty] | 2025-12-17 | 2026-01-20 | 2026-01-23 | 2025-12-17 | 2025-12-20 | 100% | 0 | 2025-12-17 | 2025-12-20 | Completed | -27 | 7 | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PIL-020 | 4 | Piles Row B (P8–P16) | Piling | Row B | Row B : Grid 1–6 | Cut-off EL(-)2.425 ; L = 26 m | Structural Foundations (Pile) | P8–P16 | 9 | CHP-PIL-020 | Construct | O24091-990-C-B-19530-001 | JSW USL-CON-CHI-1000 | 9 | Nos | 5 | CHP-PIL-010 | FS | 0 |  |  |  |  | 2026-01-24 | 2026-01-31 | 2025-12-22 | 2025-12-27 | 100% | 0 | 2025-12-22 | 2025-12-27 | Completed | -28 | 9 | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PIL-030 | 4 | Piles Row C (P17–P22) | Piling | Row C | Row C : Grid 1–6 | Cut-off EL(-)2.425 ; L = 26 m | Structural Foundations (Pile) | P17–P22 | 6 | CHP-PIL-030 | Construct | O24091-990-C-B-19530-001 | JSW USL-CON-CHI-1000 | 6 | Nos | 3 | CHP-PIL-020 | FS | 0 |  |  |  |  | 2026-02-02 | 2026-02-04 | 2025-12-29 | 2025-12-31 | 100% | 0 | 2025-12-29 | 2025-12-31 | Completed | -28 | 6 | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PIL-040 | 4 | Piles Row D (P23–P34) | Piling | Row D | Row D : Grid 1–6 | Cut-off EL(-)2.425 ; L = 26 m | Structural Foundations (Pile) | P23–P34 | 12 | CHP-PIL-040 | Construct | O24091-990-C-B-19530-001 | JSW USL-CON-CHI-1000 | 12 | Nos | 6 | CHP-PIL-030 | FS | 0 |  |  |  |  | 2026-02-05 | 2026-02-12 | 2026-01-02 | 2026-01-08 | 100% | 0 | 2026-01-02 | 2026-01-08 | Completed | -29 | 12 | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PIL-050 | 4 | Piles Rows D.1 & D.2 (P35–P41) | Piling | Row D.1/D.2 | Rows D.1 & D.2 : Grid 1, 2, 5.1, 6 | Cut-off EL(-)2.425 ; L = 26 m | Structural Foundations (Pile) | P35–P41 | 7 | CHP-PIL-050 | Construct | O24091-990-C-B-19530-001 | JSW USL-CON-CHI-1000 | 7 | Nos | 4 | CHP-PIL-040 | FS | 0 |  |  |  |  | 2026-02-13 | 2026-02-17 | 2026-01-09 | 2026-01-13 | 100% | 0 | 2026-01-09 | 2026-01-13 | Completed | -29 | 7 | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
CHP-PIL-060 | 4 | Piles Row E (P42–P53) | Piling | Row E | Row E : Grid 1–6 | Cut-off EL(-)2.425 ; L = 26 m | Structural Foundations (Pile) | P42–P53 | 12 | CHP-PIL-060 | Construct | O24091-990-C-B-19530-001 | JSW USL-CON-CHI-1000 | 12 | Nos | 5 | CHP-PIL-050 | FS | 0 |  |  |  |  | 2026-02-18 | 2026-02-24 | 2026-01-14 | 2026-01-19 | 100% | 0 | 2026-01-14 | 2026-01-19 | Completed | -30 | 12 | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates.
JSW USL-CON-CHI-1010 | 3 | Excavation incl. pile chipping | [6 empty] | 3 | [14 empty] | 2026-03-31 | 2026-06-09 | 2026-02-18 | 2026-03-30 | 100% |  | 2026-02-18 | 2026-03-30 | Completed | -60 |  | P6 check: ✔ Same as P6
CHP-EXC-010 | 4 | Excavation, pile chipping & PCC prep – Zone-1 (Grid 1–3) | Excavation | Z1 | Grid 1–3 : Row E–A | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC) | Excavation solid / Topography (if modelled) |  | 1 | CHP-EXC-010 | Demolish |  | JSW USL-CON-CHI-1010 |  |  | 15 | [6 empty] | 2026-02-18 | 2026-03-31 | 2026-04-30 | 2026-02-18 | 2026-03-07 | 100% | 0 | 2026-02-18 | 2026-03-07 | Completed | -45 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates. Task type 'Demolish' only if excavation solids are modelled.
CHP-EXC-020 | 4 | Excavation, pile chipping & PCC prep – Zone-2 (Grid 3–5) | Excavation | Z2 | Grid 3–5 : Row E–A | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC) | Excavation solid / Topography (if modelled) |  | 1 | CHP-EXC-020 | Demolish |  | JSW USL-CON-CHI-1010 |  |  | 12 | CHP-EXC-010 | SS | 10 |  |  |  | 2026-03-05 | 2026-04-25 | 2026-05-21 | 2026-03-05 | 2026-03-18 | 100% | 0 | 2026-03-05 | 2026-03-18 | Completed | -53 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates. Task type 'Demolish' only if excavation solids are modelled.
CHP-EXC-030 | 4 | Excavation, pile chipping & PCC prep – Zone-3 (Grid 5–6) | Excavation | Z3 | Grid 5–6 : Row E–A | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC) | Excavation solid / Topography (if modelled) |  | 1 | CHP-EXC-030 | Demolish |  | JSW USL-CON-CHI-1010 |  |  | 12 | CHP-EXC-020 | SS | 9 |  |  |  | 2026-03-16 | 2026-05-15 | 2026-06-09 | 2026-03-16 | 2026-03-30 | 100% | 0 | 2026-03-16 | 2026-03-30 | Completed | -60 |  | Group actual dates = P6; split inside the group ASSUMED (sequenced) – replace with register / DPR dates. Task type 'Demolish' only if excavation solids are modelled.
JSW USL-CON-CHI-1020 | 3 | Concreting - Foundations, Columns, Beams, Walls, etc. | [6 empty] | 309 |  |  |  |  | 1171.5 | [9 empty] | 2026-04-17 | 2026-10-12 | 2026-03-08 |  | 73.74% |  | 2026-03-08 | 2026-11-25 | In Progress | 37 | 863.82 | P6 check: ✔ Same as P6
CHP-SUB-010 | 4 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | Substructure | Z1 | Grid 1 to 3 (column lines 1, 2, 3 incl. SC1) | B.O.C EL(-)2.500 (75 PCC M7.5 below) | Structural Foundations (Pile Cap) | PC1 ×9, PC2 ×8 | 17 | CHP-SUB-010 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 25.5 | m³ | 14 | CHP-EXC-010 | SS | 14 |  |  |  | 2026-03-08 | 2026-04-17 | 2026-04-28 | 2026-03-08 | 2026-03-25 | 100% | 0 | 2026-03-08 | 2026-03-25 | Completed | -29 | 25.5 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-020 | 4 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | Substructure | Z2 | Grid 3 to 5 (column lines 4, 5) | B.O.C EL(-)2.500 (75 PCC M7.5 below) | Structural Foundations (Pile Cap) | PC2 ×6, PC1 ×4 | 10 | CHP-SUB-020 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 17 | m³ | 10 | CHP-EXC-020 | FS | 0 | CHP-SUB-010 | SS | 8 |  | 2026-04-24 | 2026-05-02 | 2026-03-19 | 2026-03-31 | 100% | 0 | 2026-03-19 | 2026-03-31 | Completed | -27 | 17 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-030 | 4 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | Substructure | Z3 | Grid 5 to 6 (column lines 5.1, 6) | B.O.C EL(-)2.500 (75 PCC M7.5 below) | Structural Foundations (Pile Cap) | PC2 ×4, PC1 ×4 | 8 | CHP-SUB-030 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 12.5 | m³ | 8 | CHP-EXC-030 | FS | 0 | CHP-SUB-020 | SS | 6 |  | 2026-05-02 | 2026-05-08 | 2026-03-31 | 2026-04-08 | 100% | 0 | 2026-03-31 | 2026-04-08 | Completed | -25 | 12.5 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-040 | 4 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | Substructure | Z1 | Grid 1 to 3 (column lines 1, 2, 3 incl. SC1) | EL(-)2.500 to EL(-)0.300 / Top of PCB3 to EL(-)0.300 / B/O PCB EL(-)2.400 | Structural Columns + Structural Framing (Pile Cap Beam) | C1 ×4, C9, C7 ×2, C8, C6 ×2, C4 ×6, C3, SC1, PCB1 ×10, PCB2 ×2, PCB3 ×2 | 32 | CHP-SUB-040 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 23.5 | m³ | 15 | CHP-SUB-010 | FS | 0 |  |  |  |  | 2026-04-29 | 2026-05-11 | 2026-03-26 | 2026-04-11 | 100% | 0 | 2026-03-26 | 2026-04-11 | Completed | -24 | 23.5 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-050 | 4 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | Substructure | Z2 | Grid 3 to 5 (column lines 4, 5) | EL(-)2.500 to EL(-)0.300 / B/O PCB EL(-)2.400 | Structural Columns + Structural Framing (Pile Cap Beam) | C9 ×2, C8 ×2, C5, C6 ×2, C4 ×2, C3, PCB1 ×7, PCB2 | 18 | CHP-SUB-050 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 13.3 | m³ | 12 | CHP-SUB-020 | FS | 0 | CHP-SUB-040 | SS | 8 |  | 2026-05-06 | 2026-05-14 | 2026-04-04 | 2026-04-17 | 100% | 0 | 2026-04-04 | 2026-04-17 | Completed | -22 | 13.3 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-060 | 4 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | Substructure | Z3 | Grid 5 to 6 (column lines 5.1, 6) | EL(-)2.500 to EL(-)0.300 / B/O PCB EL(-)2.400 | Structural Columns + Structural Framing (Pile Cap Beam) | C1 ×4, C2, C3 ×3, PCB1 ×5, PCB2 ×2 | 15 | CHP-SUB-060 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 11.2 | m³ | 10 | CHP-SUB-030 | FS | 0 | CHP-SUB-050 | SS | 6 |  | 2026-05-11 | 2026-05-18 | 2026-04-11 | 2026-04-22 | 100% | 0 | 2026-04-11 | 2026-04-22 | Completed | -21 | 11.2 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-070 | 4 | Backfilling & compaction up to plinth level – Zone-1 | Substructure | Z1 | Grid 1–3 | EL(-)2.500 to EL(-)0.500 | Earthwork (if modelled) |  | 1 | CHP-SUB-070 | Construct |  | JSW USL-CON-CHI-1020 |  |  | 6 | CHP-SUB-040 | FS | 0 |  |  |  |  | 2026-05-12 | 2026-05-15 | 2026-04-13 | 2026-04-18 | 100% | 0 | 2026-04-13 | 2026-04-18 | Completed | -22 |  | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-080 | 4 | Backfilling & compaction up to plinth level – Zone-2 | Substructure | Z2 | Grid 3–5 | EL(-)2.500 to EL(-)0.500 | Earthwork (if modelled) |  | 1 | CHP-SUB-080 | Construct |  | JSW USL-CON-CHI-1020 |  |  | 5 | CHP-SUB-050 | FS | 0 | CHP-SUB-070 | FS | 0 |  | 2026-05-16 | 2026-05-19 | 2026-04-20 | 2026-04-24 | 100% | 0 | 2026-04-20 | 2026-04-24 | Completed | -20 |  | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-090 | 4 | Backfilling & compaction up to plinth level – Zone-3 | Substructure | Z3 | Grid 5–6 | EL(-)2.500 to EL(-)0.500 | Earthwork (if modelled) |  | 1 | CHP-SUB-090 | Construct |  | JSW USL-CON-CHI-1020 |  |  | 5 | CHP-SUB-060 | FS | 0 | CHP-SUB-080 | FS | 0 |  | 2026-05-20 | 2026-05-23 | 2026-04-25 | 2026-04-30 | 100% | 0 | 2026-04-25 | 2026-04-30 | Completed | -19 |  | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-100 | 4 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | Substructure | Z1 | Grid 1 to 3 (column lines 1, 2, 3 incl. SC1) | T.O.B EL(-)0.300 | Structural Framing (Plinth Beam) | PB2, PB10, PB5 ×2, PB9, PB7, PB4, PB8 ×2, PB1 ×2, PB6, PB3 | 13 | CHP-SUB-100 | Construct | O24091-990-C-B-19531-002 | JSW USL-CON-CHI-1020 | 19 | m³ | 12 | CHP-SUB-070 | FS | 0 |  |  |  |  | 2026-05-16 | 2026-05-25 | 2026-04-20 | 2026-05-04 | 100% | 0 | 2026-04-20 | 2026-05-04 | Completed | -18 | 19 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-110 | 4 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | Substructure | Z2 | Grid 3 to 5 (column lines 4, 5) | T.O.B EL(-)0.300 | Structural Framing (Plinth Beam) | PB2, PB8 ×2, PB1 ×2, PB3 | 6 | CHP-SUB-110 | Construct | O24091-990-C-B-19531-002 | JSW USL-CON-CHI-1020 | 14 | m³ | 10 | CHP-SUB-080 | FS | 0 | CHP-SUB-100 | SS | 6 |  | 2026-05-21 | 2026-05-28 | 2026-04-27 | 2026-05-08 | 100% | 0 | 2026-04-27 | 2026-05-08 | Completed | -17 | 14 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUB-120 | 4 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | Substructure | Z3 | Grid 5 to 6 (column lines 5.1, 6) | T.O.B EL(-)0.300 | Structural Framing (Plinth Beam) | PB2, PB10, PB1 ×2, PB5, PB9, PB3 ×2 | 8 | CHP-SUB-120 | Construct | O24091-990-C-B-19531-002 | JSW USL-CON-CHI-1020 | 14.5 | m³ | 10 | CHP-SUB-090 | FS | 0 | CHP-SUB-110 | SS | 5 |  | 2026-05-25 | 2026-06-01 | 2026-05-04 | 2026-05-14 | 100% | 0 | 2026-05-04 | 2026-05-14 | Completed | -15 | 14.5 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-010 | 4 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | Superstructure | Z1 | Grid 1 to 3 (column lines 1, 2, 3 incl. SC1) | EL(-)0.300 to EL(+)4.000 | Structural Columns | C1 ×4, C9, C7 ×2, C8, C6 ×2, C4 ×6, C3, SC1 | 18 | CHP-SUP-010 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 19.5 | m³ | 14 | CHP-SUB-100 | FS | 0 |  |  |  |  | 2026-05-26 | 2026-06-05 | 2026-05-05 | 2026-05-20 | 100% | 0 | 2026-05-05 | 2026-05-20 | Completed | -14 | 19.5 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-020 | 4 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | Superstructure | Z2 | Grid 3 to 5 (column lines 4, 5) | EL(-)0.300 to EL(+)4.000 | Structural Columns | C9 ×2, C8 ×2, C5, C6 ×2, C4 ×2, C3 | 10 | CHP-SUP-020 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 10.8 | m³ | 10 | CHP-SUB-110 | FS | 0 | CHP-SUP-010 | SS | 7 |  | 2026-06-01 | 2026-06-08 | 2026-05-13 | 2026-05-23 | 100% | 0 | 2026-05-13 | 2026-05-23 | Completed | -13 | 10.8 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-030 | 4 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | Superstructure | Z3 | Grid 5 to 6 (column lines 5.1, 6) | EL(-)0.300 to EL(+)4.000 | Structural Columns | C1 ×4, C2, C3 ×3 | 8 | CHP-SUP-030 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 8.7 | m³ | 8 | CHP-SUB-120 | FS | 0 | CHP-SUP-020 | SS | 5 |  | 2026-06-04 | 2026-06-10 | 2026-05-19 | 2026-05-27 | 100% | 0 | 2026-05-19 | 2026-05-27 | Completed | -12 | 8.7 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-040 | 4 | Tie beam TB1 (TOB EL +2.100) at Grid 1 | Superstructure | Z1 | Grid 1 : Row D–C | EL(+)2.100 TOB | Structural Framing | TB1 | 1 | CHP-SUP-040 | Construct | O24091-990-C-B-19531-003 | JSW USL-CON-CHI-1020 | 1 | m³ | 5 | CHP-SUP-010 | SS | 6 |  |  |  |  | 2026-05-30 | 2026-06-03 | 2026-05-12 | 2026-05-16 | 100% | 0 | 2026-05-12 | 2026-05-16 | Completed | -15 | 1 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-050 | 4 | Staircase ST-2 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | Superstructure | Z1 | Grid 2–1 / Row E–D.2 | EL(-)0.050 to EL(+)4.000 | Stairs + Floors (Landing) + Structural Framing (Stair Beam) | FLT-1..FLT-3, Landings +1.300, +2.650, STB1 / STB2 | 3 | CHP-SUP-050 | Construct | O24091-990-C-B-19531-005 | JSW USL-CON-CHI-1020 | 10 | m³ | 15 | CHP-SUP-010 | FS | 0 |  |  |  |  | 2026-06-06 | 2026-06-17 | 2026-05-21 | 2026-06-06 | 100% | 0 | 2026-05-21 | 2026-06-06 | Completed | -9 | 10 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-060 | 4 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | Superstructure | Z1 | Grid 1 to 3 (column lines 1, 2, 3 incl. SC1) | T.O.C EL(+)4.000 | Structural Framing (Floor Beam) + Floors (Structural slab) | FB1, FB4, FB5, FB9, FB10, FB11/FB12/FB13, FB14, SLAB-FF | 8 | CHP-SUP-060 | Construct | O24091-990-C-B-19531-003 | JSW USL-CON-CHI-1020 | 33 | m³ | 24 | CHP-SUP-010 | FS | 0 |  |  |  |  | 2026-06-06 | 2026-06-24 | 2026-05-21 | 2026-06-17 | 100% | 0 | 2026-05-21 | 2026-06-17 | Completed | -6 | 33 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-070 | 4 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | Superstructure | Z2 | Grid 3 to 5 (column lines 4, 5) | T.O.C EL(+)4.000 | Structural Framing (Floor Beam) + Floors (Structural slab) | FB1, FB4, FB2, FB8, FB9, FB11/FB12/FB13, SLAB-FF | 7 | CHP-SUP-070 | Construct | O24091-990-C-B-19531-003 | JSW USL-CON-CHI-1020 | 30 | m³ | 22 | CHP-SUP-020 | FS | 0 | CHP-SUP-060 | SS | 12 |  | 2026-06-16 | 2026-07-02 | 2026-06-04 | 2026-06-29 | 100% | 0 | 2026-06-04 | 2026-06-29 | Completed | -3 | 30 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-080 | 4 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | Superstructure | Z3 | Grid 5 to 6 (column lines 5.1, 6) | T.O.C EL(+)4.000 | Structural Framing (Floor Beam) + Floors (Structural slab) | FB1, FB2/FB3, FB4, FB6/FB7, FB11/FB12/FB13, FB14, SLAB-FF | 7 | CHP-SUP-080 | Construct | O24091-990-C-B-19531-003 | JSW USL-CON-CHI-1020 | 18 | m³ | 20 | CHP-SUP-030 | FS | 0 | CHP-SUP-070 | SS | 10 |  | 2026-06-24 | 2026-07-08 | 2026-06-16 | 2026-07-08 | 100% | 0 | 2026-06-16 | 2026-07-08 | Completed | 0 | 18 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-090 | 4 | Staircase ST-1 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | Superstructure | Z3 | Grid 6–5.1 / Row E–D.1 | EL(-)0.050 to EL(+)4.000 | Stairs + Floors (Landing) + Structural Framing (Stair Beam) | FLT-1..FLT-3, Landings +1.300, +2.650, STB1 / STB2 | 3 | CHP-SUP-090 | Construct | O24091-990-C-B-19531-005 | JSW USL-CON-CHI-1020 | 10 | m³ | 15 | CHP-SUP-030 | FS | 0 |  |  |  |  | 2026-06-11 | 2026-06-22 | 2026-05-28 | 2026-06-13 | 100% | 0 | 2026-05-28 | 2026-06-13 | Completed | -7 | 10 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-100 | 4 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | Superstructure | Z1 | Grid 1 to 3 (column lines 1, 2, 3 incl. SC1) | EL(+)4.000 to EL(+)9.150 | Structural Columns | C1 ×4, C9, C7 ×2, C8, C6 ×2, C4 ×6, C3, SC1 | 18 | CHP-SUP-100 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 21.5 | m³ | 18 | CHP-SUP-060 | FS | 0 |  |  |  |  | 2026-06-25 | 2026-07-08 | 2026-06-18 | 2026-07-08 | 100% | 0 | 2026-06-18 | 2026-07-08 | Completed | 0 | 21.5 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-110 | 4 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | Superstructure | Z2 | Grid 3 to 5 (column lines 4, 5) | EL(+)4.000 to EL(+)9.150 | Structural Columns | C9 ×2, C8 ×2, C5, C6 ×2, C4 ×2, C3 | 10 | CHP-SUP-110 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 11.9 | m³ | 14 | CHP-SUP-070 | FS | 0 | CHP-SUP-100 | SS | 8 |  | 2026-07-03 | 2026-07-13 | 2026-06-30 | 2026-07-15 | 100% | 0 | 2026-06-30 | 2026-07-15 | Completed | 2 | 11.9 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-120 | 4 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | Superstructure | Z3 | Grid 5 to 6 (column lines 5.1, 6) | EL(+)4.000 to EL(+)9.150 | Structural Columns | C1 ×4, C2, C3 ×3 | 8 | CHP-SUP-120 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 9.6 | m³ | 12 | CHP-SUP-080 | FS | 0 | CHP-SUP-110 | SS | 6 |  | 2026-07-09 | 2026-07-17 | 2026-07-09 | 2026-07-22 | 100% | 0 | 2026-07-09 | 2026-07-22 | Completed | 4 | 9.6 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-130 | 4 | Staircase ST-2 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | Superstructure | Z1 | Grid 2–1 / Row E–D.2 | EL(+)4.000 to EL(+)9.150 | Stairs + Floors (Landing) + Structural Framing (Stair Beam) | FLT-4..FLT-7, Landings +5.350, +6.700, +7.900, STB1 / STB2 | 3 | CHP-SUP-130 | Construct | O24091-990-C-B-19531-005 | JSW USL-CON-CHI-1020 | 13 | m³ | 22 | CHP-SUP-050 | FS | 0 | CHP-SUP-060 | FS | 0 |  | 2026-06-25 | 2026-07-11 | 2026-06-18 | 2026-07-13 | 100% | 0 | 2026-06-18 | 2026-07-13 | Completed | 1 | 13 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-140 | 4 | Staircase ST-1 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | Superstructure | Z3 | Grid 6–5.1 / Row E–D.1 | EL(+)4.000 to EL(+)9.150 | Stairs + Floors (Landing) + Structural Framing (Stair Beam) | FLT-4..FLT-7, Landings +5.350, +6.700, +7.900, STB1 / STB2 | 3 | CHP-SUP-140 | Construct | O24091-990-C-B-19531-005 | JSW USL-CON-CHI-1020 | 13 | m³ | 22 | CHP-SUP-090 | FS | 0 | CHP-SUP-080 | FS | 0 |  | 2026-07-09 | 2026-07-25 | 2026-07-09 | 2026-08-03 | 100% | 0 | 2026-07-09 | 2026-08-03 | Completed | 7 | 13 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-150 | 4 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | Superstructure | Z1 | Grid 1 to 3 (column lines 1, 2, 3 incl. SC1) | T.O.C EL(+)9.150 | Structural Framing (Roof Beam) + Floors / Roofs (Structural slab) | RB1, RB2, RB3, RB4, RB5, RB6, RB7, RB8, RB10/RB11, RB12/RB13, SLAB-RF | 11 | CHP-SUP-150 | Construct | O24091-990-C-B-19531-004 | JSW USL-CON-CHI-1020 | 88 | m³ | 30 | CHP-SUP-100 | FS | 0 |  |  |  |  | 2026-07-09 | 2026-08-01 | 2026-07-09 | 2026-08-12 | 100% | 0 | 2026-07-09 | 2026-08-12 | Completed | 9 | 88 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-160 | 4 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | Superstructure | Z2 | Grid 3 to 5 (column lines 4, 5) | T.O.C EL(+)9.150 | Structural Framing (Roof Beam) + Floors / Roofs (Structural slab) | RB1, RB2, RB3, RB4, RB5, RB7, RB8, RB10, SLAB-RF | 9 | CHP-SUP-160 | Construct | O24091-990-C-B-19531-004 | JSW USL-CON-CHI-1020 | 88 | m³ | 28 | CHP-SUP-110 | FS | 0 | CHP-SUP-150 | SS | 15 |  | 2026-07-21 | 2026-08-12 | 2026-07-27 | 2026-08-28 | 100% | 0 | 2026-07-27 | 2026-08-28 | Completed | 13 | 88 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-170 | 4 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | Superstructure | Z3 | Grid 5 to 6 (column lines 5.1, 6) | T.O.C EL(+)9.150 | Structural Framing (Roof Beam) + Floors / Roofs (Structural slab) | RB1, RB2, RB3, RB4, RB5, RB8, RB9/RB10, RB14, SLAB-RF | 9 | CHP-SUP-170 | Construct | O24091-990-C-B-19531-004 | JSW USL-CON-CHI-1020 | 62 | m³ | 24 | CHP-SUP-120 | FS | 0 | CHP-SUP-160 | SS | 14 |  | 2026-08-01 | 2026-08-20 | 2026-08-12 | 2026-09-09 | 100% | 0 | 2026-08-12 | 2026-09-09 | Completed | 17 | 62 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-180 | 4 | Mumty columns (EL +9.150 to +12.150) – ST-2 (C1 ×4) | Superstructure | Z1 | 1/E; 2/E; 1/D.2; 2/D.2 | EL(+)9.150 to EL(+)12.150 | Structural Columns | C1 ×4 | 4 | CHP-SUP-180 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 2 | m³ | 8 | CHP-SUP-150 | FS | 0 | CHP-SUP-130 | FS | 0 |  | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-08-22 | 100% | 0 | 2026-08-13 | 2026-08-22 | Completed | 12 | 2 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-190 | 4 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-2 | Superstructure | Z1 | Grid 2–1 / Row E–D.2 | T.O.C EL(+)12.150 | Structural Framing (Roof Beam) + Floors / Roofs (Structural slab) | RB15 / RB16, SLAB 150 | 2 | CHP-SUP-190 | Construct | O24091-990-C-B-19531-004 | JSW USL-CON-CHI-1020 | 8.5 | m³ | 12 | CHP-SUP-180 | FS | 0 |  |  |  |  | 2026-08-08 | 2026-08-18 | 2026-08-24 | 2026-09-05 | 100% | 0 | 2026-08-24 | 2026-09-05 | Completed | 16 | 8.5 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-200 | 4 | Mumty columns (EL +9.150 to +12.150) – ST-1 (C1 ×4) | Superstructure | Z3 | 5.1/E; 6/E; 5.1/D.1; 6/D.1 | EL(+)9.150 to EL(+)12.150 | Structural Columns | C1 ×4 | 4 | CHP-SUP-200 | Construct | O24091-990-C-B-19531-001 | JSW USL-CON-CHI-1020 | 2 | m³ | 8 | CHP-SUP-170 | FS | 0 | CHP-SUP-140 | FS | 0 |  | 2026-08-21 | 2026-08-27 | 2026-09-10 | 2026-09-18 | 100% | 0 | 2026-09-10 | 2026-09-18 | Completed | 19 | 2 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-SUP-210 | 4 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-1 | Superstructure | Z3 | Grid 6–5.1 / Row E–D.1 | T.O.C EL(+)12.150 | Structural Framing (Roof Beam) + Floors / Roofs (Structural slab) | RB15 / RB16, SLAB 150 | 2 | CHP-SUP-210 | Construct | O24091-990-C-B-19531-004 | JSW USL-CON-CHI-1020 | 8.5 | m³ | 12 | CHP-SUP-200 | FS | 0 |  |  |  |  | 2026-08-28 | 2026-09-05 | 2026-09-19 |  | 92% | 1 | 2026-09-19 | 2026-10-03 | In Progress | 23 | 7.82 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates. In progress at DD; remaining duration set so the group finishes on the P6 date.
CHP-GRD-010 | 4 | Cable trench T1 (1500 deep) Row D–C, Grid 6→1 incl. cable pit at Grid 6 | Grade slab & foundations | All | Row D–C : Grid 6→1; Grid 6 / Row D–C | Top EL ±0.000, base EL(-)1.500 / Top EL ±0.000 | Generic Models / Structural (Trench) + Generic Models / Structural (Pit) | T1, Cable pit | 2 | CHP-GRD-010 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 95 | m³ | 25 | CHP-SUB-120 | FS | 0 |  |  |  |  | 2026-06-02 | 2026-06-20 | 2026-05-15 | 2026-06-12 | 100% | 0 | 2026-05-15 | 2026-06-12 | Completed | -7 | 95 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-GRD-020 | 4 | Cable trench T2 (1500 deep) Row B–A, Grid 6→1 | Grade slab & foundations | All | Row B–A : Grid 6→1 | Top EL ±0.000, base EL(-)1.500 | Generic Models / Structural (Trench) | T2 | 1 | CHP-GRD-020 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 85 | m³ | 22 | CHP-GRD-010 | SS | 10 |  |  |  |  | 2026-06-10 | 2026-06-26 | 2026-05-27 | 2026-06-20 | 100% | 0 | 2026-05-27 | 2026-06-20 | Completed | -5 | 85 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-GRD-030 | 4 | Grade slab 150 thk – Row E–D block (cable cellar, toilets, shift room, ante rooms) | Grade slab & foundations | All | Row E–D : Grid 6–1 (cable cellar, toilets, shift room) | T.O.C EL ±0.000 / (-)0.050 | Floors (Grade slab) | GS-ED | 1 | CHP-GRD-030 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 40 | m³ | 12 | CHP-SUP-080 | FS | 10 | CHP-GRD-010 | FS | 0 |  | 2026-07-17 | 2026-07-25 | 2026-07-21 | 2026-08-03 | 100% | 0 | 2026-07-21 | 2026-08-03 | Completed | 7 | 40 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-GRD-040 | 4 | Grade slab 150 thk – Row D–C strip (around trench T1) | Grade slab & foundations | All | Row D–C : Grid 6–1 | T.O.C EL ±0.000 | Floors (Grade slab) | GS-DC | 1 | CHP-GRD-040 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 25 | m³ | 10 | CHP-GRD-010 | FS | 0 | CHP-GRD-030 | SS | 5 |  | 2026-07-21 | 2026-07-28 | 2026-07-27 | 2026-08-06 | 100% | 0 | 2026-07-27 | 2026-08-06 | Completed | 8 | 25 | ASSUMED actual (derived from P6 70% @ DD), sequenced inside the P6 group – replace with DPR / pour-card dates.
CHP-GRD-050 | 4 | Chiller foundations F1-01 & F1-02 (Bays 1–2, 2–3) | Grade slab & foundations | Z1 | Bay 1–2 / Row C–B; Bay 2–3 / Row C–B | T.O.C EL ±0.000 | Structural Foundations (Equipment) | F1-01, F1-02 | 2 | CHP-GRD-050 | Construct | O24091-990-C-B-19531-008 | JSW USL-CON-CHI-1020 | 56 | m³ | 18 | CHP-MS-040 | FS | 0 | CHP-SUP-150 | FS | 0 | 2026-10-03 | 2026-09-05 | 2026-09-19 |  |  | 0% | 18 | 2026-10-03 | 2026-10-24 | Not Started (Late) | 28 | 0 | Was on HOLD (vendor GA); released by equipment drawing release 24-Sep-26.
CHP-GRD-060 | 4 | Chiller foundations F1-03 & F1-04 (Bays 3–4, 4–5) | Grade slab & foundations | Z2 | Bay 3–4 / Row C–B; Bay 4–5 / Row C–B | T.O.C EL ±0.000 | Structural Foundations (Equipment) | F1-03, F1-04 | 2 | CHP-GRD-060 | Construct | O24091-990-C-B-19531-008 | JSW USL-CON-CHI-1020 | 56 | m³ | 18 | CHP-GRD-050 | SS | 5 | CHP-SUP-160 | FS | 0 |  | 2026-09-10 | 2026-09-23 |  |  | 0% | 18 | 2026-10-09 | 2026-10-30 | Not Started (Late) | 30 | 0 | Was on HOLD (vendor GA); released by equipment drawing release 24-Sep-26.
CHP-GRD-070 | 4 | Chiller foundation F1-05 (Bay 5–6) | Grade slab & foundations | Z3 | Bay 5–6 / Row C–B | T.O.C EL ±0.000 | Structural Foundations (Equipment) | F1-05 | 1 | CHP-GRD-070 | Construct | O24091-990-C-B-19531-008 | JSW USL-CON-CHI-1020 | 28 | m³ | 12 | CHP-GRD-060 | SS | 5 | CHP-SUP-170 | FS | 0 |  | 2026-09-14 | 2026-09-22 |  |  | 0% | 12 | 2026-10-15 | 2026-10-29 | Not Started (Late) | 30 | 0 | Was on HOLD (vendor GA); released by equipment drawing release 24-Sep-26.
CHP-GRD-080 | 4 | Pump foundations F2-01 to F2-04 (Bays 1–3) | Grade slab & foundations | Z1 | Row B–A : Bays 1–3 | T.O.C EL ±0.000 | Structural Foundations (Equipment) | F2-01, F2-02, F2-03, F2-04 | 4 | CHP-GRD-080 | Construct | O24091-990-C-B-19531-008 | JSW USL-CON-CHI-1020 | 16 | m³ | 10 | CHP-GRD-050 | SS | 5 | CHP-GRD-020 | FS | 0 |  | 2026-09-10 | 2026-09-17 |  |  | 0% | 10 | 2026-10-09 | 2026-10-21 | Not Started (Late) | 27 | 0 | Was on HOLD (vendor GA); released by equipment drawing release 24-Sep-26.
CHP-GRD-090 | 4 | Pump foundations F2-05 to F2-08 (Bays 3–5) | Grade slab & foundations | Z2 | Row B–A : Bays 3–5 | T.O.C EL ±0.000 | Structural Foundations (Equipment) | F2-05, F2-06, F2-07, F2-08 | 4 | CHP-GRD-090 | Construct | O24091-990-C-B-19531-008 | JSW USL-CON-CHI-1020 | 16 | m³ | 10 | CHP-GRD-080 | SS | 5 | CHP-GRD-060 | SS | 3 |  | 2026-09-14 | 2026-09-21 |  |  | 0% | 10 | 2026-10-15 | 2026-10-27 | Not Started (Late) | 29 | 0 | Was on HOLD (vendor GA); released by equipment drawing release 24-Sep-26.
CHP-GRD-100 | 4 | Pump foundations F2-09 & F2-10 (Bay 5–6) | Grade slab & foundations | Z3 | Bay 5–6 / Row B–A | T.O.C EL ±0.000 | Structural Foundations (Equipment) | F2-09, F2-10 | 2 | CHP-GRD-100 | Construct | O24091-990-C-B-19531-008 | JSW USL-CON-CHI-1020 | 8 | m³ | 6 | CHP-GRD-090 | SS | 4 | CHP-GRD-070 | SS | 3 |  | 2026-09-17 | 2026-09-21 |  |  | 0% | 6 | 2026-10-21 | 2026-10-27 | Not Started (Late) | 29 | 0 | Was on HOLD (vendor GA); released by equipment drawing release 24-Sep-26.
CHP-GRD-110 | 4 | Cable slits (600 deep) between chiller foundations (5 nos) | Grade slab & foundations | All | Row C–B : beside F1-01 … F1-05 | Top EL ±0.000 | Generic Models / Structural (Trench) | Slit-1, Slit-2, Slit-3, Slit-4, Slit-5 | 5 | CHP-GRD-110 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 15 | m³ | 8 | CHP-GRD-070 | FS | 0 | CHP-GRD-060 | FS | 0 |  | 2026-09-24 | 2026-09-29 |  |  | 0% | 8 | 2026-10-31 | 2026-11-09 | Not Started (Late) | 33 | 0
CHP-GRD-120 | 4 | Grade slab 150 thk – Chiller room (Row C–B) | Grade slab & foundations | All | Row C–B : Grid 6–1 | T.O.C EL ±0.000 | Floors (Grade slab) | GS-CB | 1 | CHP-GRD-120 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 35 | m³ | 10 | CHP-GRD-110 | FS | 0 |  |  |  |  | 2026-09-30 | 2026-10-08 |  |  | 0% | 10 | 2026-11-10 | 2026-11-20 | Not Started (Late) | 36 | 0
CHP-GRD-130 | 4 | Grade slab 150 thk – Pump area (Row B–A) incl. 150×100 surface drain | Grade slab & foundations | All | Row B–A : Grid 6–1; Along Row A (inside) | T.O.C EL ±0.000 / EL ±0.000 | Floors (Grade slab) + Generic Models (Drain) | GS-BA, Surface drain | 2 | CHP-GRD-130 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 30 | m³ | 11 | CHP-GRD-100 | FS | 0 | CHP-GRD-120 | SS | 3 |  | 2026-10-05 | 2026-10-12 |  |  | 0% | 11 | 2026-11-13 | 2026-11-25 | Not Started | 37 | 0
CHP-GRD-140 | 4 | Precast covers – cable trenches, cable pit & drain crossings (placement) | Grade slab & foundations | All | T1, T2, cable pit, crossings | EL ±0.000 | Generic Models (Precast cover) | Precast covers | 1 | CHP-GRD-140 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 7 | m³ | 6 | CHP-GRD-120 | SS | 2 |  |  |  |  | 2026-10-03 | 2026-10-07 |  |  | 0% | 6 | 2026-11-12 | 2026-11-18 | Not Started | 35 | 0
CHP-GRD-150 | 4 | Plinth protection, garland drain & 100Ø PVC drain pipes (all round) | Grade slab & foundations | All | All round building; Grid 6/A & 1/A corners | FGL EL(-)0.500 / Below FGL | Generic Models / Floors (Plinth protection) + Pipes (Drain) | Plinth protection, Drain pipes | 2 | CHP-GRD-150 | Construct | O24091-990-C-B-19531-007 | JSW USL-CON-CHI-1020 | 40 | m³ | 15 | CHP-SUP-170 | FS | 5 | CHP-SUP-210 | FS | 0 |  | 2026-09-07 | 2026-09-17 |  |  | 0% | 15 | 2026-10-05 | 2026-10-22 | Not Started (Late) | 28 | 0
CHP-MS-090 | 4 | Civil works complete (all RCC incl. grade slab & equipment foundations) | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-CON-CHI-1020 |  |  | 0 | [7 empty] | 2026-10-12 | 2026-10-12 |  |  | 0% | 0 | 2026-11-25 | 2026-11-25 | Not Started | 37 |  | Date = latest finish of all activities in this group (= P6 JSW USL-CON-CHI-1020 finish).
JSW USL-CON-CHI-1030 | 3 | Erection of Chiller Plant including Fans, Pumps, Drives, etc. | [6 empty] | 18 | [14 empty] | 2027-01-15 | 2027-04-03 |  |  | 0% |  | 2027-01-02 | 2027-03-20 | Not Started | -11 |  | P6 check: ✔ Same as P6
CHP-EQP-010 | 4 | Chiller CH-01 on F1-01 (Bay 1–2) – setting, levelling, alignment & grouting | Equipment | Z1 | On F1-01 (Bay 1–2, Row C–B) | EL ±0.000 | Mechanical Equipment | CH-01 | 1 | CHP-EQP-010 | Construct | Equipment GA (vendor) | JSW USL-CON-CHI-1030 |  |  | 14 | CHP-MS-070 | FS | 0 | CHP-GRD-120 | FS | 0 |  | 2027-01-15 | 2027-02-01 |  |  | 0% | 14 | 2027-01-02 | 2027-01-18 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-020 | 4 | Chiller CH-02 on F1-02 (Bay 2–3) – setting, levelling, alignment & grouting | Equipment | Z1 | On F1-02 (Bay 2–3, Row C–B) | EL ±0.000 | Mechanical Equipment | CH-02 | 1 | CHP-EQP-020 | Construct | Equipment GA (vendor) | JSW USL-CON-CHI-1030 |  |  | 14 | CHP-EQP-010 | SS | 8 |  |  |  |  | 2027-01-25 | 2027-02-10 |  |  | 0% | 14 | 2027-01-12 | 2027-01-28 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-030 | 4 | Chiller CH-03 on F1-03 (Bay 3–4) – setting, levelling, alignment & grouting | Equipment | Z2 | On F1-03 (Bay 3–4, Row C–B) | EL ±0.000 | Mechanical Equipment | CH-03 | 1 | CHP-EQP-030 | Construct | Equipment GA (vendor) | JSW USL-CON-CHI-1030 |  |  | 14 | CHP-EQP-020 | SS | 8 |  |  |  |  | 2027-02-04 | 2027-02-19 |  |  | 0% | 14 | 2027-01-21 | 2027-02-06 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-040 | 4 | Chiller CH-04 on F1-04 (Bay 4–5) – setting, levelling, alignment & grouting | Equipment | Z2 | On F1-04 (Bay 4–5, Row C–B) | EL ±0.000 | Mechanical Equipment | CH-04 | 1 | CHP-EQP-040 | Construct | Equipment GA (vendor) | JSW USL-CON-CHI-1030 |  |  | 14 | CHP-EQP-030 | SS | 8 |  |  |  |  | 2027-02-13 | 2027-03-01 |  |  | 0% | 14 | 2027-02-01 | 2027-02-16 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-050 | 4 | Chiller CH-05 on F1-05 (Bay 5–6) – setting, levelling, alignment & grouting | Equipment | Z3 | On F1-05 (Bay 5–6, Row C–B) | EL ±0.000 | Mechanical Equipment | CH-05 | 1 | CHP-EQP-050 | Construct | Equipment GA (vendor) | JSW USL-CON-CHI-1030 |  |  | 14 | CHP-EQP-040 | SS | 8 |  |  |  |  | 2027-02-23 | 2027-03-11 |  |  | 0% | 14 | 2027-02-10 | 2027-02-25 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-060 | 4 | Hoists – 2T chain pulley block on MR-1 & 10T electric hoist on MR-2 | Equipment | All | MR-1; MR-2 | B.O.MR +8.100 / B.O.MR +7.900 | Mechanical Equipment (Hoist) | CPB on MR-1, EH on MR-2 | 2 | CHP-EQP-060 | Construct | O24091-990-C-B-19531-004 | JSW USL-CON-CHI-1030 |  |  | 5 | CHP-STL-010 | FS | 0 | CHP-EQP-010 | SS | 0 |  | 2027-01-15 | 2027-01-20 |  |  | 0% | 5 | 2027-01-02 | 2027-01-07 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-070 | 4 | Pumps P-01 to P-04 on F2-01..04 (Bays 1–3) – setting, alignment & grouting | Equipment | Z1 | Row B–A : Bays 1–3 (F2-01 … F2-04) | EL ±0.000 | Mechanical Equipment | P-01, P-02, P-03, P-04 | 4 | CHP-EQP-070 | Construct | Equipment GA (vendor) | JSW USL-CON-CHI-1030 |  |  | 12 | CHP-MS-080 | FS | 0 | CHP-EQP-010 | SS | 10 |  | 2027-01-28 | 2027-02-10 |  |  | 0% | 12 | 2027-01-14 | 2027-01-28 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-080 | 4 | Pumps P-05 to P-08 on F2-05..08 (Bays 3–5) – setting, alignment & grouting | Equipment | Z2 | Row B–A : Bays 3–5 (F2-05 … F2-08) | EL ±0.000 | Mechanical Equipment | P-05, P-06, P-07, P-08 | 4 | CHP-EQP-080 | Construct | Equipment GA (vendor) | JSW USL-CON-CHI-1030 |  |  | 12 | CHP-EQP-070 | SS | 8 | CHP-GRD-130 | FS | 0 |  | 2027-02-06 | 2027-02-19 |  |  | 0% | 12 | 2027-01-23 | 2027-02-06 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-090 | 4 | Pumps P-09 & P-10 on F2-09..10 (Bay 5–6) – setting, alignment & grouting | Equipment | Z3 | Row B–A : Bay 5–6 (F2-09, F2-10) | EL ±0.000 | Mechanical Equipment | P-09, P-10 | 2 | CHP-EQP-090 | Construct | Equipment GA (vendor) | JSW USL-CON-CHI-1030 |  |  | 8 | CHP-EQP-080 | SS | 8 |  |  |  |  | 2027-02-16 | 2027-02-24 |  |  | 0% | 8 | 2027-02-03 | 2027-02-11 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
CHP-EQP-100 | 4 | Final alignment, motor/drive coupling & box-up of chillers and pumps | Equipment | All | Chiller hall | ±0.000 | Mechanical Equipment | CH-01..05, P-01..10 (drives) | 1 | CHP-EQP-100 | Construct |  | JSW USL-CON-CHI-1030 |  |  | 19 | CHP-EQP-050 | FS | 0 | CHP-EQP-090 | FS | 0 |  | 2027-03-12 | 2027-04-03 |  |  | 0% | 19 | 2027-02-26 | 2027-03-20 | Not Started | -11 |  | Equipment tag nos. assumed from Grid 1 – verify.
JSW USL-CON-CHI-1040 | 3 | Piping works incl. testing | [6 empty] | 5 | [14 empty] | 2027-02-09 | 2027-04-21 |  |  | 0% |  | 2027-01-27 | 2027-04-08 | Not Started | -11 |  | P6 check: ✔ Same as P6
CHP-PIP-010 | 4 | Pipe supports & sleepers – chiller hall | Piping | All | Chiller hall Row C–A | ±0.000 to +3.0 | Pipe Accessories / Generic (supports) | Pipe supports | 1 | CHP-PIP-010 | Construct |  | JSW USL-CON-CHI-1040 |  |  | 15 | CHP-MS-050 | FS | 0 | CHP-EQP-010 | SS | 20 |  | 2027-02-09 | 2027-02-25 |  |  | 0% | 15 | 2027-01-27 | 2027-02-12 | Not Started | -11
CHP-PIP-020 | 4 | CHW & CW headers (supply / return) – fabrication & erection | Piping | All | Chiller hall Row C–A | Header elevation | Pipes | CHWS, CHWR, CWS, CWR headers | 1 | CHP-PIP-020 | Construct |  | JSW USL-CON-CHI-1040 |  |  | 25 | CHP-PIP-010 | SS | 8 |  |  |  |  | 2027-02-18 | 2027-03-19 |  |  | 0% | 25 | 2027-02-05 | 2027-03-05 | Not Started | -11
CHP-PIP-030 | 4 | Chiller hook-up piping CH-01..CH-05 incl. valves, strainers & flexible connectors | Piping | All | Row C–B | ±0.000 to +3.0 | Pipes / Pipe Accessories | Chiller branch lines | 1 | CHP-PIP-030 | Construct |  | JSW USL-CON-CHI-1040 |  |  | 20 | CHP-PIP-020 | SS | 10 | CHP-EQP-050 | FS | 0 |  | 2027-03-12 | 2027-04-05 |  |  | 0% | 20 | 2027-02-26 | 2027-03-23 | Not Started | -11
CHP-PIP-040 | 4 | Pump suction / discharge hook-up P-01..P-10 | Piping | All | Row B–A | ±0.000 to +2.0 | Pipes / Pipe Accessories | Pump branch lines | 1 | CHP-PIP-040 | Construct |  | JSW USL-CON-CHI-1040 |  |  | 18 | CHP-PIP-020 | SS | 12 | CHP-EQP-090 | FS | 0 |  | 2027-03-04 | 2027-03-26 |  |  | 0% | 18 | 2027-02-19 | 2027-03-12 | Not Started | -11
CHP-PIP-050 | 4 | Hydro test, flushing & reinstatement | Piping | All | Chiller hall | All | Pipes (status change) | All CHW/CW piping | 1 | CHP-PIP-050 | Construct |  | JSW USL-CON-CHI-1040 |  |  | 14 | CHP-PIP-030 | FS | 0 | CHP-PIP-040 | FS | 0 |  | 2027-04-06 | 2027-04-21 |  |  | 0% | 14 | 2027-03-24 | 2027-04-08 | Not Started | -11
JSW USL-CON-CHI-1050 | 3 | Cable tray erection incl. support, cable Laying | [6 empty] | 3 | [14 empty] | 2027-02-15 | 2027-04-09 |  |  | 0% |  | 2027-02-02 | 2027-03-27 | Not Started | -11 |  | P6 check: ✔ Same as P6
CHP-ELE-010 | 4 | Cable trays & supports – trenches T1/T2, cable pit & cable cellar | Electrical | All | Trenches & cable cellar | EL(-)1.500 to ±0.000 | Cable Trays | Cable trays | 1 | CHP-ELE-010 | Construct |  | JSW USL-CON-CHI-1050 |  |  | 20 | CHP-MS-060 | FS | 0 | CHP-EQP-010 | SS | 25 |  | 2027-02-15 | 2027-03-10 |  |  | 0% | 20 | 2027-02-02 | 2027-02-24 | Not Started | -11
CHP-ELE-020 | 4 | Cable trays & supports – chiller hall, switchgear room & first floor | Electrical | All | Chiller hall & FF | +0.000 to +8.0 | Cable Trays | Cable trays | 1 | CHP-ELE-020 | Construct |  | JSW USL-CON-CHI-1050 |  |  | 20 | CHP-ELE-010 | SS | 8 |  |  |  |  | 2027-02-24 | 2027-03-19 |  |  | 0% | 20 | 2027-02-11 | 2027-03-05 | Not Started | -11
CHP-ELE-030 | 4 | Cable laying, glanding & termination (power & control) | Electrical | All | Whole plant | All | Cable Trays (fill) / Conduits | Cables | 1 | CHP-ELE-030 | Construct |  | JSW USL-CON-CHI-1050 |  |  | 30 | CHP-ELE-010 | SS | 15 |  |  |  |  | 2027-03-04 | 2027-04-09 |  |  | 0% | 30 | 2027-02-19 | 2027-03-27 | Not Started | -11
JSW USL-CON-CHI-1060 | 3 | Other electrical works incl. light fixtures installation | [6 empty] | 3 | [14 empty] | 2027-03-04 | 2027-04-27 |  |  | 0% |  | 2027-02-19 | 2027-04-14 | Not Started | -11 |  | P6 check: ✔ Same as P6
CHP-ELE-040 | 4 | Earthing & lightning protection | Electrical | All | Whole building | All | Electrical Fixtures (earthing) | Earth grid, LPS | 1 | CHP-ELE-040 | Construct |  | JSW USL-CON-CHI-1060 |  |  | 15 | CHP-ELE-010 | SS | 15 |  |  |  |  | 2027-03-04 | 2027-03-23 |  |  | 0% | 15 | 2027-02-19 | 2027-03-08 | Not Started | -11
CHP-ELE-050 | 4 | Lighting fixtures, JBs & small power | Electrical | All | Whole building | All | Lighting Fixtures / Electrical Fixtures | Light fixtures, JBs, sockets | 1 | CHP-ELE-050 | Construct |  | JSW USL-CON-CHI-1060 |  |  | 40 | CHP-ELE-020 | SS | 12 |  |  |  |  | 2027-03-11 | 2027-04-27 |  |  | 0% | 40 | 2027-02-25 | 2027-04-14 | Not Started | -11
CHP-ELE-060 | 4 | Switchgear room panels (6.6 kV SWBD, ESS6-PDB-1) – placement & termination | Electrical | All | FF switchgear room (Row E–D) | +4.050 FFL | Electrical Equipment | 6.6kV SWBD, ESS6-PDB-1 | 1 | CHP-ELE-060 | Construct |  | JSW USL-CON-CHI-1060 |  |  | 20 | CHP-ELE-020 | SS | 7 |  |  |  |  | 2027-03-04 | 2027-03-29 |  |  | 0% | 20 | 2027-02-19 | 2027-03-15 | Not Started | -11
JSW USL-CON-CHI-1070 | 3 | Instrument installation works | [6 empty] | 2 | [14 empty] | 2027-03-24 | 2027-05-15 |  |  | 0% |  | 2027-03-10 | 2027-05-03 | Not Started | -11 |  | P6 check: ✔ Same as P6
CHP-INS-010 | 4 | Field instruments installation (PT / TT / FT / flow switches) | Instrumentation | All | Chiller hall | ±0.000 to +3.0 | Mechanical Equipment / Generic (instruments) | Field instruments | 1 | CHP-INS-010 | Construct |  | JSW USL-CON-CHI-1070 |  |  | 25 | CHP-PIP-030 | SS | 9 | CHP-ELE-030 | SS | 15 |  | 2027-03-24 | 2027-04-21 |  |  | 0% | 25 | 2027-03-10 | 2027-04-08 | Not Started | -11
CHP-INS-020 | 4 | Instrument cabling, impulse tubing & loop checks | Instrumentation | All | Chiller hall | All | Conduits / Cable Trays (fill) | Instrument cables, tubing | 1 | CHP-INS-020 | Construct |  | JSW USL-CON-CHI-1070 |  |  | 35 | CHP-INS-010 | SS | 10 |  |  |  |  | 2027-04-05 | 2027-05-15 |  |  | 0% | 35 | 2027-03-23 | 2027-05-03 | Not Started | -11
CHP-MS-100 | 4 | Chiller plant ready for Mechanical Completion (feeds JSW USL-COM-1110) | Milestone |  |  |  | — (non-BIM milestone) |  | 0 |  | Milestone |  | JSW USL-CON-CHI-1070 |  |  | 0 | CHP-INS-020 | FS | 0 | CHP-PIP-050 | FS | 0 |  | 2027-05-15 | 2027-05-15 |  |  | 0% | 0 | 2027-05-03 | 2027-05-03 | Not Started | -11 |  | Feeds P6 JSW USL-COM-1110 Mechanical Completion (28-Oct-27).
CHP.A | 2 | ADDITIONAL SCOPE – NOT IN P6 (planned by 4D team) | [6 empty] | 15 | [14 empty] | 2026-10-05 | 2027-01-04 |  |  | 0% |  | 2026-10-05 | 2027-01-04 | Not Started | 0
CHP.A1 | 3 | Masonry, lintels & architectural finishes | [6 empty] | 12 |  |  |  |  | 15 | [9 empty] | 2026-10-05 | 2027-01-04 |  |  | 0% |  | 2026-10-05 | 2027-01-04 | Not Started | 0 | 0 | No P6 activity – group dates = 4D plan. Recommend adding to P6.
CHP-ARC-010 | 4 | Brickwork 230 thk – GF Row E–D block up to lintel level | Architectural | All | Row E–D : Grid 6–1 | EL ±0.000 to +2.100 | Walls (Architectural) | Brick walls GF | 1 | CHP-ARC-010 | Construct | O24091-990-C-B-19531-005 | CHP.A1 |  |  | 12 | CHP-GRD-030 | FS | 0 |  |  |  | 2026-10-05 | 2026-10-05 | 2026-10-17 |  |  | 0% | 12 | 2026-10-05 | 2026-10-17 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-020 | 4 | Lintels & chajjas – GF (LB1–LB6) | Architectural | All | GF openings (Table-1) | B/O lintel +2.100 to +3.400 | Structural Framing (Lintel) | LB1, LB2, LB3, LB4, LB5, LB6 | 1 | CHP-ARC-020 | Construct | O24091-990-C-B-19531-006 | CHP.A1 | 6 | m³ | 6 | CHP-ARC-010 | SS | 8 |  |  |  |  | 2026-10-14 | 2026-10-21 |  |  | 0% | 6 | 2026-10-14 | 2026-10-21 | Not Started | 0 | 0 | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-030 | 4 | Brickwork – GF above lintel up to first-floor soffit | Architectural | All | Row E–D : Grid 6–1 | +2.100 to +3.400 | Walls (Architectural) | Brick walls GF | 1 | CHP-ARC-030 | Construct | O24091-990-C-B-19531-005 | CHP.A1 |  |  | 8 | CHP-ARC-020 | FS | 0 |  |  |  |  | 2026-10-22 | 2026-10-30 |  |  | 0% | 8 | 2026-10-22 | 2026-10-30 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-040 | 4 | Brickwork – FF (switchgear, AC & AHU rooms, ante rooms) up to lintel | Architectural | All | Row E–D : Grid 6–1 (FF) | +4.000 to +6.150 | Walls (Architectural) | Brick walls FF | 1 | CHP-ARC-040 | Construct | O24091-990-C-B-19531-005 | CHP.A1 |  |  | 10 | CHP-ARC-030 | SS | 4 | CHP-SUP-170 | FS | 0 |  | 2026-10-27 | 2026-11-06 |  |  | 0% | 10 | 2026-10-27 | 2026-11-06 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-050 | 4 | Lintels & chajjas – FF (LB7–LB9B) | Architectural | All | FF openings (Table-2) | B/O lintel +6.150 to +7.350 | Structural Framing (Lintel) | LB7, LB7A, LB8, LB9, LB9A, LB9B | 1 | CHP-ARC-050 | Construct | O24091-990-C-B-19531-006 | CHP.A1 | 5 | m³ | 6 | CHP-ARC-040 | SS | 7 |  |  |  |  | 2026-11-04 | 2026-11-10 |  |  | 0% | 6 | 2026-11-04 | 2026-11-10 | Not Started | 0 | 0 | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-060 | 4 | Brickwork – chiller hall external walls (Row A, Grid 1 & 6) incl. LB1A lintels & monorail-door openings | Architectural | All | Row C–A : Grid 6 / Row A / Grid 1 | ±0.000 to +9.150 | Walls (Architectural) + Lintel | Brick walls, LB1A | 1 | CHP-ARC-060 | Construct | O24091-990-C-B-19531-006 | CHP.A1 | 2 | m³ | 20 | CHP-SUP-170 | FS | 0 |  |  |  | 2026-10-12 | 2026-10-12 | 2026-11-04 |  |  | 0% | 20 | 2026-10-12 | 2026-11-04 | Not Started | 0 | 0 | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-070 | 4 | Mumty brickwork & lintels LB10–LB12 – ST-1 & ST-2 | Architectural | All | Grid 6–5.1 & 2–1 : Row E–D.1/D.2 | +9.150 to +12.150 | Walls + Structural Framing (Lintel) | Brick walls, LB10, LB11, LB12 | 1 | CHP-ARC-070 | Construct | O24091-990-C-B-19531-006 | CHP.A1 | 2 | m³ | 10 | CHP-SUP-210 | FS | 0 | CHP-SUP-190 | FS | 0 |  | 2026-10-05 | 2026-10-15 |  |  | 0% | 10 | 2026-10-05 | 2026-10-15 | Not Started | 0 | 0 | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-080 | 4 | Parapet wall, roof waterproofing, PCC wearing course & rainwater pipes | Architectural | All | Roof EL +9.150 & +12.150 | +9.150 / +12.150 | Roofs / Walls (Architectural) | Parapet, WP membrane, wearing course | 1 | CHP-ARC-080 | Construct | O24091-990-C-B-19531-004 | CHP.A1 |  |  | 15 | CHP-SUP-210 | FS | 0 | CHP-ARC-070 | SS | 3 |  | 2026-10-08 | 2026-10-26 |  |  | 0% | 15 | 2026-10-08 | 2026-10-26 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-090 | 4 | Plastering – internal & external | Architectural | All | Whole building | All | Finishes (if modelled) | Plaster | 1 | CHP-ARC-090 | Construct |  | CHP.A1 |  |  | 25 | CHP-ARC-060 | SS | 10 | CHP-ARC-050 | FS | 0 |  | 2026-11-11 | 2026-12-09 |  |  | 0% | 25 | 2026-11-11 | 2026-12-09 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-100 | 4 | Flooring & floor finishes (GF rooms, FF, staircases) | Architectural | All | Whole building | ±0.000 / +4.050 | Floors (finish) | Floor finish | 1 | CHP-ARC-100 | Construct |  | CHP.A1 |  |  | 15 | CHP-ARC-090 | SS | 10 | CHP-GRD-130 | FS | 0 |  | 2026-11-26 | 2026-12-12 |  |  | 0% | 15 | 2026-11-26 | 2026-12-12 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-110 | 4 | Doors, windows, rolling shutters & monorail doors | Architectural | All | Whole building | All | Doors / Windows | Doors, windows, RS, monorail doors | 1 | CHP-ARC-110 | Construct |  | CHP.A1 |  |  | 15 | CHP-ARC-090 | SS | 15 |  |  |  |  | 2026-11-28 | 2026-12-15 |  |  | 0% | 15 | 2026-11-28 | 2026-12-15 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP-ARC-120 | 4 | Painting – internal & external | Architectural | All | Whole building | All | Finishes (if modelled) | Paint | 1 | CHP-ARC-120 | Construct |  | CHP.A1 |  |  | 20 | CHP-ARC-090 | FS | 0 |  |  |  |  | 2026-12-10 | 2027-01-04 |  |  | 0% | 20 | 2026-12-10 | 2027-01-04 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP.A2 | 3 | Structural steel & miscellaneous | [6 empty] | 3 | [14 empty] | 2026-11-02 | 2026-11-27 |  |  | 0% |  | 2026-11-02 | 2026-11-27 | Not Started | 0 |  | No P6 activity – group dates = 4D plan. Recommend adding to P6.
CHP-STL-010 | 4 | Monorail beams MR-1 (NPB 300×150, B.O.MR +8.100) & MR-2 (NPB 500×200, B.O.MR +7.900) incl. end stoppers | Steel & misc. | All | MR-1: 2250 N of Row A ; MR-2: 3500 N of Row B ; Grid 6→beyond 1 | +7.900 / +8.100 B.O.MR | Structural Framing (Steel) | MR-1, MR-2 | 2 | CHP-STL-010 | Construct | O24091-990-C-B-19531-004 | CHP.A2 |  |  | 10 | CHP-SUP-170 | FS | 10 | CHP-SUP-160 | FS | 0 | 2026-11-02 | 2026-11-02 | 2026-11-12 |  |  | 0% | 10 | 2026-11-02 | 2026-11-12 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
CHP-STL-020 | 4 | Handrails – staircases ST-1/ST-2 & removable handrails at FF openings / platforms | Steel & misc. | All | ST-1, ST-2, FF edges | +1.300 to +12.150 | Railings | Handrails | 1 | CHP-STL-020 | Construct | O24091-990-C-B-19531-003 | CHP.A2 |  |  | 10 | CHP-SUP-210 | FS | 0 | CHP-ARC-090 | SS | 5 |  | 2026-11-17 | 2026-11-27 |  |  | 0% | 10 | 2026-11-17 | 2026-11-27 | Not Started | 0 |  | Not in P6 – planned by 4D team; BL = this plan.
Formulas:
Current Start = IF([ACTUAL – SITE INPUT]<>"",[ACTUAL – SITE INPUT],MAX(AF62:AF109))
Current Finish = IF([Actual Finish]<>"",[Actual Finish],IF([LOGIC (working days)]=0,[Current Start],INDEX(WorkDays,MATCH(MAX([Current Start],NextWD)-1,WorkDays,1)+[CURRENT SCHEDULE])))
Note on X5: Start-No-Earlier-Than constraint (hold release, crew availability or P6 date).
Note on AA5: Enter the actual start date from DPR / pour card. Leave blank if not started.
Note on AB5: Enter the actual finish date. Status becomes Completed and successors re-plan from this date.
Note on AC5: Physical % complete for activities in progress (Remaining Dur = Orig Dur × (1 – %)).

## BIM Element Map
BIM ELEMENT MAP – element → 4D activity link (Chiller Plant)
Use: add two shared/text parameters in the model (4D_Element_ID, 4D_Activity_ID) and populate them from columns A and J (Dynamo / Excel link / Navisworks property append). Then in TimeLiner use Rules to attach by 4D_Activity_ID.
Columns K–N are live look-ups from the 4D Schedule. Columns are split at construction joints (EL -0.300, +4.000, +9.150) – split model columns the same way, or attach a full-height column to its first lift only.
Element ID (suggested 4D_Element_ID) | BIM Category | Element Type / Description | Mark | Grid / Location | Zone | Level / Elevation | Size | Drawing No. | 4D Activity ID (4D_Activity_ID) | Activity Name | Current Start | Current Finish | Status | Notes
CHP-PILE-P01 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P1 | 1/A | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-010 | Piles Row A (P1–P7) | 2025-12-17 | 2025-12-20 | Completed
CHP-PILE-P02 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P2 | 2/A | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-010 | Piles Row A (P1–P7) | 2025-12-17 | 2025-12-20 | Completed
CHP-PILE-P03 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P3 | 3/A | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-010 | Piles Row A (P1–P7) | 2025-12-17 | 2025-12-20 | Completed
CHP-PILE-P04 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P4 | 4/A | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-010 | Piles Row A (P1–P7) | 2025-12-17 | 2025-12-20 | Completed
CHP-PILE-P05 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P5 | 5/A | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-010 | Piles Row A (P1–P7) | 2025-12-17 | 2025-12-20 | Completed
CHP-PILE-P06 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P6 | 5/A | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-010 | Piles Row A (P1–P7) | 2025-12-17 | 2025-12-20 | Completed
CHP-PILE-P07 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P7 | 6/A | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-010 | Piles Row A (P1–P7) | 2025-12-17 | 2025-12-20 | Completed
CHP-PILE-P08 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P8 | 1/B | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P09 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P9 | 1/B | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P10 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P10 | 2/B | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P11 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P11 | 3/B | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P12 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P12 | 4/B | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P13 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P13 | 5/B | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P14 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P14 | 5/B | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P15 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P15 | 6/B | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P16 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P16 | 6/B | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-020 | Piles Row B (P8–P16) | 2025-12-22 | 2025-12-27 | Completed
CHP-PILE-P17 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P17 | 1/C | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-030 | Piles Row C (P17–P22) | 2025-12-29 | 2025-12-31 | Completed
CHP-PILE-P18 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P18 | 2/C | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-030 | Piles Row C (P17–P22) | 2025-12-29 | 2025-12-31 | Completed
CHP-PILE-P19 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P19 | 3/C | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-030 | Piles Row C (P17–P22) | 2025-12-29 | 2025-12-31 | Completed
CHP-PILE-P20 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P20 | 4/C | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-030 | Piles Row C (P17–P22) | 2025-12-29 | 2025-12-31 | Completed
CHP-PILE-P21 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P21 | 5/C | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-030 | Piles Row C (P17–P22) | 2025-12-29 | 2025-12-31 | Completed
CHP-PILE-P22 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P22 | 6/C | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-030 | Piles Row C (P17–P22) | 2025-12-29 | 2025-12-31 | Completed
CHP-PILE-P23 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P23 | 1/D | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P24 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P24 | 1/D | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P25 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P25 | 2/D | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P26 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P26 | 2/D | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P27 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P27 | 3/D | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P28 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P28 | 3/D | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P29 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P29 | 4/D | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P30 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P30 | 4/D | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P31 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P31 | 5/D | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P32 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P32 | 5/D | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P33 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P33 | 6/D | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P34 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P34 | 6/D | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-040 | Piles Row D (P23–P34) | 2026-01-02 | 2026-01-08 | Completed
CHP-PILE-P35 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P35 | 5.1/D.1 | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | 2026-01-09 | 2026-01-13 | Completed
CHP-PILE-P36 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P36 | 5.1/D.1 | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | 2026-01-09 | 2026-01-13 | Completed
CHP-PILE-P37 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P37 | 6/D.1 | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | 2026-01-09 | 2026-01-13 | Completed
CHP-PILE-P38 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P38 | 1/D.2 | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | 2026-01-09 | 2026-01-13 | Completed
CHP-PILE-P39 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P39 | 1/D.2 | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | 2026-01-09 | 2026-01-13 | Completed
CHP-PILE-P40 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P40 | 2/D.2 | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | 2026-01-09 | 2026-01-13 | Completed
CHP-PILE-P41 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P41 | 2/D.2 | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | 2026-01-09 | 2026-01-13 | Completed
CHP-PILE-P42 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P42 | 1/E | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P43 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P43 | 2/E | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P44 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P44 | 2/E | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P45 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P45 | 3/E | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P46 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P46 | 3/E | Z1 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P47 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P47 | 4/E | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P48 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P48 | 4/E | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P49 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P49 | 5/E | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P50 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P50 | 5/E | Z2 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P51 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P51 | 5.1/E | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P52 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P52 | 5.1/E | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-PILE-P53 | Structural Foundations (Pile) | Bored cast-in-situ pile, Type-I, M30 | P53 | 6/E | Z3 | Cut-off EL(-)2.425 ; L = 26 m | 600 Ø | O24091-990-C-B-19530-001 | CHP-PIL-060 | Piles Row E (P42–P53) | 2026-01-14 | 2026-01-19 | Completed
CHP-GRP-EXC-010 | Excavation solid / Topography (if modelled) | Excavation, pile chipping & PCC prep – Zone-1 (Grid 1–3) | — | Grid 1–3 : Row E–A | Z1 | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC) |  |  | CHP-EXC-010 | Excavation, pile chipping & PCC prep – Zone-1 (Grid 1–3) | 2026-02-18 | 2026-03-07 | Completed | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-EXC-020 | Excavation solid / Topography (if modelled) | Excavation, pile chipping & PCC prep – Zone-2 (Grid 3–5) | — | Grid 3–5 : Row E–A | Z2 | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC) |  |  | CHP-EXC-020 | Excavation, pile chipping & PCC prep – Zone-2 (Grid 3–5) | 2026-03-05 | 2026-03-18 | Completed | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-EXC-030 | Excavation solid / Topography (if modelled) | Excavation, pile chipping & PCC prep – Zone-3 (Grid 5–6) | — | Grid 5–6 : Row E–A | Z3 | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC) |  |  | CHP-EXC-030 | Excavation, pile chipping & PCC prep – Zone-3 (Grid 5–6) | 2026-03-16 | 2026-03-30 | Completed | Group element – attach all model objects of this scope (if modelled)
CHP-PC-1-A | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 1/A | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-1-B | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 1/B | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-1-C | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 1/C | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-1-D | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 1/D | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-1-D.2 | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 1/D.2 | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-1-E | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 1/E | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-2-A | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 2/A | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-2-B | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 2/B | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-2-C | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 2/C | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-2-D | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 2/D | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-2-D.2 | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 2/D.2 | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-2-E | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 2/E | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-3-A | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 3/A | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-3-B | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 3/B | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-3-C | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 3/C | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-3-D | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 3/D | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-3-E | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 3/E | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | 2026-03-08 | 2026-03-25 | Completed
CHP-PC-4-A | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 4/A | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-4-B | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 4/B | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-4-C | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 4/C | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-4-D | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 4/D | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-4-E | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 4/E | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-5-A | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 5/A | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-5-B | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 5/B | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-5-C | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 5/C | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-5-D | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 5/D | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-5-E | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 5/E | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | 2026-03-19 | 2026-03-31 | Completed
CHP-PC-5.1-D.1 | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 5.1/D.1 | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | 2026-03-31 | 2026-04-08 | Completed
CHP-PC-5.1-E | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 5.1/E | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | 2026-03-31 | 2026-04-08 | Completed
CHP-PC-6-A | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 6/A | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | 2026-03-31 | 2026-04-08 | Completed
CHP-PC-6-B | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 6/B | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | 2026-03-31 | 2026-04-08 | Completed
CHP-PC-6-C | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 6/C | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | 2026-03-31 | 2026-04-08 | Completed
CHP-PC-6-D | Structural Foundations (Pile Cap) | Pile cap PC2 – 2-pile, 45° rotated | PC2 | 6/D | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 2700×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | 2026-03-31 | 2026-04-08 | Completed
CHP-PC-6-D.1 | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 6/D.1 | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | 2026-03-31 | 2026-04-08 | Completed
CHP-PC-6-E | Structural Foundations (Pile Cap) | Pile cap PC1 – single pile | PC1 | 6/E | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below) | 900×900×1000 (ref. dwg) | O24091-990-C-B-19531-001 | CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | 2026-03-31 | 2026-04-08 | Completed
CHP-COL-1-A-L0 | Structural Columns | RCC column C6 – pedestal | C6 | 1/A | Z1 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-1-B-L0 | Structural Columns | RCC column C3 – pedestal | C3 | 1/B | Z1 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-1-C-L0 | Structural Columns | RCC column C6 – pedestal | C6 | 1/C | Z1 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-1-D-L0 | Structural Columns | RCC column C7 – pedestal | C7 | 1/D | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-1-D.2-L0 | Structural Columns | RCC column C1 – pedestal | C1 | 1/D.2 | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-1-E-L0 | Structural Columns | RCC column C1 – pedestal | C1 | 1/E | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-1-SC-L0 | Structural Columns | RCC column SC1 – pedestal | SC1 | 1 / 2400 S of Row B (on PCB3) | Z1 | Top of PCB3 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-2-A-L0 | Structural Columns | RCC column C4 – pedestal | C4 | 2/A | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-2-B-L0 | Structural Columns | RCC column C4 – pedestal | C4 | 2/B | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-2-C-L0 | Structural Columns | RCC column C4 – pedestal | C4 | 2/C | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-2-D-L0 | Structural Columns | RCC column C7 – pedestal | C7 | 2/D | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-2-D.2-L0 | Structural Columns | RCC column C1 – pedestal | C1 | 2/D.2 | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-2-E-L0 | Structural Columns | RCC column C1 – pedestal | C1 | 2/E | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-3-A-L0 | Structural Columns | RCC column C4 – pedestal | C4 | 3/A | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-3-B-L0 | Structural Columns | RCC column C4 – pedestal | C4 | 3/B | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-3-C-L0 | Structural Columns | RCC column C4 – pedestal | C4 | 3/C | Z1 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-3-D-L0 | Structural Columns | RCC column C8 – pedestal | C8 | 3/D | Z1 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-3-E-L0 | Structural Columns | RCC column C9 – pedestal | C9 | 3/E | Z1 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-PCB-Z1-01 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row E : Grid 2–1 | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-02 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Grid 1 : Row E–D.2 | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-03 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Grid 1 : Row D–C | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-04 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Grid 2 : Row D–C | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-05 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Grid 3 : Row D–C | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-06 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row D : Grid 3–2 | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-07 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row C : Grid 3–2 | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-08 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row C : Grid 2–1 | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-09 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row B : Grid 2–1 | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-10 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row A : Grid 2–1 | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-11 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB2 | PCB2 | Grid 3 : Row B–A | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-12 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB2 | PCB2 | Grid 2 : Row B–A | Z1 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-13 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB3 | PCB3 | Grid 1 : Row B–SC1 | Z1 | B/O PCB EL(-)2.400 | 600x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-PCB-Z1-14 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB3 | PCB3 | Grid 1 : SC1–Row A | Z1 | B/O PCB EL(-)2.400 | 600x600 | O24091-990-C-B-19531-001 | CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | 2026-03-26 | 2026-04-11 | Completed
CHP-COL-4-A-L0 | Structural Columns | RCC column C4 – pedestal | C4 | 4/A | Z2 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-4-B-L0 | Structural Columns | RCC column C4 – pedestal | C4 | 4/B | Z2 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-4-C-L0 | Structural Columns | RCC column C5 – pedestal | C5 | 4/C | Z2 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-4-D-L0 | Structural Columns | RCC column C8 – pedestal | C8 | 4/D | Z2 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-4-E-L0 | Structural Columns | RCC column C9 – pedestal | C9 | 4/E | Z2 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-5-A-L0 | Structural Columns | RCC column C3 – pedestal | C3 | 5/A | Z2 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-5-B-L0 | Structural Columns | RCC column C6 – pedestal | C6 | 5/B | Z2 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-5-C-L0 | Structural Columns | RCC column C6 – pedestal | C6 | 5/C | Z2 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-5-D-L0 | Structural Columns | RCC column C8 – pedestal | C8 | 5/D | Z2 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-5-E-L0 | Structural Columns | RCC column C9 – pedestal | C9 | 5/E | Z2 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-PCB-Z2-01 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row D : Grid 5–4 | Z2 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed
CHP-PCB-Z2-02 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Grid 4 : Row D–C | Z2 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed
CHP-PCB-Z2-03 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Grid 5 : Row D–C | Z2 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed
CHP-PCB-Z2-04 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row C : Grid 5–4 | Z2 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed
CHP-PCB-Z2-05 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row C : Grid 4–3 | Z2 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed
CHP-PCB-Z2-06 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row B : Grid 4–3 | Z2 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed
CHP-PCB-Z2-07 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row A : Grid 4–3 | Z2 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed
CHP-PCB-Z2-08 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB2 | PCB2 | Grid 4 : Row B–A | Z2 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | 2026-04-04 | 2026-04-17 | Completed
CHP-COL-5.1-D.1-L0 | Structural Columns | RCC column C1 – pedestal | C1 | 5.1/D.1 | Z3 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-5.1-E-L0 | Structural Columns | RCC column C1 – pedestal | C1 | 5.1/E | Z3 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-6-A-L0 | Structural Columns | RCC column C3 – pedestal | C3 | 6/A | Z3 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-6-B-L0 | Structural Columns | RCC column C3 – pedestal | C3 | 6/B | Z3 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-6-C-L0 | Structural Columns | RCC column C3 – pedestal | C3 | 6/C | Z3 | EL(-)2.500 to EL(-)0.300 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-6-D-L0 | Structural Columns | RCC column C2 – pedestal | C2 | 6/D | Z3 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-6-D.1-L0 | Structural Columns | RCC column C1 – pedestal | C1 | 6/D.1 | Z3 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-COL-6-E-L0 | Structural Columns | RCC column C1 – pedestal | C1 | 6/E | Z3 | EL(-)2.500 to EL(-)0.300 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed | Split model column at EL(-)0.300 (construction joint)
CHP-PCB-Z3-01 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row E : Grid 6–5.1 | Z3 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed
CHP-PCB-Z3-02 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Grid 6 : Row E–D.1 | Z3 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed
CHP-PCB-Z3-03 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row D.1 : Grid 6–5.1 | Z3 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed
CHP-PCB-Z3-04 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Grid 6 : Row D–C | Z3 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed
CHP-PCB-Z3-05 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB1 | PCB1 | Row C : Grid 6–5 | Z3 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed
CHP-PCB-Z3-06 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB2 | PCB2 | Grid 6 : Row B–A | Z3 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed
CHP-PCB-Z3-07 | Structural Framing (Pile Cap Beam) | Pile cap beam PCB2 | PCB2 | Row A : Grid 6–5 | Z3 | B/O PCB EL(-)2.400 | 300x600 | O24091-990-C-B-19531-001 | CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | 2026-04-11 | 2026-04-22 | Completed
CHP-GRP-SUB-070 | Earthwork (if modelled) | Backfilling & compaction up to plinth level – Zone-1 | — | Grid 1–3 | Z1 | EL(-)2.500 to EL(-)0.500 |  |  | CHP-SUB-070 | Backfilling & compaction up to plinth level – Zone-1 | 2026-04-13 | 2026-04-18 | Completed | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-SUB-080 | Earthwork (if modelled) | Backfilling & compaction up to plinth level – Zone-2 | — | Grid 3–5 | Z2 | EL(-)2.500 to EL(-)0.500 |  |  | CHP-SUB-080 | Backfilling & compaction up to plinth level – Zone-2 | 2026-04-20 | 2026-04-24 | Completed | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-SUB-090 | Earthwork (if modelled) | Backfilling & compaction up to plinth level – Zone-3 | — | Grid 5–6 | Z3 | EL(-)2.500 to EL(-)0.500 |  |  | CHP-SUB-090 | Backfilling & compaction up to plinth level – Zone-3 | 2026-04-25 | 2026-04-30 | Completed | Group element – attach all model objects of this scope (if modelled)
CHP-PB-Z1-01 | Structural Framing (Plinth Beam) | Plinth beam PB2 | PB2 | Row E : Grid 3–2–1 | Z1 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-02 | Structural Framing (Plinth Beam) | Plinth beam PB10 | PB10 | Stair ST-2 : 2100 from Grid 1, Row E–D.2 | Z1 | T.O.B EL(-)0.300 | 300x450 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-03 | Structural Framing (Plinth Beam) | Plinth beam PB5 | PB5 | Grid 2 : Row E–D | Z1 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-04 | Structural Framing (Plinth Beam) | Plinth beam PB5 | PB5 | Grid 1 : Row E–C | Z1 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-05 | Structural Framing (Plinth Beam) | Plinth beam PB9 | PB9 | Row D.2 : Grid 2–1 | Z1 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-06 | Structural Framing (Plinth Beam) | Plinth beam PB7 | PB7 | Grid 2–1 : 1850 & 3500 below D.2 (2 nos) | Z1 | T.O.B EL(-)0.300 | 300x500 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-07 | Structural Framing (Plinth Beam) | Plinth beam PB4 | PB4 | Grid 2–1 : 2035 from Grid 2 | Z1 | T.O.B EL(-)0.300 | 300x450 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-08 | Structural Framing (Plinth Beam) | Plinth beam PB8 | PB8 | Row D : Grid 3–2–1 | Z1 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-09 | Structural Framing (Plinth Beam) | Plinth beam PB8 | PB8 | Grid 3 : Row E–D | Z1 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-10 | Structural Framing (Plinth Beam) | Plinth beam PB1 | PB1 | Grid 3 & Grid 2 : Row C–B | Z1 | T.O.B EL(-)0.300 | 300x500 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-11 | Structural Framing (Plinth Beam) | Plinth beam PB1 | PB1 | Row B : Grid 3–2 | Z1 | T.O.B EL(-)0.300 | 300x500 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-12 | Structural Framing (Plinth Beam) | Plinth beam PB6 | PB6 | Grid 1 : Row C–B–A (monorail door) | Z1 | T.O.B EL(-)0.300 | 450x700 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z1-13 | Structural Framing (Plinth Beam) | Plinth beam PB3 | PB3 | Row A : Grid 3–2–1 | Z1 | T.O.B EL(-)0.300 | 450x700 | O24091-990-C-B-19531-002 | CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | 2026-04-20 | 2026-05-04 | Completed
CHP-PB-Z2-01 | Structural Framing (Plinth Beam) | Plinth beam PB2 | PB2 | Row E : Grid 5–4–3 | Z2 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-110 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | 2026-04-27 | 2026-05-08 | Completed
CHP-PB-Z2-02 | Structural Framing (Plinth Beam) | Plinth beam PB8 | PB8 | Grid 5 & Grid 4 : Row E–D | Z2 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-110 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | 2026-04-27 | 2026-05-08 | Completed
CHP-PB-Z2-03 | Structural Framing (Plinth Beam) | Plinth beam PB8 | PB8 | Row D : Grid 5–4–3 | Z2 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-110 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | 2026-04-27 | 2026-05-08 | Completed
CHP-PB-Z2-04 | Structural Framing (Plinth Beam) | Plinth beam PB1 | PB1 | Grid 5 & Grid 4 : Row C–B | Z2 | T.O.B EL(-)0.300 | 300x500 | O24091-990-C-B-19531-002 | CHP-SUB-110 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | 2026-04-27 | 2026-05-08 | Completed
CHP-PB-Z2-05 | Structural Framing (Plinth Beam) | Plinth beam PB1 | PB1 | Row B : Grid 5–4 | Z2 | T.O.B EL(-)0.300 | 300x500 | O24091-990-C-B-19531-002 | CHP-SUB-110 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | 2026-04-27 | 2026-05-08 | Completed
CHP-PB-Z2-06 | Structural Framing (Plinth Beam) | Plinth beam PB3 | PB3 | Row A : Grid 5–4–3 | Z2 | T.O.B EL(-)0.300 | 450x700 | O24091-990-C-B-19531-002 | CHP-SUB-110 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | 2026-04-27 | 2026-05-08 | Completed
CHP-PB-Z3-01 | Structural Framing (Plinth Beam) | Plinth beam PB2 | PB2 | Row E : Grid 6–5.1–5 | Z3 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | 2026-05-04 | 2026-05-14 | Completed
CHP-PB-Z3-02 | Structural Framing (Plinth Beam) | Plinth beam PB10 | PB10 | Stair ST-1 : 2100 below Row E, Grid 6–5.1 | Z3 | T.O.B EL(-)0.300 | 300x450 | O24091-990-C-B-19531-002 | CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | 2026-05-04 | 2026-05-14 | Completed
CHP-PB-Z3-03 | Structural Framing (Plinth Beam) | Plinth beam PB1 | PB1 | Grid 5.1 : Row E–D.1 | Z3 | T.O.B EL(-)0.300 | 300x500 | O24091-990-C-B-19531-002 | CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | 2026-05-04 | 2026-05-14 | Completed
CHP-PB-Z3-04 | Structural Framing (Plinth Beam) | Plinth beam PB1 | PB1 | Row D.1 : Grid 6–5.1 | Z3 | T.O.B EL(-)0.300 | 300x500 | O24091-990-C-B-19531-002 | CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | 2026-05-04 | 2026-05-14 | Completed
CHP-PB-Z3-05 | Structural Framing (Plinth Beam) | Plinth beam PB5 | PB5 | Grid 6 : Row E–C | Z3 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | 2026-05-04 | 2026-05-14 | Completed
CHP-PB-Z3-06 | Structural Framing (Plinth Beam) | Plinth beam PB9 | PB9 | Row D : Grid 6–5 | Z3 | T.O.B EL(-)0.300 | 300x600 | O24091-990-C-B-19531-002 | CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | 2026-05-04 | 2026-05-14 | Completed
CHP-PB-Z3-07 | Structural Framing (Plinth Beam) | Plinth beam PB3 | PB3 | Grid 6 : Row C–B–A | Z3 | T.O.B EL(-)0.300 | 450x700 | O24091-990-C-B-19531-002 | CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | 2026-05-04 | 2026-05-14 | Completed
CHP-PB-Z3-08 | Structural Framing (Plinth Beam) | Plinth beam PB3 | PB3 | Row A : Grid 6–5 | Z3 | T.O.B EL(-)0.300 | 450x700 | O24091-990-C-B-19531-002 | CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | 2026-05-04 | 2026-05-14 | Completed
CHP-COL-1-A-L1 | Structural Columns | RCC column C6 – lift 1 | C6 | 1/A | Z1 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-1-B-L1 | Structural Columns | RCC column C3 – lift 1 | C3 | 1/B | Z1 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-1-C-L1 | Structural Columns | RCC column C6 – lift 1 | C6 | 1/C | Z1 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-1-D-L1 | Structural Columns | RCC column C7 – lift 1 | C7 | 1/D | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-1-D.2-L1 | Structural Columns | RCC column C1 – lift 1 | C1 | 1/D.2 | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-1-E-L1 | Structural Columns | RCC column C1 – lift 1 | C1 | 1/E | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-1-SC-L1 | Structural Columns | RCC column SC1 – lift 1 | SC1 | 1 / 2400 S of Row B (on PCB3) | Z1 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-2-A-L1 | Structural Columns | RCC column C4 – lift 1 | C4 | 2/A | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-2-B-L1 | Structural Columns | RCC column C4 – lift 1 | C4 | 2/B | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-2-C-L1 | Structural Columns | RCC column C4 – lift 1 | C4 | 2/C | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-2-D-L1 | Structural Columns | RCC column C7 – lift 1 | C7 | 2/D | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-2-D.2-L1 | Structural Columns | RCC column C1 – lift 1 | C1 | 2/D.2 | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-2-E-L1 | Structural Columns | RCC column C1 – lift 1 | C1 | 2/E | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-3-A-L1 | Structural Columns | RCC column C4 – lift 1 | C4 | 3/A | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-3-B-L1 | Structural Columns | RCC column C4 – lift 1 | C4 | 3/B | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-3-C-L1 | Structural Columns | RCC column C4 – lift 1 | C4 | 3/C | Z1 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-3-D-L1 | Structural Columns | RCC column C8 – lift 1 | C8 | 3/D | Z1 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-3-E-L1 | Structural Columns | RCC column C9 – lift 1 | C9 | 3/E | Z1 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | 2026-05-05 | 2026-05-20 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-4-A-L1 | Structural Columns | RCC column C4 – lift 1 | C4 | 4/A | Z2 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-4-B-L1 | Structural Columns | RCC column C4 – lift 1 | C4 | 4/B | Z2 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-4-C-L1 | Structural Columns | RCC column C5 – lift 1 | C5 | 4/C | Z2 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-4-D-L1 | Structural Columns | RCC column C8 – lift 1 | C8 | 4/D | Z2 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-4-E-L1 | Structural Columns | RCC column C9 – lift 1 | C9 | 4/E | Z2 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-5-A-L1 | Structural Columns | RCC column C3 – lift 1 | C3 | 5/A | Z2 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-5-B-L1 | Structural Columns | RCC column C6 – lift 1 | C6 | 5/B | Z2 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-5-C-L1 | Structural Columns | RCC column C6 – lift 1 | C6 | 5/C | Z2 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-5-D-L1 | Structural Columns | RCC column C8 – lift 1 | C8 | 5/D | Z2 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-5-E-L1 | Structural Columns | RCC column C9 – lift 1 | C9 | 5/E | Z2 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | 2026-05-13 | 2026-05-23 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-5.1-D.1-L1 | Structural Columns | RCC column C1 – lift 1 | C1 | 5.1/D.1 | Z3 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | 2026-05-19 | 2026-05-27 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-5.1-E-L1 | Structural Columns | RCC column C1 – lift 1 | C1 | 5.1/E | Z3 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | 2026-05-19 | 2026-05-27 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-6-A-L1 | Structural Columns | RCC column C3 – lift 1 | C3 | 6/A | Z3 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | 2026-05-19 | 2026-05-27 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-6-B-L1 | Structural Columns | RCC column C3 – lift 1 | C3 | 6/B | Z3 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | 2026-05-19 | 2026-05-27 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-6-C-L1 | Structural Columns | RCC column C3 – lift 1 | C3 | 6/C | Z3 | EL(-)0.300 to EL(+)4.000 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | 2026-05-19 | 2026-05-27 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-6-D-L1 | Structural Columns | RCC column C2 – lift 1 | C2 | 6/D | Z3 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | 2026-05-19 | 2026-05-27 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-6-D.1-L1 | Structural Columns | RCC column C1 – lift 1 | C1 | 6/D.1 | Z3 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | 2026-05-19 | 2026-05-27 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-COL-6-E-L1 | Structural Columns | RCC column C1 – lift 1 | C1 | 6/E | Z3 | EL(-)0.300 to EL(+)4.000 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | 2026-05-19 | 2026-05-27 | Completed | Split model column at EL(+)4.000 (construction joint)
CHP-FF-TB1 | Structural Framing (Tie Beam) | Tie beam TB1 | TB1 | Grid 1 : Row D–C | Z1 | T.O.B EL(+)2.100 | ref. dwg | O24091-990-C-B-19531-003 | CHP-SUP-040 | Tie beam TB1 (TOB EL +2.100) at Grid 1 | 2026-05-12 | 2026-05-16 | Completed
CHP-ST2-LOWER-FLT | Stairs | RCC staircase ST-2 flights (lower) | FLT-1..FLT-3 | Grid 2–1 / Row E–D.2 | Z1 | EL(-)0.050 to EL(+)4.000 | Waist slab (Type-1/Type-2) | O24091-990-C-B-19531-005 | CHP-SUP-050 | Staircase ST-2 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | 2026-05-21 | 2026-06-06 | Completed
CHP-ST2-LOWER-LDG | Floors (Landing) | RCC landings ST-2 (lower) | Landings +1.300, +2.650 | Grid 2–1 / Row E–D.2 | Z1 | EL(-)0.050 to EL(+)4.000 | 150 thk | O24091-990-C-B-19531-005 | CHP-SUP-050 | Staircase ST-2 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | 2026-05-21 | 2026-06-06 | Completed
CHP-ST2-LOWER-STB | Structural Framing (Stair Beam) | Stair beams ST-2 (lower) | STB1 / STB2 | Grid 2–1 / Row E–D.2 | Z1 | EL(-)0.050 to EL(+)4.000 | 300×500 (ref. dwg) | O24091-990-C-B-19531-005 | CHP-SUP-050 | Staircase ST-2 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | 2026-05-21 | 2026-06-06 | Completed
CHP-FF-Z1-01 | Structural Framing (Floor Beam) | Floor beam FB1 | FB1 | Row D : Grid 3–1 | Z1 | T.O.C EL(+)4.000 | 400x600 | O24091-990-C-B-19531-003 | CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | 2026-05-21 | 2026-06-17 | Completed
CHP-FF-Z1-02 | Structural Framing (Floor Beam) | Floor beam FB4 | FB4 | Row E : Grid 3–1 | Z1 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | 2026-05-21 | 2026-06-17 | Completed
CHP-FF-Z1-03 | Structural Framing (Floor Beam) | Floor beam FB5 | FB5 | Ante room : Row E–D.2 (Grid 3–2) | Z1 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | 2026-05-21 | 2026-06-17 | Completed
CHP-FF-Z1-04 | Structural Framing (Floor Beam) | Floor beam FB9 | FB9 | Grid 3 & Grid 1 : Row E–D | Z1 | T.O.C EL(+)4.000 | 400x1000 | O24091-990-C-B-19531-003 | CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | 2026-05-21 | 2026-06-17 | Completed
CHP-FF-Z1-05 | Structural Framing (Floor Beam) | Floor beam FB10 | FB10 | Grid 2 : Row D.2–D | Z1 | T.O.C EL(+)4.000 | 400x1000 | O24091-990-C-B-19531-003 | CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | 2026-05-21 | 2026-06-17 | Completed
CHP-FF-Z1-06 | Structural Framing (Floor Beam) | Floor beam FB11/FB12/FB13 | FB11/FB12/FB13 | Secondary beams Grid 3–2 | Z1 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | 2026-05-21 | 2026-06-17 | Completed
CHP-FF-Z1-07 | Structural Framing (Floor Beam) | Floor beam FB14 | FB14 | AHU platform edge east of Grid 1 | Z1 | T.O.C EL(+)4.000 | 300x500 | O24091-990-C-B-19531-003 | CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | 2026-05-21 | 2026-06-17 | Completed
CHP-FF-Z1-08 | Floors (Structural slab) | RCC slab 150 thk, M30 | SLAB-FF | First floor slab Grid 3–1 (excl. ST-2 & openings) | Z1 | T.O.C EL(+)4.000 | 150 thk | O24091-990-C-B-19531-003 | CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | 2026-05-21 | 2026-06-17 | Completed
CHP-FF-Z2-01 | Structural Framing (Floor Beam) | Floor beam FB1 | FB1 | Row D : Grid 5–3 | Z2 | T.O.C EL(+)4.000 | 400x600 | O24091-990-C-B-19531-003 | CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | 2026-06-04 | 2026-06-29 | Completed
CHP-FF-Z2-02 | Structural Framing (Floor Beam) | Floor beam FB4 | FB4 | Row E : Grid 5–3 | Z2 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | 2026-06-04 | 2026-06-29 | Completed
CHP-FF-Z2-03 | Structural Framing (Floor Beam) | Floor beam FB2 | FB2 | Row D.1 : Grid 5–3 | Z2 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | 2026-06-04 | 2026-06-29 | Completed
CHP-FF-Z2-04 | Structural Framing (Floor Beam) | Floor beam FB8 | FB8 | Grid 5 : Row E–D | Z2 | T.O.C EL(+)4.000 | 400x1000 | O24091-990-C-B-19531-003 | CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | 2026-06-04 | 2026-06-29 | Completed
CHP-FF-Z2-05 | Structural Framing (Floor Beam) | Floor beam FB9 | FB9 | Grid 4 : Row E–D | Z2 | T.O.C EL(+)4.000 | 400x1000 | O24091-990-C-B-19531-003 | CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | 2026-06-04 | 2026-06-29 | Completed
CHP-FF-Z2-06 | Structural Framing (Floor Beam) | Floor beam FB11/FB12/FB13 | FB11/FB12/FB13 | Secondary beams Grid 5–3 | Z2 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | 2026-06-04 | 2026-06-29 | Completed
CHP-FF-Z2-07 | Floors (Structural slab) | RCC slab 150 thk, M30 | SLAB-FF | First floor slab Grid 5–3 (with floor openings) | Z2 | T.O.C EL(+)4.000 | 150 thk | O24091-990-C-B-19531-003 | CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | 2026-06-04 | 2026-06-29 | Completed
CHP-FF-Z3-01 | Structural Framing (Floor Beam) | Floor beam FB1 | FB1 | Row D : Grid 6–5 | Z3 | T.O.C EL(+)4.000 | 400x600 | O24091-990-C-B-19531-003 | CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | 2026-06-16 | 2026-07-08 | Completed
CHP-FF-Z3-02 | Structural Framing (Floor Beam) | Floor beam FB2/FB3 | FB2/FB3 | Row D.1 : Grid 6–5 | Z3 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | 2026-06-16 | 2026-07-08 | Completed
CHP-FF-Z3-03 | Structural Framing (Floor Beam) | Floor beam FB4 | FB4 | Row E : Grid 6–5 | Z3 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | 2026-06-16 | 2026-07-08 | Completed
CHP-FF-Z3-04 | Structural Framing (Floor Beam) | Floor beam FB6/FB7 | FB6/FB7 | Grid 6 & 5.1 : Row D.1–D (ante room) | Z3 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | 2026-06-16 | 2026-07-08 | Completed
CHP-FF-Z3-05 | Structural Framing (Floor Beam) | Floor beam FB11/FB12/FB13 | FB11/FB12/FB13 | Secondary beams Grid 5.1–5 | Z3 | T.O.C EL(+)4.000 | 300x600 | O24091-990-C-B-19531-003 | CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | 2026-06-16 | 2026-07-08 | Completed
CHP-FF-Z3-06 | Structural Framing (Floor Beam) | Floor beam FB14 | FB14 | Platform edge north of Row E (Grid 5.1–5) | Z3 | T.O.C EL(+)4.000 | 300x500 | O24091-990-C-B-19531-003 | CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | 2026-06-16 | 2026-07-08 | Completed
CHP-FF-Z3-07 | Floors (Structural slab) | RCC slab 150 thk, M30 | SLAB-FF | First floor slab Grid 6–5 (excl. ST-1) | Z3 | T.O.C EL(+)4.000 | 150 thk | O24091-990-C-B-19531-003 | CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | 2026-06-16 | 2026-07-08 | Completed
CHP-ST1-LOWER-FLT | Stairs | RCC staircase ST-1 flights (lower) | FLT-1..FLT-3 | Grid 6–5.1 / Row E–D.1 | Z3 | EL(-)0.050 to EL(+)4.000 | Waist slab (Type-1/Type-2) | O24091-990-C-B-19531-005 | CHP-SUP-090 | Staircase ST-1 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | 2026-05-28 | 2026-06-13 | Completed
CHP-ST1-LOWER-LDG | Floors (Landing) | RCC landings ST-1 (lower) | Landings +1.300, +2.650 | Grid 6–5.1 / Row E–D.1 | Z3 | EL(-)0.050 to EL(+)4.000 | 150 thk | O24091-990-C-B-19531-005 | CHP-SUP-090 | Staircase ST-1 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | 2026-05-28 | 2026-06-13 | Completed
CHP-ST1-LOWER-STB | Structural Framing (Stair Beam) | Stair beams ST-1 (lower) | STB1 / STB2 | Grid 6–5.1 / Row E–D.1 | Z3 | EL(-)0.050 to EL(+)4.000 | 300×500 (ref. dwg) | O24091-990-C-B-19531-005 | CHP-SUP-090 | Staircase ST-1 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | 2026-05-28 | 2026-06-13 | Completed
CHP-COL-1-A-L2 | Structural Columns | RCC column C6 – lift 2 | C6 | 1/A | Z1 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-1-B-L2 | Structural Columns | RCC column C3 – lift 2 | C3 | 1/B | Z1 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-1-C-L2 | Structural Columns | RCC column C6 – lift 2 | C6 | 1/C | Z1 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-1-D-L2 | Structural Columns | RCC column C7 – lift 2 | C7 | 1/D | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-1-D.2-L2 | Structural Columns | RCC column C1 – lift 2 | C1 | 1/D.2 | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-1-E-L2 | Structural Columns | RCC column C1 – lift 2 | C1 | 1/E | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-1-SC-L2 | Structural Columns | RCC column SC1 – lift 2 | SC1 | 1 / 2400 S of Row B (on PCB3) | Z1 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-2-A-L2 | Structural Columns | RCC column C4 – lift 2 | C4 | 2/A | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-2-B-L2 | Structural Columns | RCC column C4 – lift 2 | C4 | 2/B | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-2-C-L2 | Structural Columns | RCC column C4 – lift 2 | C4 | 2/C | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-2-D-L2 | Structural Columns | RCC column C7 – lift 2 | C7 | 2/D | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-2-D.2-L2 | Structural Columns | RCC column C1 – lift 2 | C1 | 2/D.2 | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-2-E-L2 | Structural Columns | RCC column C1 – lift 2 | C1 | 2/E | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-3-A-L2 | Structural Columns | RCC column C4 – lift 2 | C4 | 3/A | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-3-B-L2 | Structural Columns | RCC column C4 – lift 2 | C4 | 3/B | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-3-C-L2 | Structural Columns | RCC column C4 – lift 2 | C4 | 3/C | Z1 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-3-D-L2 | Structural Columns | RCC column C8 – lift 2 | C8 | 3/D | Z1 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-3-E-L2 | Structural Columns | RCC column C9 – lift 2 | C9 | 3/E | Z1 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | 2026-06-18 | 2026-07-08 | Completed
CHP-COL-4-A-L2 | Structural Columns | RCC column C4 – lift 2 | C4 | 4/A | Z2 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-4-B-L2 | Structural Columns | RCC column C4 – lift 2 | C4 | 4/B | Z2 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-4-C-L2 | Structural Columns | RCC column C5 – lift 2 | C5 | 4/C | Z2 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-4-D-L2 | Structural Columns | RCC column C8 – lift 2 | C8 | 4/D | Z2 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-4-E-L2 | Structural Columns | RCC column C9 – lift 2 | C9 | 4/E | Z2 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-5-A-L2 | Structural Columns | RCC column C3 – lift 2 | C3 | 5/A | Z2 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-5-B-L2 | Structural Columns | RCC column C6 – lift 2 | C6 | 5/B | Z2 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-5-C-L2 | Structural Columns | RCC column C6 – lift 2 | C6 | 5/C | Z2 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-5-D-L2 | Structural Columns | RCC column C8 – lift 2 | C8 | 5/D | Z2 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-5-E-L2 | Structural Columns | RCC column C9 – lift 2 | C9 | 5/E | Z2 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | 2026-06-30 | 2026-07-15 | Completed
CHP-COL-5.1-D.1-L2 | Structural Columns | RCC column C1 – lift 2 | C1 | 5.1/D.1 | Z3 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | 2026-07-09 | 2026-07-22 | Completed
CHP-COL-5.1-E-L2 | Structural Columns | RCC column C1 – lift 2 | C1 | 5.1/E | Z3 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | 2026-07-09 | 2026-07-22 | Completed
CHP-COL-6-A-L2 | Structural Columns | RCC column C3 – lift 2 | C3 | 6/A | Z3 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | 2026-07-09 | 2026-07-22 | Completed
CHP-COL-6-B-L2 | Structural Columns | RCC column C3 – lift 2 | C3 | 6/B | Z3 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | 2026-07-09 | 2026-07-22 | Completed
CHP-COL-6-C-L2 | Structural Columns | RCC column C3 – lift 2 | C3 | 6/C | Z3 | EL(+)4.000 to EL(+)9.150 | 500x600 | O24091-990-C-B-19531-001 | CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | 2026-07-09 | 2026-07-22 | Completed
CHP-COL-6-D-L2 | Structural Columns | RCC column C2 – lift 2 | C2 | 6/D | Z3 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | 2026-07-09 | 2026-07-22 | Completed
CHP-COL-6-D.1-L2 | Structural Columns | RCC column C1 – lift 2 | C1 | 6/D.1 | Z3 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | 2026-07-09 | 2026-07-22 | Completed
CHP-COL-6-E-L2 | Structural Columns | RCC column C1 – lift 2 | C1 | 6/E | Z3 | EL(+)4.000 to EL(+)9.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | 2026-07-09 | 2026-07-22 | Completed
CHP-ST2-UPPER-FLT | Stairs | RCC staircase ST-2 flights (upper) | FLT-4..FLT-7 | Grid 2–1 / Row E–D.2 | Z1 | EL(+)4.000 to EL(+)9.150 | Waist slab (Type-1/Type-2) | O24091-990-C-B-19531-005 | CHP-SUP-130 | Staircase ST-2 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | 2026-06-18 | 2026-07-13 | Completed
CHP-ST2-UPPER-LDG | Floors (Landing) | RCC landings ST-2 (upper) | Landings +5.350, +6.700, +7.900 | Grid 2–1 / Row E–D.2 | Z1 | EL(+)4.000 to EL(+)9.150 | 150 thk | O24091-990-C-B-19531-005 | CHP-SUP-130 | Staircase ST-2 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | 2026-06-18 | 2026-07-13 | Completed
CHP-ST2-UPPER-STB | Structural Framing (Stair Beam) | Stair beams ST-2 (upper) | STB1 / STB2 | Grid 2–1 / Row E–D.2 | Z1 | EL(+)4.000 to EL(+)9.150 | 300×500 (ref. dwg) | O24091-990-C-B-19531-005 | CHP-SUP-130 | Staircase ST-2 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | 2026-06-18 | 2026-07-13 | Completed
CHP-ST1-UPPER-FLT | Stairs | RCC staircase ST-1 flights (upper) | FLT-4..FLT-7 | Grid 6–5.1 / Row E–D.1 | Z3 | EL(+)4.000 to EL(+)9.150 | Waist slab (Type-1/Type-2) | O24091-990-C-B-19531-005 | CHP-SUP-140 | Staircase ST-1 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | 2026-07-09 | 2026-08-03 | Completed
CHP-ST1-UPPER-LDG | Floors (Landing) | RCC landings ST-1 (upper) | Landings +5.350, +6.700, +7.900 | Grid 6–5.1 / Row E–D.1 | Z3 | EL(+)4.000 to EL(+)9.150 | 150 thk | O24091-990-C-B-19531-005 | CHP-SUP-140 | Staircase ST-1 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | 2026-07-09 | 2026-08-03 | Completed
CHP-ST1-UPPER-STB | Structural Framing (Stair Beam) | Stair beams ST-1 (upper) | STB1 / STB2 | Grid 6–5.1 / Row E–D.1 | Z3 | EL(+)4.000 to EL(+)9.150 | 300×500 (ref. dwg) | O24091-990-C-B-19531-005 | CHP-SUP-140 | Staircase ST-1 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | 2026-07-09 | 2026-08-03 | Completed
CHP-RF-Z1-01 | Structural Framing (Roof Beam) | Roof beam RB1 | RB1 | Row E : Grid 3–2 | Z1 | T.O.C EL(+)9.150 | 300x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-02 | Structural Framing (Roof Beam) | Roof beam RB2 | RB2 | Row D : Grid 3–1 | Z1 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-03 | Structural Framing (Roof Beam) | Roof beam RB3 | RB3 | Row C : Grid 3–1 | Z1 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-04 | Structural Framing (Roof Beam) | Roof beam RB4 | RB4 | Row B : Grid 3–1 | Z1 | T.O.C EL(+)9.150 | 450x800 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-05 | Structural Framing (Roof Beam) | Roof beam RB5 | RB5 | Row A : Grid 3–1 | Z1 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-06 | Structural Framing (Roof Beam) | Roof beam RB6 | RB6 | East edge beyond Grid 1 : Row C–A | Z1 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-07 | Structural Framing (Roof Beam) | Roof beam RB7 | RB7 | Grid 3, 2 & 1 : Row C–A | Z1 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-08 | Structural Framing (Roof Beam) | Roof beam RB8 | RB8 | Secondary beams Grid 3–1 : Row C–A | Z1 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-09 | Structural Framing (Roof Beam) | Roof beam RB10/RB11 | RB10/RB11 | Secondary beams Row E–D | Z1 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-10 | Structural Framing (Roof Beam) | Roof beam RB12/RB13 | RB12/RB13 | Tank support & ST-2 edge beams | Z1 | T.O.C EL(+)9.150 | 300x500 / 300x600 | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z1-11 | Floors / Roofs (Structural slab) | RCC roof slab 150 thk, M30 | SLAB-RF | Roof slab Grid 3–1 (Row E–A) | Z1 | T.O.C EL(+)9.150 | 150 thk | O24091-990-C-B-19531-004 | CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | 2026-07-09 | 2026-08-12 | Completed
CHP-RF-Z2-01 | Structural Framing (Roof Beam) | Roof beam RB1 | RB1 | Row E : Grid 5–3 | Z2 | T.O.C EL(+)9.150 | 300x600 | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z2-02 | Structural Framing (Roof Beam) | Roof beam RB2 | RB2 | Row D : Grid 5–3 | Z2 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z2-03 | Structural Framing (Roof Beam) | Roof beam RB3 | RB3 | Row C : Grid 5–3 | Z2 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z2-04 | Structural Framing (Roof Beam) | Roof beam RB4 | RB4 | Row B : Grid 5–3 | Z2 | T.O.C EL(+)9.150 | 450x800 | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z2-05 | Structural Framing (Roof Beam) | Roof beam RB5 | RB5 | Row A : Grid 5–3 | Z2 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z2-06 | Structural Framing (Roof Beam) | Roof beam RB7 | RB7 | Grid 5 & 4 : Row C–A | Z2 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z2-07 | Structural Framing (Roof Beam) | Roof beam RB8 | RB8 | Secondary beams Grid 5–3 : Row C–A | Z2 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z2-08 | Structural Framing (Roof Beam) | Roof beam RB10 | RB10 | Secondary beams Row E–D | Z2 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z2-09 | Floors / Roofs (Structural slab) | RCC roof slab 150 thk, M30 | SLAB-RF | Roof slab Grid 5–3 (Row E–A) | Z2 | T.O.C EL(+)9.150 | 150 thk | O24091-990-C-B-19531-004 | CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | 2026-07-27 | 2026-08-28 | Completed
CHP-RF-Z3-01 | Structural Framing (Roof Beam) | Roof beam RB1 | RB1 | Row E Grid 5.1–5 & Grid 6 : Row D–A | Z3 | T.O.C EL(+)9.150 | 300x600 | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-RF-Z3-02 | Structural Framing (Roof Beam) | Roof beam RB2 | RB2 | Row D : Grid 6–5 | Z3 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-RF-Z3-03 | Structural Framing (Roof Beam) | Roof beam RB3 | RB3 | Row C : Grid 6–5 | Z3 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-RF-Z3-04 | Structural Framing (Roof Beam) | Roof beam RB4 | RB4 | Row B : Grid 6–5 | Z3 | T.O.C EL(+)9.150 | 450x800 | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-RF-Z3-05 | Structural Framing (Roof Beam) | Roof beam RB5 | RB5 | Row A : Grid 6–5 | Z3 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-RF-Z3-06 | Structural Framing (Roof Beam) | Roof beam RB8 | RB8 | Secondary beams Grid 6–5 : Row C–A | Z3 | T.O.C EL(+)9.150 | 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-RF-Z3-07 | Structural Framing (Roof Beam) | Roof beam RB9/RB10 | RB9/RB10 | Grid 5.1 : Row D.1–D & secondaries | Z3 | T.O.C EL(+)9.150 | 300x600 / 400x600 | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-RF-Z3-08 | Structural Framing (Roof Beam) | Roof beam RB14 | RB14 | Row D.1 : Grid 6–5.1 (ST-1 edge) | Z3 | T.O.C EL(+)9.150 | 300x500 | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-RF-Z3-09 | Floors / Roofs (Structural slab) | RCC roof slab 150 thk, M30 | SLAB-RF | Roof slab Grid 6–5 (Row E–A, excl. ST-1) | Z3 | T.O.C EL(+)9.150 | 150 thk | O24091-990-C-B-19531-004 | CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | 2026-08-12 | 2026-09-09 | Completed
CHP-COL-1-D.2-L3 | Structural Columns | RCC column C1 – mumty | C1 | 1/D.2 | Z1 | EL(+)9.150 to EL(+)12.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-180 | Mumty columns (EL +9.150 to +12.150) – ST-2 (C1 ×4) | 2026-08-13 | 2026-08-22 | Completed
CHP-COL-1-E-L3 | Structural Columns | RCC column C1 – mumty | C1 | 1/E | Z1 | EL(+)9.150 to EL(+)12.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-180 | Mumty columns (EL +9.150 to +12.150) – ST-2 (C1 ×4) | 2026-08-13 | 2026-08-22 | Completed
CHP-COL-2-D.2-L3 | Structural Columns | RCC column C1 – mumty | C1 | 2/D.2 | Z1 | EL(+)9.150 to EL(+)12.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-180 | Mumty columns (EL +9.150 to +12.150) – ST-2 (C1 ×4) | 2026-08-13 | 2026-08-22 | Completed
CHP-COL-2-E-L3 | Structural Columns | RCC column C1 – mumty | C1 | 2/E | Z1 | EL(+)9.150 to EL(+)12.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-180 | Mumty columns (EL +9.150 to +12.150) – ST-2 (C1 ×4) | 2026-08-13 | 2026-08-22 | Completed
CHP-MR-ST2-RB | Structural Framing (Roof Beam) | Mumty roof beams ST-2 | RB15 / RB16 | Grid 2–1 / Row E–D.2 | Z1 | T.O.C EL(+)12.150 | 300×500 | O24091-990-C-B-19531-004 | CHP-SUP-190 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-2 | 2026-08-24 | 2026-09-05 | Completed
CHP-MR-ST2-SLAB | Floors / Roofs (Structural slab) | Mumty roof slab ST-2 | SLAB 150 | Grid 2–1 / Row E–D.2 | Z1 | T.O.C EL(+)12.150 | 150 thk | O24091-990-C-B-19531-004 | CHP-SUP-190 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-2 | 2026-08-24 | 2026-09-05 | Completed
CHP-COL-5.1-D.1-L3 | Structural Columns | RCC column C1 – mumty | C1 | 5.1/D.1 | Z3 | EL(+)9.150 to EL(+)12.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-200 | Mumty columns (EL +9.150 to +12.150) – ST-1 (C1 ×4) | 2026-09-10 | 2026-09-18 | Completed
CHP-COL-5.1-E-L3 | Structural Columns | RCC column C1 – mumty | C1 | 5.1/E | Z3 | EL(+)9.150 to EL(+)12.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-200 | Mumty columns (EL +9.150 to +12.150) – ST-1 (C1 ×4) | 2026-09-10 | 2026-09-18 | Completed
CHP-COL-6-D.1-L3 | Structural Columns | RCC column C1 – mumty | C1 | 6/D.1 | Z3 | EL(+)9.150 to EL(+)12.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-200 | Mumty columns (EL +9.150 to +12.150) – ST-1 (C1 ×4) | 2026-09-10 | 2026-09-18 | Completed
CHP-COL-6-E-L3 | Structural Columns | RCC column C1 – mumty | C1 | 6/E | Z3 | EL(+)9.150 to EL(+)12.150 | 400x600 | O24091-990-C-B-19531-001 | CHP-SUP-200 | Mumty columns (EL +9.150 to +12.150) – ST-1 (C1 ×4) | 2026-09-10 | 2026-09-18 | Completed
CHP-MR-ST1-RB | Structural Framing (Roof Beam) | Mumty roof beams ST-1 | RB15 / RB16 | Grid 6–5.1 / Row E–D.1 | Z3 | T.O.C EL(+)12.150 | 300×500 | O24091-990-C-B-19531-004 | CHP-SUP-210 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-1 | 2026-09-19 | 2026-10-03 | In Progress
CHP-MR-ST1-SLAB | Floors / Roofs (Structural slab) | Mumty roof slab ST-1 | SLAB 150 | Grid 6–5.1 / Row E–D.1 | Z3 | T.O.C EL(+)12.150 | 150 thk | O24091-990-C-B-19531-004 | CHP-SUP-210 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-1 | 2026-09-19 | 2026-10-03 | In Progress
CHP-GRD-PIT | Generic Models / Structural (Pit) | Cable pit 1500 deep with precast cover | Cable pit | Grid 6 / Row D–C | All | Top EL ±0.000 | ref. dwg | O24091-990-C-B-19531-007 | CHP-GRD-010 | Cable trench T1 (1500 deep) Row D–C, Grid 6→1 incl. cable pit at Grid 6 | 2026-05-15 | 2026-06-12 | Completed
CHP-GRD-T1 | Generic Models / Structural (Trench) | Cable trench T1 – walls & base, 1500 deep | T1 | Row D–C : Grid 6→1 | All | Top EL ±0.000, base EL(-)1.500 | 1500 wide (ref. dwg) | O24091-990-C-B-19531-007 | CHP-GRD-010 | Cable trench T1 (1500 deep) Row D–C, Grid 6→1 incl. cable pit at Grid 6 | 2026-05-15 | 2026-06-12 | Completed
CHP-GRD-T2 | Generic Models / Structural (Trench) | Cable trench T2 – walls & base, 1500 deep | T2 | Row B–A : Grid 6→1 | All | Top EL ±0.000, base EL(-)1.500 | 1500 wide (ref. dwg) | O24091-990-C-B-19531-007 | CHP-GRD-020 | Cable trench T2 (1500 deep) Row B–A, Grid 6→1 | 2026-05-27 | 2026-06-20 | Completed
CHP-GS-ED | Floors (Grade slab) | Grade slab 150 thk M25 on PCC & boulder soling | GS-ED | Row E–D : Grid 6–1 (cable cellar, toilets, shift room) | All | T.O.C EL ±0.000 / (-)0.050 | 150 thk | O24091-990-C-B-19531-007 | CHP-GRD-030 | Grade slab 150 thk – Row E–D block (cable cellar, toilets, shift room, ante rooms) | 2026-07-21 | 2026-08-03 | Completed
CHP-GS-DC | Floors (Grade slab) | Grade slab 150 thk M25 | GS-DC | Row D–C : Grid 6–1 | All | T.O.C EL ±0.000 | 150 thk | O24091-990-C-B-19531-007 | CHP-GRD-040 | Grade slab 150 thk – Row D–C strip (around trench T1) | 2026-07-27 | 2026-08-06 | Completed
CHP-F1-01 | Structural Foundations (Equipment) | Chiller foundation F1 | F1-01 | Bay 1–2 / Row C–B | All | T.O.C EL ±0.000 | ref. dwg 19531-008 S9 | O24091-990-C-B-19531-008 | CHP-GRD-050 | Chiller foundations F1-01 & F1-02 (Bays 1–2, 2–3) | 2026-10-03 | 2026-10-24 | Not Started (Late)
CHP-F1-02 | Structural Foundations (Equipment) | Chiller foundation F1 | F1-02 | Bay 2–3 / Row C–B | All | T.O.C EL ±0.000 | ref. dwg 19531-008 S9 | O24091-990-C-B-19531-008 | CHP-GRD-050 | Chiller foundations F1-01 & F1-02 (Bays 1–2, 2–3) | 2026-10-03 | 2026-10-24 | Not Started (Late)
CHP-F1-03 | Structural Foundations (Equipment) | Chiller foundation F1 | F1-03 | Bay 3–4 / Row C–B | All | T.O.C EL ±0.000 | ref. dwg 19531-008 S9 | O24091-990-C-B-19531-008 | CHP-GRD-060 | Chiller foundations F1-03 & F1-04 (Bays 3–4, 4–5) | 2026-10-09 | 2026-10-30 | Not Started (Late)
CHP-F1-04 | Structural Foundations (Equipment) | Chiller foundation F1 | F1-04 | Bay 4–5 / Row C–B | All | T.O.C EL ±0.000 | ref. dwg 19531-008 S9 | O24091-990-C-B-19531-008 | CHP-GRD-060 | Chiller foundations F1-03 & F1-04 (Bays 3–4, 4–5) | 2026-10-09 | 2026-10-30 | Not Started (Late)
CHP-F1-05 | Structural Foundations (Equipment) | Chiller foundation F1 | F1-05 | Bay 5–6 / Row C–B | All | T.O.C EL ±0.000 | ref. dwg 19531-008 S9 | O24091-990-C-B-19531-008 | CHP-GRD-070 | Chiller foundation F1-05 (Bay 5–6) | 2026-10-15 | 2026-10-29 | Not Started (Late)
CHP-F2-01 | Structural Foundations (Equipment) | Pump foundation F2 | F2-01 | Bay 1–2 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-080 | Pump foundations F2-01 to F2-04 (Bays 1–3) | 2026-10-09 | 2026-10-21 | Not Started (Late)
CHP-F2-02 | Structural Foundations (Equipment) | Pump foundation F2 | F2-02 | Bay 1–2 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-080 | Pump foundations F2-01 to F2-04 (Bays 1–3) | 2026-10-09 | 2026-10-21 | Not Started (Late)
CHP-F2-03 | Structural Foundations (Equipment) | Pump foundation F2 | F2-03 | Bay 2–3 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-080 | Pump foundations F2-01 to F2-04 (Bays 1–3) | 2026-10-09 | 2026-10-21 | Not Started (Late)
CHP-F2-04 | Structural Foundations (Equipment) | Pump foundation F2 | F2-04 | Bay 2–3 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-080 | Pump foundations F2-01 to F2-04 (Bays 1–3) | 2026-10-09 | 2026-10-21 | Not Started (Late)
CHP-F2-05 | Structural Foundations (Equipment) | Pump foundation F2 | F2-05 | Bay 3–4 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-090 | Pump foundations F2-05 to F2-08 (Bays 3–5) | 2026-10-15 | 2026-10-27 | Not Started (Late)
CHP-F2-06 | Structural Foundations (Equipment) | Pump foundation F2 | F2-06 | Bay 3–4 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-090 | Pump foundations F2-05 to F2-08 (Bays 3–5) | 2026-10-15 | 2026-10-27 | Not Started (Late)
CHP-F2-07 | Structural Foundations (Equipment) | Pump foundation F2 | F2-07 | Bay 4–5 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-090 | Pump foundations F2-05 to F2-08 (Bays 3–5) | 2026-10-15 | 2026-10-27 | Not Started (Late)
CHP-F2-08 | Structural Foundations (Equipment) | Pump foundation F2 | F2-08 | Bay 4–5 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-090 | Pump foundations F2-05 to F2-08 (Bays 3–5) | 2026-10-15 | 2026-10-27 | Not Started (Late)
CHP-F2-09 | Structural Foundations (Equipment) | Pump foundation F2 | F2-09 | Bay 5–6 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-100 | Pump foundations F2-09 & F2-10 (Bay 5–6) | 2026-10-21 | 2026-10-27 | Not Started (Late)
CHP-F2-10 | Structural Foundations (Equipment) | Pump foundation F2 | F2-10 | Bay 5–6 / Row B–A | All | T.O.C EL ±0.000 | 2170×1400 (ref. dwg) | O24091-990-C-B-19531-008 | CHP-GRD-100 | Pump foundations F2-09 & F2-10 (Bay 5–6) | 2026-10-21 | 2026-10-27 | Not Started (Late)
CHP-SLIT-01 | Generic Models / Structural (Trench) | Cable slit 600 deep | Slit-1 | Beside F1-01 / Row C–B | All | Top EL ±0.000 | 600 deep | O24091-990-C-B-19531-007 | CHP-GRD-110 | Cable slits (600 deep) between chiller foundations (5 nos) | 2026-10-31 | 2026-11-09 | Not Started (Late)
CHP-SLIT-02 | Generic Models / Structural (Trench) | Cable slit 600 deep | Slit-2 | Beside F1-02 / Row C–B | All | Top EL ±0.000 | 600 deep | O24091-990-C-B-19531-007 | CHP-GRD-110 | Cable slits (600 deep) between chiller foundations (5 nos) | 2026-10-31 | 2026-11-09 | Not Started (Late)
CHP-SLIT-03 | Generic Models / Structural (Trench) | Cable slit 600 deep | Slit-3 | Beside F1-03 / Row C–B | All | Top EL ±0.000 | 600 deep | O24091-990-C-B-19531-007 | CHP-GRD-110 | Cable slits (600 deep) between chiller foundations (5 nos) | 2026-10-31 | 2026-11-09 | Not Started (Late)
CHP-SLIT-04 | Generic Models / Structural (Trench) | Cable slit 600 deep | Slit-4 | Beside F1-04 / Row C–B | All | Top EL ±0.000 | 600 deep | O24091-990-C-B-19531-007 | CHP-GRD-110 | Cable slits (600 deep) between chiller foundations (5 nos) | 2026-10-31 | 2026-11-09 | Not Started (Late)
CHP-SLIT-05 | Generic Models / Structural (Trench) | Cable slit 600 deep | Slit-5 | Beside F1-05 / Row C–B | All | Top EL ±0.000 | 600 deep | O24091-990-C-B-19531-007 | CHP-GRD-110 | Cable slits (600 deep) between chiller foundations (5 nos) | 2026-10-31 | 2026-11-09 | Not Started (Late)
CHP-GS-CB | Floors (Grade slab) | Grade slab 150 thk M25 – chiller room | GS-CB | Row C–B : Grid 6–1 | All | T.O.C EL ±0.000 | 150 thk | O24091-990-C-B-19531-007 | CHP-GRD-120 | Grade slab 150 thk – Chiller room (Row C–B) | 2026-11-10 | 2026-11-20 | Not Started (Late)
CHP-DRN-SURF | Generic Models (Drain) | Surface drain 150(W)×100 deep | Surface drain | Along Row A (inside) | All | EL ±0.000 | 150×100 | O24091-990-C-B-19531-007 | CHP-GRD-130 | Grade slab 150 thk – Pump area (Row B–A) incl. 150×100 surface drain | 2026-11-13 | 2026-11-25 | Not Started
CHP-GS-BA | Floors (Grade slab) | Grade slab 150 thk M25 – pump area | GS-BA | Row B–A : Grid 6–1 | All | T.O.C EL ±0.000 | 150 thk | O24091-990-C-B-19531-007 | CHP-GRD-130 | Grade slab 150 thk – Pump area (Row B–A) incl. 150×100 surface drain | 2026-11-13 | 2026-11-25 | Not Started
CHP-PCV-ALL | Generic Models (Precast cover) | Precast RCC covers – trench, pit, drain crossings | Precast covers | T1, T2, cable pit, crossings | All | EL ±0.000 | ref. dwg 19531-008 | O24091-990-C-B-19531-007 | CHP-GRD-140 | Precast covers – cable trenches, cable pit & drain crossings (placement) | 2026-11-12 | 2026-11-18 | Not Started
CHP-DRN-PVC | Pipes (Drain) | 100Ø PVC drain pipes to main drain | Drain pipes | Grid 6/A & 1/A corners | All | Below FGL | 100 Ø | O24091-990-C-B-19531-007 | CHP-GRD-150 | Plinth protection, garland drain & 100Ø PVC drain pipes (all round) | 2026-10-05 | 2026-10-22 | Not Started (Late)
CHP-PP-ALL | Generic Models / Floors (Plinth protection) | Plinth protection & garland drain | Plinth protection | All round building | All | FGL EL(-)0.500 | ref. dwg 19531-007 | O24091-990-C-B-19531-007 | CHP-GRD-150 | Plinth protection, garland drain & 100Ø PVC drain pipes (all round) | 2026-10-05 | 2026-10-22 | Not Started (Late)
CHP-EQ-CH-01 | Mechanical Equipment | Centrifugal chiller (vendor model) | CH-01 | On F1-01 (Bay 1–2, Row C–B) | Z1 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-010 | Chiller CH-01 on F1-01 (Bay 1–2) – setting, levelling, alignment & grouting | 2027-01-02 | 2027-01-18 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-CH-02 | Mechanical Equipment | Centrifugal chiller (vendor model) | CH-02 | On F1-02 (Bay 2–3, Row C–B) | Z1 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-020 | Chiller CH-02 on F1-02 (Bay 2–3) – setting, levelling, alignment & grouting | 2027-01-12 | 2027-01-28 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-CH-03 | Mechanical Equipment | Centrifugal chiller (vendor model) | CH-03 | On F1-03 (Bay 3–4, Row C–B) | Z2 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-030 | Chiller CH-03 on F1-03 (Bay 3–4) – setting, levelling, alignment & grouting | 2027-01-21 | 2027-02-06 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-CH-04 | Mechanical Equipment | Centrifugal chiller (vendor model) | CH-04 | On F1-04 (Bay 4–5, Row C–B) | Z2 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-040 | Chiller CH-04 on F1-04 (Bay 4–5) – setting, levelling, alignment & grouting | 2027-02-01 | 2027-02-16 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-CH-05 | Mechanical Equipment | Centrifugal chiller (vendor model) | CH-05 | On F1-05 (Bay 5–6, Row C–B) | Z3 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-050 | Chiller CH-05 on F1-05 (Bay 5–6) – setting, levelling, alignment & grouting | 2027-02-10 | 2027-02-25 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-HOIST-MR1 | Mechanical Equipment (Hoist) | 2T chain pulley block | CPB on MR-1 | MR-1 | All | B.O.MR +8.100 | 2 T | O24091-990-C-B-19531-004 | CHP-EQP-060 | Hoists – 2T chain pulley block on MR-1 & 10T electric hoist on MR-2 | 2027-01-02 | 2027-01-07 | Not Started
CHP-EQ-HOIST-MR2 | Mechanical Equipment (Hoist) | 10T electric hoist | EH on MR-2 | MR-2 | All | B.O.MR +7.900 | 10 T | O24091-990-C-B-19531-004 | CHP-EQP-060 | Hoists – 2T chain pulley block on MR-1 & 10T electric hoist on MR-2 | 2027-01-02 | 2027-01-07 | Not Started
CHP-EQ-P-01 | Mechanical Equipment | Pump with motor (vendor model) | P-01 | On F2-01 (Bay 1–2, Row B–A) | Z1 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-070 | Pumps P-01 to P-04 on F2-01..04 (Bays 1–3) – setting, alignment & grouting | 2027-01-14 | 2027-01-28 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-02 | Mechanical Equipment | Pump with motor (vendor model) | P-02 | On F2-02 (Bay 1–2, Row B–A) | Z1 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-070 | Pumps P-01 to P-04 on F2-01..04 (Bays 1–3) – setting, alignment & grouting | 2027-01-14 | 2027-01-28 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-03 | Mechanical Equipment | Pump with motor (vendor model) | P-03 | On F2-03 (Bay 2–3, Row B–A) | Z1 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-070 | Pumps P-01 to P-04 on F2-01..04 (Bays 1–3) – setting, alignment & grouting | 2027-01-14 | 2027-01-28 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-04 | Mechanical Equipment | Pump with motor (vendor model) | P-04 | On F2-04 (Bay 2–3, Row B–A) | Z1 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-070 | Pumps P-01 to P-04 on F2-01..04 (Bays 1–3) – setting, alignment & grouting | 2027-01-14 | 2027-01-28 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-05 | Mechanical Equipment | Pump with motor (vendor model) | P-05 | On F2-05 (Bay 3–4, Row B–A) | Z2 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-080 | Pumps P-05 to P-08 on F2-05..08 (Bays 3–5) – setting, alignment & grouting | 2027-01-23 | 2027-02-06 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-06 | Mechanical Equipment | Pump with motor (vendor model) | P-06 | On F2-06 (Bay 3–4, Row B–A) | Z2 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-080 | Pumps P-05 to P-08 on F2-05..08 (Bays 3–5) – setting, alignment & grouting | 2027-01-23 | 2027-02-06 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-07 | Mechanical Equipment | Pump with motor (vendor model) | P-07 | On F2-07 (Bay 4–5, Row B–A) | Z2 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-080 | Pumps P-05 to P-08 on F2-05..08 (Bays 3–5) – setting, alignment & grouting | 2027-01-23 | 2027-02-06 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-08 | Mechanical Equipment | Pump with motor (vendor model) | P-08 | On F2-08 (Bay 4–5, Row B–A) | Z2 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-080 | Pumps P-05 to P-08 on F2-05..08 (Bays 3–5) – setting, alignment & grouting | 2027-01-23 | 2027-02-06 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-09 | Mechanical Equipment | Pump with motor (vendor model) | P-09 | On F2-09 (Bay 5–6, Row B–A) | Z3 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-090 | Pumps P-09 & P-10 on F2-09..10 (Bay 5–6) – setting, alignment & grouting | 2027-02-03 | 2027-02-11 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-EQ-P-10 | Mechanical Equipment | Pump with motor (vendor model) | P-10 | On F2-10 (Bay 5–6, Row B–A) | Z3 | EL ±0.000 | Vendor GA | Equipment GA (vendor) | CHP-EQP-090 | Pumps P-09 & P-10 on F2-09..10 (Bay 5–6) – setting, alignment & grouting | 2027-02-03 | 2027-02-11 | Not Started | Tag numbering assumed from Grid 1 – verify with equipment layout
CHP-GRP-EQP-100 | Mechanical Equipment | Final alignment, motor/drive coupling & box-up of chillers and pumps | CH-01..05, P-01..10 (drives) | Chiller hall | All | ±0.000 |  |  | CHP-EQP-100 | Final alignment, motor/drive coupling & box-up of chillers and pumps | 2027-02-26 | 2027-03-20 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-PIP-010 | Pipe Accessories / Generic (supports) | Pipe supports & sleepers – chiller hall | Pipe supports | Chiller hall Row C–A | All | ±0.000 to +3.0 |  |  | CHP-PIP-010 | Pipe supports & sleepers – chiller hall | 2027-01-27 | 2027-02-12 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-PIP-020 | Pipes | CHW & CW headers (supply / return) – fabrication & erection | CHWS, CHWR, CWS, CWR headers | Chiller hall Row C–A | All | Header elevation |  |  | CHP-PIP-020 | CHW & CW headers (supply / return) – fabrication & erection | 2027-02-05 | 2027-03-05 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-PIP-030 | Pipes / Pipe Accessories | Chiller hook-up piping CH-01..CH-05 incl. valves, strainers & flexible connectors | Chiller branch lines | Row C–B | All | ±0.000 to +3.0 |  |  | CHP-PIP-030 | Chiller hook-up piping CH-01..CH-05 incl. valves, strainers & flexible connectors | 2027-02-26 | 2027-03-23 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-PIP-040 | Pipes / Pipe Accessories | Pump suction / discharge hook-up P-01..P-10 | Pump branch lines | Row B–A | All | ±0.000 to +2.0 |  |  | CHP-PIP-040 | Pump suction / discharge hook-up P-01..P-10 | 2027-02-19 | 2027-03-12 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-PIP-050 | Pipes (status change) | Hydro test, flushing & reinstatement | All CHW/CW piping | Chiller hall | All | All |  |  | CHP-PIP-050 | Hydro test, flushing & reinstatement | 2027-03-24 | 2027-04-08 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ELE-010 | Cable Trays | Cable trays & supports – trenches T1/T2, cable pit & cable cellar | Cable trays | Trenches & cable cellar | All | EL(-)1.500 to ±0.000 |  |  | CHP-ELE-010 | Cable trays & supports – trenches T1/T2, cable pit & cable cellar | 2027-02-02 | 2027-02-24 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ELE-020 | Cable Trays | Cable trays & supports – chiller hall, switchgear room & first floor | Cable trays | Chiller hall & FF | All | +0.000 to +8.0 |  |  | CHP-ELE-020 | Cable trays & supports – chiller hall, switchgear room & first floor | 2027-02-11 | 2027-03-05 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ELE-030 | Cable Trays (fill) / Conduits | Cable laying, glanding & termination (power & control) | Cables | Whole plant | All | All |  |  | CHP-ELE-030 | Cable laying, glanding & termination (power & control) | 2027-02-19 | 2027-03-27 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ELE-040 | Electrical Fixtures (earthing) | Earthing & lightning protection | Earth grid, LPS | Whole building | All | All |  |  | CHP-ELE-040 | Earthing & lightning protection | 2027-02-19 | 2027-03-08 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ELE-050 | Lighting Fixtures / Electrical Fixtures | Lighting fixtures, JBs & small power | Light fixtures, JBs, sockets | Whole building | All | All |  |  | CHP-ELE-050 | Lighting fixtures, JBs & small power | 2027-02-25 | 2027-04-14 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ELE-060 | Electrical Equipment | Switchgear room panels (6.6 kV SWBD, ESS6-PDB-1) – placement & termination | 6.6kV SWBD, ESS6-PDB-1 | FF switchgear room (Row E–D) | All | +4.050 FFL |  |  | CHP-ELE-060 | Switchgear room panels (6.6 kV SWBD, ESS6-PDB-1) – placement & termination | 2027-02-19 | 2027-03-15 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-INS-010 | Mechanical Equipment / Generic (instruments) | Field instruments installation (PT / TT / FT / flow switches) | Field instruments | Chiller hall | All | ±0.000 to +3.0 |  |  | CHP-INS-010 | Field instruments installation (PT / TT / FT / flow switches) | 2027-03-10 | 2027-04-08 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-INS-020 | Conduits / Cable Trays (fill) | Instrument cabling, impulse tubing & loop checks | Instrument cables, tubing | Chiller hall | All | All |  |  | CHP-INS-020 | Instrument cabling, impulse tubing & loop checks | 2027-03-23 | 2027-05-03 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-010 | Walls (Architectural) | Brickwork 230 thk – GF Row E–D block up to lintel level | Brick walls GF | Row E–D : Grid 6–1 | All | EL ±0.000 to +2.100 |  | O24091-990-C-B-19531-005 | CHP-ARC-010 | Brickwork 230 thk – GF Row E–D block up to lintel level | 2026-10-05 | 2026-10-17 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-020 | Structural Framing (Lintel) | Lintels & chajjas – GF (LB1–LB6) | LB1, LB2, LB3, LB4, LB5, LB6 | GF openings (Table-1) | All | B/O lintel +2.100 to +3.400 |  | O24091-990-C-B-19531-006 | CHP-ARC-020 | Lintels & chajjas – GF (LB1–LB6) | 2026-10-14 | 2026-10-21 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-030 | Walls (Architectural) | Brickwork – GF above lintel up to first-floor soffit | Brick walls GF | Row E–D : Grid 6–1 | All | +2.100 to +3.400 |  | O24091-990-C-B-19531-005 | CHP-ARC-030 | Brickwork – GF above lintel up to first-floor soffit | 2026-10-22 | 2026-10-30 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-040 | Walls (Architectural) | Brickwork – FF (switchgear, AC & AHU rooms, ante rooms) up to lintel | Brick walls FF | Row E–D : Grid 6–1 (FF) | All | +4.000 to +6.150 |  | O24091-990-C-B-19531-005 | CHP-ARC-040 | Brickwork – FF (switchgear, AC & AHU rooms, ante rooms) up to lintel | 2026-10-27 | 2026-11-06 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-050 | Structural Framing (Lintel) | Lintels & chajjas – FF (LB7–LB9B) | LB7, LB7A, LB8, LB9, LB9A, LB9B | FF openings (Table-2) | All | B/O lintel +6.150 to +7.350 |  | O24091-990-C-B-19531-006 | CHP-ARC-050 | Lintels & chajjas – FF (LB7–LB9B) | 2026-11-04 | 2026-11-10 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-060 | Walls (Architectural) + Lintel | Brickwork – chiller hall external walls (Row A, Grid 1 & 6) incl. LB1A lintels & monorail-door openings | Brick walls, LB1A | Row C–A : Grid 6 / Row A / Grid 1 | All | ±0.000 to +9.150 |  | O24091-990-C-B-19531-006 | CHP-ARC-060 | Brickwork – chiller hall external walls (Row A, Grid 1 & 6) incl. LB1A lintels & monorail-door openings | 2026-10-12 | 2026-11-04 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-070 | Walls + Structural Framing (Lintel) | Mumty brickwork & lintels LB10–LB12 – ST-1 & ST-2 | Brick walls, LB10, LB11, LB12 | Grid 6–5.1 & 2–1 : Row E–D.1/D.2 | All | +9.150 to +12.150 |  | O24091-990-C-B-19531-006 | CHP-ARC-070 | Mumty brickwork & lintels LB10–LB12 – ST-1 & ST-2 | 2026-10-05 | 2026-10-15 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-080 | Roofs / Walls (Architectural) | Parapet wall, roof waterproofing, PCC wearing course & rainwater pipes | Parapet, WP membrane, wearing course | Roof EL +9.150 & +12.150 | All | +9.150 / +12.150 |  | O24091-990-C-B-19531-004 | CHP-ARC-080 | Parapet wall, roof waterproofing, PCC wearing course & rainwater pipes | 2026-10-08 | 2026-10-26 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-090 | Finishes (if modelled) | Plastering – internal & external | Plaster | Whole building | All | All |  |  | CHP-ARC-090 | Plastering – internal & external | 2026-11-11 | 2026-12-09 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-100 | Floors (finish) | Flooring & floor finishes (GF rooms, FF, staircases) | Floor finish | Whole building | All | ±0.000 / +4.050 |  |  | CHP-ARC-100 | Flooring & floor finishes (GF rooms, FF, staircases) | 2026-11-26 | 2026-12-12 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-110 | Doors / Windows | Doors, windows, rolling shutters & monorail doors | Doors, windows, RS, monorail doors | Whole building | All | All |  |  | CHP-ARC-110 | Doors, windows, rolling shutters & monorail doors | 2026-11-28 | 2026-12-15 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-GRP-ARC-120 | Finishes (if modelled) | Painting – internal & external | Paint | Whole building | All | All |  |  | CHP-ARC-120 | Painting – internal & external | 2026-12-10 | 2027-01-04 | Not Started | Group element – attach all model objects of this scope (if modelled)
CHP-STL-MR1 | Structural Framing (Steel) | Monorail NPB 300×150×49.32 | MR-1 | 2250 N of Row A, Grid 6 → beyond Grid 1 | All | B.O.MR EL(+)8.100 | NPB 300×150 | O24091-990-C-B-19531-004 | CHP-STL-010 | Monorail beams MR-1 (NPB 300×150, B.O.MR +8.100) & MR-2 (NPB 500×200, B.O.MR +7.900) incl. end stoppers | 2026-11-02 | 2026-11-12 | Not Started
CHP-STL-MR2 | Structural Framing (Steel) | Monorail NPB 500×200×90.7 + bottom flange plate | MR-2 | 3500 N of Row B, Grid 6 → beyond Grid 1 | All | B.O.MR EL(+)7.900 | NPB 500×200 | O24091-990-C-B-19531-004 | CHP-STL-010 | Monorail beams MR-1 (NPB 300×150, B.O.MR +8.100) & MR-2 (NPB 500×200, B.O.MR +7.900) incl. end stoppers | 2026-11-02 | 2026-11-12 | Not Started
CHP-GRP-STL-020 | Railings | Handrails – staircases ST-1/ST-2 & removable handrails at FF openings / platforms | Handrails | ST-1, ST-2, FF edges | All | +1.300 to +12.150 |  | O24091-990-C-B-19531-003 | CHP-STL-020 | Handrails – staircases ST-1/ST-2 & removable handrails at FF openings / platforms | 2026-11-17 | 2026-11-27 | Not Started | Group element – attach all model objects of this scope (if modelled)

## TimeLiner Import
Display ID | Task Name | Task Type | Planned Start | Planned End | Actual Start | Actual End | Baseline Start | Baseline End | % Complete | Status | Selection Set | Parent (P6 Group) | Work Package | Zone | Level
CHP-MS-010 | Basic drawings / technical specification inputs received | Construct | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-01-20 | 2026-01-20 | 100% | Completed |  | JSW USL-BE-CHI-1000 | Milestone
CHP-ENG-010 | Pile layout & detail drawing (19530-001) – design & preparation | Construct | 2025-11-29 | 2025-12-15 | 2025-11-29 | 2025-12-15 | 2026-02-07 | 2026-02-23 | 100% | Completed |  | JSW USL-DE-CHI-1000 | Engineering
CHP-ENG-020 | Pile drawing – review, client approval & IFC issue | Construct | 2025-12-16 | 2025-12-22 | 2025-12-16 | 2025-12-22 | 2026-02-24 | 2026-03-02 | 100% | Completed |  | JSW USL-DE-CHI-1000 | Engineering
CHP-MS-020 | Pile drawings released (IFC) | Construct | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2026-03-02 | 2026-03-02 | 100% | Completed |  | JSW USL-DE-CHI-1000 | Milestone
CHP-ENG-030 | Civil GA & RC drawings 19531-001 … 008 – preparation & checking | Construct | 2025-12-23 | 2025-12-31 | 2025-12-23 | 2025-12-31 | 2026-01-20 | 2026-02-10 | 100% | Completed |  | JSW USL-DE-CHI-1010 | Engineering
CHP-ENG-040 | Civil drawings – client review & IFC release | Construct | 2026-01-02 | 2026-01-07 | 2026-01-02 | 2026-01-07 | 2026-02-11 | 2026-02-24 | 100% | Completed |  | JSW USL-DE-CHI-1010 | Engineering
CHP-MS-030 | Civil drawings released (IFC) | Construct | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-02-24 | 2026-02-24 | 100% | Completed |  | JSW USL-DE-CHI-1010 | Milestone
CHP-ENG-050 | Vendor GA drawings (centrifugal chillers & pumps) – receipt & review | Construct | 2026-08-31 | 2026-09-14 | 2026-08-31 | 2026-09-14 | 2026-08-31 | 2026-09-23 | 100% | Completed |  | JSW USL-DE-CHI-1020 | Engineering
CHP-ENG-060 | Equipment layout & foundation loading data – approval & release | Construct | 2026-09-15 | 2026-09-24 | 2026-09-15 | 2026-09-24 | 2026-09-24 | 2026-10-10 | 100% | Completed |  | JSW USL-DE-CHI-1020 | Engineering
CHP-MS-040 | Equipment drawings released – HOLD on chiller / pump foundations F1 & F2 lifted | Construct | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-10-10 | 2026-10-10 | 100% | Completed |  | JSW USL-DE-CHI-1020 | Milestone
CHP-ENG-070 | Piping GA, isometric & pipe-support drawings – preparation | Construct | 2026-10-03 | 2026-11-07 |  |  | 2026-10-12 | 2026-11-20 | 0% | Not Started |  | JSW USL-DE-CHI-1030 | Engineering
CHP-ENG-080 | Piping drawings – review, comments & IFC release | Construct | 2026-11-09 | 2026-11-19 |  |  | 2026-11-21 | 2026-12-03 | 0% | Not Started |  | JSW USL-DE-CHI-1030 | Engineering
CHP-MS-050 | Piping drawings released (IFC) | Construct | 2026-11-19 | 2026-11-19 |  |  | 2026-12-03 | 2026-12-03 | 0% | Not Started |  | JSW USL-DE-CHI-1030 | Milestone
CHP-ENG-090 | E&I layouts (cable routing, lighting, earthing, instrument locations) – preparation | Construct | 2026-10-01 | 2026-10-26 | 2026-10-01 |  | 2026-12-04 | 2026-12-15 | 38% | In Progress |  | JSW USL-DE-CHI-1040 | Engineering
CHP-ENG-100 | E&I drawings – coordination with piping drawings, review & IFC release | Construct | 2026-11-20 | 2026-12-11 |  |  | 2026-12-30 | 2027-01-09 | 0% | Not Started |  | JSW USL-DE-CHI-1040 | Engineering
CHP-MS-060 | E&I drawings released (IFC) | Construct | 2026-12-11 | 2026-12-11 |  |  | 2027-01-09 | 2027-01-09 | 0% | Not Started |  | JSW USL-DE-CHI-1040 | Milestone
CHP-PRC-010 | Centrifugal chillers – PR, RFQ, bids & technical evaluation | Construct | 2026-02-03 | 2026-04-13 | 2026-02-03 | 2026-04-13 | 2026-02-28 | 2026-04-16 | 100% | Completed |  | JSW USL-PR-2440 | Procurement
CHP-PRC-020 | Centrifugal chillers – commercial negotiation & PO placement | Construct | 2026-04-14 | 2026-05-20 | 2026-04-14 | 2026-05-20 | 2026-04-17 | 2026-05-12 | 100% | Completed |  | JSW USL-PR-2440 | Procurement
CHP-PRC-030 | PO placed – centrifugal chillers | Construct | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-12 | 2026-05-12 | 100% | Completed |  | JSW USL-PR-2440 | Procurement
CHP-PRC-040 | Centrifugal chillers – manufacturing | Construct | 2026-05-22 | 2026-12-03 | 2026-05-22 |  | 2026-06-30 | 2026-12-03 | 68.48% | In Progress |  | JSW USL-PR-2450 | Procurement
CHP-PRC-050 | Centrifugal chillers – stage inspection & FAT | Construct | 2026-12-04 | 2026-12-12 |  |  | 2026-12-04 | 2026-12-10 | 0% | Not Started |  | JSW USL-PR-2450 | Procurement
CHP-PRC-060 | Centrifugal chillers – dispatch & transit to site | Construct | 2026-12-14 | 2026-12-31 |  |  | 2026-12-11 | 2026-12-24 | 0% | Not Started |  | JSW USL-PR-2450 | Procurement
CHP-MS-070 | Centrifugal chillers delivered at site | Construct | 2026-12-31 | 2026-12-31 |  |  | 2026-12-24 | 2026-12-24 | 0% | Not Started |  | JSW USL-PR-2450 | Milestone
CHP-PRC-070 | Pumps – PR, RFQ, bids & technical evaluation | Construct | 2026-02-03 | 2026-03-30 | 2026-02-03 | 2026-03-30 | 2026-02-28 | 2026-04-16 | 100% | Completed |  | JSW USL-PR-2460 | Procurement
CHP-PRC-080 | Pumps – commercial negotiation & PO placement | Construct | 2026-03-31 | 2026-04-27 | 2026-03-31 | 2026-04-27 | 2026-04-17 | 2026-05-12 | 100% | Completed |  | JSW USL-PR-2460 | Procurement
CHP-PRC-090 | PO placed – pumps | Construct | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-12 | 2026-05-12 | 100% | Completed |  | JSW USL-PR-2460 | Procurement
CHP-PRC-100 | Pumps – manufacturing | Construct | 2026-04-29 | 2026-12-07 | 2026-04-29 |  | 2026-04-30 | 2026-09-04 | 70.59% | In Progress |  | JSW USL-PR-2470 | Procurement
CHP-PRC-110 | Pumps – inspection & performance test | Construct | 2026-12-08 | 2026-12-14 |  |  | 2026-09-05 | 2026-09-09 | 0% | Not Started (Late) |  | JSW USL-PR-2470 | Procurement
CHP-PRC-120 | Pumps – dispatch & transit to site | Construct | 2026-12-15 | 2026-12-31 |  |  | 2026-09-10 | 2026-09-18 | 0% | Not Started (Late) |  | JSW USL-PR-2470 | Procurement
CHP-MS-080 | Pumps delivered at site | Construct | 2026-12-31 | 2026-12-31 |  |  | 2026-09-18 | 2026-09-18 | 0% | Not Started (Late) |  | JSW USL-PR-2470 | Milestone
CHP-PIL-010 | Piles Row A (P1–P7) | Construct | 2025-12-17 | 2025-12-20 | 2025-12-17 | 2025-12-20 | 2026-01-20 | 2026-01-23 | 100% | Completed | CHP-PIL-010 | JSW USL-CON-CHI-1000 | Piling | Row A | Cut-off EL(-)2.425 ; L = 26 m
CHP-PIL-020 | Piles Row B (P8–P16) | Construct | 2025-12-22 | 2025-12-27 | 2025-12-22 | 2025-12-27 | 2026-01-24 | 2026-01-31 | 100% | Completed | CHP-PIL-020 | JSW USL-CON-CHI-1000 | Piling | Row B | Cut-off EL(-)2.425 ; L = 26 m
CHP-PIL-030 | Piles Row C (P17–P22) | Construct | 2025-12-29 | 2025-12-31 | 2025-12-29 | 2025-12-31 | 2026-02-02 | 2026-02-04 | 100% | Completed | CHP-PIL-030 | JSW USL-CON-CHI-1000 | Piling | Row C | Cut-off EL(-)2.425 ; L = 26 m
CHP-PIL-040 | Piles Row D (P23–P34) | Construct | 2026-01-02 | 2026-01-08 | 2026-01-02 | 2026-01-08 | 2026-02-05 | 2026-02-12 | 100% | Completed | CHP-PIL-040 | JSW USL-CON-CHI-1000 | Piling | Row D | Cut-off EL(-)2.425 ; L = 26 m
CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | Construct | 2026-01-09 | 2026-01-13 | 2026-01-09 | 2026-01-13 | 2026-02-13 | 2026-02-17 | 100% | Completed | CHP-PIL-050 | JSW USL-CON-CHI-1000 | Piling | Row D.1/D.2 | Cut-off EL(-)2.425 ; L = 26 m
CHP-PIL-060 | Piles Row E (P42–P53) | Construct | 2026-01-14 | 2026-01-19 | 2026-01-14 | 2026-01-19 | 2026-02-18 | 2026-02-24 | 100% | Completed | CHP-PIL-060 | JSW USL-CON-CHI-1000 | Piling | Row E | Cut-off EL(-)2.425 ; L = 26 m
CHP-EXC-010 | Excavation, pile chipping & PCC prep – Zone-1 (Grid 1–3) | Demolish | 2026-02-18 | 2026-03-07 | 2026-02-18 | 2026-03-07 | 2026-03-31 | 2026-04-30 | 100% | Completed | CHP-EXC-010 | JSW USL-CON-CHI-1010 | Excavation | Z1 | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC)
CHP-EXC-020 | Excavation, pile chipping & PCC prep – Zone-2 (Grid 3–5) | Demolish | 2026-03-05 | 2026-03-18 | 2026-03-05 | 2026-03-18 | 2026-04-25 | 2026-05-21 | 100% | Completed | CHP-EXC-020 | JSW USL-CON-CHI-1010 | Excavation | Z2 | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC)
CHP-EXC-030 | Excavation, pile chipping & PCC prep – Zone-3 (Grid 5–6) | Demolish | 2026-03-16 | 2026-03-30 | 2026-03-16 | 2026-03-30 | 2026-05-15 | 2026-06-09 | 100% | Completed | CHP-EXC-030 | JSW USL-CON-CHI-1010 | Excavation | Z3 | FGL EL(-)0.500 to EL(-)2.575 (incl. PCC)
CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | Construct | 2026-03-08 | 2026-03-25 | 2026-03-08 | 2026-03-25 | 2026-04-17 | 2026-04-28 | 100% | Completed | CHP-SUB-010 | JSW USL-CON-CHI-1020 | Substructure | Z1 | B.O.C EL(-)2.500 (75 PCC M7.5 below)
CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | Construct | 2026-03-19 | 2026-03-31 | 2026-03-19 | 2026-03-31 | 2026-04-24 | 2026-05-02 | 100% | Completed | CHP-SUB-020 | JSW USL-CON-CHI-1020 | Substructure | Z2 | B.O.C EL(-)2.500 (75 PCC M7.5 below)
CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | Construct | 2026-03-31 | 2026-04-08 | 2026-03-31 | 2026-04-08 | 2026-05-02 | 2026-05-08 | 100% | Completed | CHP-SUB-030 | JSW USL-CON-CHI-1020 | Substructure | Z3 | B.O.C EL(-)2.500 (75 PCC M7.5 below)
CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | Construct | 2026-03-26 | 2026-04-11 | 2026-03-26 | 2026-04-11 | 2026-04-29 | 2026-05-11 | 100% | Completed | CHP-SUB-040 | JSW USL-CON-CHI-1020 | Substructure | Z1 | EL(-)2.500 to EL(-)0.300 / Top of PCB3 to EL(-)0.300 / B/O PCB EL(-)2.400
CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | Construct | 2026-04-04 | 2026-04-17 | 2026-04-04 | 2026-04-17 | 2026-05-06 | 2026-05-14 | 100% | Completed | CHP-SUB-050 | JSW USL-CON-CHI-1020 | Substructure | Z2 | EL(-)2.500 to EL(-)0.300 / B/O PCB EL(-)2.400
CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | Construct | 2026-04-11 | 2026-04-22 | 2026-04-11 | 2026-04-22 | 2026-05-11 | 2026-05-18 | 100% | Completed | CHP-SUB-060 | JSW USL-CON-CHI-1020 | Substructure | Z3 | EL(-)2.500 to EL(-)0.300 / B/O PCB EL(-)2.400
CHP-SUB-070 | Backfilling & compaction up to plinth level – Zone-1 | Construct | 2026-04-13 | 2026-04-18 | 2026-04-13 | 2026-04-18 | 2026-05-12 | 2026-05-15 | 100% | Completed | CHP-SUB-070 | JSW USL-CON-CHI-1020 | Substructure | Z1 | EL(-)2.500 to EL(-)0.500
CHP-SUB-080 | Backfilling & compaction up to plinth level – Zone-2 | Construct | 2026-04-20 | 2026-04-24 | 2026-04-20 | 2026-04-24 | 2026-05-16 | 2026-05-19 | 100% | Completed | CHP-SUB-080 | JSW USL-CON-CHI-1020 | Substructure | Z2 | EL(-)2.500 to EL(-)0.500
CHP-SUB-090 | Backfilling & compaction up to plinth level – Zone-3 | Construct | 2026-04-25 | 2026-04-30 | 2026-04-25 | 2026-04-30 | 2026-05-20 | 2026-05-23 | 100% | Completed | CHP-SUB-090 | JSW USL-CON-CHI-1020 | Substructure | Z3 | EL(-)2.500 to EL(-)0.500
CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | Construct | 2026-04-20 | 2026-05-04 | 2026-04-20 | 2026-05-04 | 2026-05-16 | 2026-05-25 | 100% | Completed | CHP-SUB-100 | JSW USL-CON-CHI-1020 | Substructure | Z1 | T.O.B EL(-)0.300
CHP-SUB-110 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | Construct | 2026-04-27 | 2026-05-08 | 2026-04-27 | 2026-05-08 | 2026-05-21 | 2026-05-28 | 100% | Completed | CHP-SUB-110 | JSW USL-CON-CHI-1020 | Substructure | Z2 | T.O.B EL(-)0.300
CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | Construct | 2026-05-04 | 2026-05-14 | 2026-05-04 | 2026-05-14 | 2026-05-25 | 2026-06-01 | 100% | Completed | CHP-SUB-120 | JSW USL-CON-CHI-1020 | Substructure | Z3 | T.O.B EL(-)0.300
CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | Construct | 2026-05-05 | 2026-05-20 | 2026-05-05 | 2026-05-20 | 2026-05-26 | 2026-06-05 | 100% | Completed | CHP-SUP-010 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | EL(-)0.300 to EL(+)4.000
CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | Construct | 2026-05-13 | 2026-05-23 | 2026-05-13 | 2026-05-23 | 2026-06-01 | 2026-06-08 | 100% | Completed | CHP-SUP-020 | JSW USL-CON-CHI-1020 | Superstructure | Z2 | EL(-)0.300 to EL(+)4.000
CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | Construct | 2026-05-19 | 2026-05-27 | 2026-05-19 | 2026-05-27 | 2026-06-04 | 2026-06-10 | 100% | Completed | CHP-SUP-030 | JSW USL-CON-CHI-1020 | Superstructure | Z3 | EL(-)0.300 to EL(+)4.000
CHP-SUP-040 | Tie beam TB1 (TOB EL +2.100) at Grid 1 | Construct | 2026-05-12 | 2026-05-16 | 2026-05-12 | 2026-05-16 | 2026-05-30 | 2026-06-03 | 100% | Completed | CHP-SUP-040 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | EL(+)2.100 TOB
CHP-SUP-050 | Staircase ST-2 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | Construct | 2026-05-21 | 2026-06-06 | 2026-05-21 | 2026-06-06 | 2026-06-06 | 2026-06-17 | 100% | Completed | CHP-SUP-050 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | EL(-)0.050 to EL(+)4.000
CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | Construct | 2026-05-21 | 2026-06-17 | 2026-05-21 | 2026-06-17 | 2026-06-06 | 2026-06-24 | 100% | Completed | CHP-SUP-060 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | T.O.C EL(+)4.000
CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | Construct | 2026-06-04 | 2026-06-29 | 2026-06-04 | 2026-06-29 | 2026-06-16 | 2026-07-02 | 100% | Completed | CHP-SUP-070 | JSW USL-CON-CHI-1020 | Superstructure | Z2 | T.O.C EL(+)4.000
CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | Construct | 2026-06-16 | 2026-07-08 | 2026-06-16 | 2026-07-08 | 2026-06-24 | 2026-07-08 | 100% | Completed | CHP-SUP-080 | JSW USL-CON-CHI-1020 | Superstructure | Z3 | T.O.C EL(+)4.000
CHP-SUP-090 | Staircase ST-1 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | Construct | 2026-05-28 | 2026-06-13 | 2026-05-28 | 2026-06-13 | 2026-06-11 | 2026-06-22 | 100% | Completed | CHP-SUP-090 | JSW USL-CON-CHI-1020 | Superstructure | Z3 | EL(-)0.050 to EL(+)4.000
CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | Construct | 2026-06-18 | 2026-07-08 | 2026-06-18 | 2026-07-08 | 2026-06-25 | 2026-07-08 | 100% | Completed | CHP-SUP-100 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | EL(+)4.000 to EL(+)9.150
CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | Construct | 2026-06-30 | 2026-07-15 | 2026-06-30 | 2026-07-15 | 2026-07-03 | 2026-07-13 | 100% | Completed | CHP-SUP-110 | JSW USL-CON-CHI-1020 | Superstructure | Z2 | EL(+)4.000 to EL(+)9.150
CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | Construct | 2026-07-09 | 2026-07-22 | 2026-07-09 | 2026-07-22 | 2026-07-09 | 2026-07-17 | 100% | Completed | CHP-SUP-120 | JSW USL-CON-CHI-1020 | Superstructure | Z3 | EL(+)4.000 to EL(+)9.150
CHP-SUP-130 | Staircase ST-2 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | Construct | 2026-06-18 | 2026-07-13 | 2026-06-18 | 2026-07-13 | 2026-06-25 | 2026-07-11 | 100% | Completed | CHP-SUP-130 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | EL(+)4.000 to EL(+)9.150
CHP-SUP-140 | Staircase ST-1 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | Construct | 2026-07-09 | 2026-08-03 | 2026-07-09 | 2026-08-03 | 2026-07-09 | 2026-07-25 | 100% | Completed | CHP-SUP-140 | JSW USL-CON-CHI-1020 | Superstructure | Z3 | EL(+)4.000 to EL(+)9.150
CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | Construct | 2026-07-09 | 2026-08-12 | 2026-07-09 | 2026-08-12 | 2026-07-09 | 2026-08-01 | 100% | Completed | CHP-SUP-150 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | T.O.C EL(+)9.150
CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | Construct | 2026-07-27 | 2026-08-28 | 2026-07-27 | 2026-08-28 | 2026-07-21 | 2026-08-12 | 100% | Completed | CHP-SUP-160 | JSW USL-CON-CHI-1020 | Superstructure | Z2 | T.O.C EL(+)9.150
CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | Construct | 2026-08-12 | 2026-09-09 | 2026-08-12 | 2026-09-09 | 2026-08-01 | 2026-08-20 | 100% | Completed | CHP-SUP-170 | JSW USL-CON-CHI-1020 | Superstructure | Z3 | T.O.C EL(+)9.150
CHP-SUP-180 | Mumty columns (EL +9.150 to +12.150) – ST-2 (C1 ×4) | Construct | 2026-08-13 | 2026-08-22 | 2026-08-13 | 2026-08-22 | 2026-08-03 | 2026-08-07 | 100% | Completed | CHP-SUP-180 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | EL(+)9.150 to EL(+)12.150
CHP-SUP-190 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-2 | Construct | 2026-08-24 | 2026-09-05 | 2026-08-24 | 2026-09-05 | 2026-08-08 | 2026-08-18 | 100% | Completed | CHP-SUP-190 | JSW USL-CON-CHI-1020 | Superstructure | Z1 | T.O.C EL(+)12.150
CHP-SUP-200 | Mumty columns (EL +9.150 to +12.150) – ST-1 (C1 ×4) | Construct | 2026-09-10 | 2026-09-18 | 2026-09-10 | 2026-09-18 | 2026-08-21 | 2026-08-27 | 100% | Completed | CHP-SUP-200 | JSW USL-CON-CHI-1020 | Superstructure | Z3 | EL(+)9.150 to EL(+)12.150
CHP-SUP-210 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-1 | Construct | 2026-09-19 | 2026-10-03 | 2026-09-19 |  | 2026-08-28 | 2026-09-05 | 92% | In Progress | CHP-SUP-210 | JSW USL-CON-CHI-1020 | Superstructure | Z3 | T.O.C EL(+)12.150
CHP-GRD-010 | Cable trench T1 (1500 deep) Row D–C, Grid 6→1 incl. cable pit at Grid 6 | Construct | 2026-05-15 | 2026-06-12 | 2026-05-15 | 2026-06-12 | 2026-06-02 | 2026-06-20 | 100% | Completed | CHP-GRD-010 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | Top EL ±0.000, base EL(-)1.500 / Top EL ±0.000
CHP-GRD-020 | Cable trench T2 (1500 deep) Row B–A, Grid 6→1 | Construct | 2026-05-27 | 2026-06-20 | 2026-05-27 | 2026-06-20 | 2026-06-10 | 2026-06-26 | 100% | Completed | CHP-GRD-020 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | Top EL ±0.000, base EL(-)1.500
CHP-GRD-030 | Grade slab 150 thk – Row E–D block (cable cellar, toilets, shift room, ante rooms) | Construct | 2026-07-21 | 2026-08-03 | 2026-07-21 | 2026-08-03 | 2026-07-17 | 2026-07-25 | 100% | Completed | CHP-GRD-030 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | T.O.C EL ±0.000 / (-)0.050
CHP-GRD-040 | Grade slab 150 thk – Row D–C strip (around trench T1) | Construct | 2026-07-27 | 2026-08-06 | 2026-07-27 | 2026-08-06 | 2026-07-21 | 2026-07-28 | 100% | Completed | CHP-GRD-040 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | T.O.C EL ±0.000
CHP-GRD-050 | Chiller foundations F1-01 & F1-02 (Bays 1–2, 2–3) | Construct | 2026-10-03 | 2026-10-24 |  |  | 2026-09-05 | 2026-09-19 | 0% | Not Started (Late) | CHP-GRD-050 | JSW USL-CON-CHI-1020 | Grade slab & foundations | Z1 | T.O.C EL ±0.000
CHP-GRD-060 | Chiller foundations F1-03 & F1-04 (Bays 3–4, 4–5) | Construct | 2026-10-09 | 2026-10-30 |  |  | 2026-09-10 | 2026-09-23 | 0% | Not Started (Late) | CHP-GRD-060 | JSW USL-CON-CHI-1020 | Grade slab & foundations | Z2 | T.O.C EL ±0.000
CHP-GRD-070 | Chiller foundation F1-05 (Bay 5–6) | Construct | 2026-10-15 | 2026-10-29 |  |  | 2026-09-14 | 2026-09-22 | 0% | Not Started (Late) | CHP-GRD-070 | JSW USL-CON-CHI-1020 | Grade slab & foundations | Z3 | T.O.C EL ±0.000
CHP-GRD-080 | Pump foundations F2-01 to F2-04 (Bays 1–3) | Construct | 2026-10-09 | 2026-10-21 |  |  | 2026-09-10 | 2026-09-17 | 0% | Not Started (Late) | CHP-GRD-080 | JSW USL-CON-CHI-1020 | Grade slab & foundations | Z1 | T.O.C EL ±0.000
CHP-GRD-090 | Pump foundations F2-05 to F2-08 (Bays 3–5) | Construct | 2026-10-15 | 2026-10-27 |  |  | 2026-09-14 | 2026-09-21 | 0% | Not Started (Late) | CHP-GRD-090 | JSW USL-CON-CHI-1020 | Grade slab & foundations | Z2 | T.O.C EL ±0.000
CHP-GRD-100 | Pump foundations F2-09 & F2-10 (Bay 5–6) | Construct | 2026-10-21 | 2026-10-27 |  |  | 2026-09-17 | 2026-09-21 | 0% | Not Started (Late) | CHP-GRD-100 | JSW USL-CON-CHI-1020 | Grade slab & foundations | Z3 | T.O.C EL ±0.000
CHP-GRD-110 | Cable slits (600 deep) between chiller foundations (5 nos) | Construct | 2026-10-31 | 2026-11-09 |  |  | 2026-09-24 | 2026-09-29 | 0% | Not Started (Late) | CHP-GRD-110 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | Top EL ±0.000
CHP-GRD-120 | Grade slab 150 thk – Chiller room (Row C–B) | Construct | 2026-11-10 | 2026-11-20 |  |  | 2026-09-30 | 2026-10-08 | 0% | Not Started (Late) | CHP-GRD-120 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | T.O.C EL ±0.000
CHP-GRD-130 | Grade slab 150 thk – Pump area (Row B–A) incl. 150×100 surface drain | Construct | 2026-11-13 | 2026-11-25 |  |  | 2026-10-05 | 2026-10-12 | 0% | Not Started | CHP-GRD-130 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | T.O.C EL ±0.000 / EL ±0.000
CHP-GRD-140 | Precast covers – cable trenches, cable pit & drain crossings (placement) | Construct | 2026-11-12 | 2026-11-18 |  |  | 2026-10-03 | 2026-10-07 | 0% | Not Started | CHP-GRD-140 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | EL ±0.000
CHP-GRD-150 | Plinth protection, garland drain & 100Ø PVC drain pipes (all round) | Construct | 2026-10-05 | 2026-10-22 |  |  | 2026-09-07 | 2026-09-17 | 0% | Not Started (Late) | CHP-GRD-150 | JSW USL-CON-CHI-1020 | Grade slab & foundations | All | FGL EL(-)0.500 / Below FGL
CHP-MS-090 | Civil works complete (all RCC incl. grade slab & equipment foundations) | Construct | 2026-11-25 | 2026-11-25 |  |  | 2026-10-12 | 2026-10-12 | 0% | Not Started |  | JSW USL-CON-CHI-1020 | Milestone
CHP-EQP-010 | Chiller CH-01 on F1-01 (Bay 1–2) – setting, levelling, alignment & grouting | Construct | 2027-01-02 | 2027-01-18 |  |  | 2027-01-15 | 2027-02-01 | 0% | Not Started | CHP-EQP-010 | JSW USL-CON-CHI-1030 | Equipment | Z1 | EL ±0.000
CHP-EQP-020 | Chiller CH-02 on F1-02 (Bay 2–3) – setting, levelling, alignment & grouting | Construct | 2027-01-12 | 2027-01-28 |  |  | 2027-01-25 | 2027-02-10 | 0% | Not Started | CHP-EQP-020 | JSW USL-CON-CHI-1030 | Equipment | Z1 | EL ±0.000
CHP-EQP-030 | Chiller CH-03 on F1-03 (Bay 3–4) – setting, levelling, alignment & grouting | Construct | 2027-01-21 | 2027-02-06 |  |  | 2027-02-04 | 2027-02-19 | 0% | Not Started | CHP-EQP-030 | JSW USL-CON-CHI-1030 | Equipment | Z2 | EL ±0.000
CHP-EQP-040 | Chiller CH-04 on F1-04 (Bay 4–5) – setting, levelling, alignment & grouting | Construct | 2027-02-01 | 2027-02-16 |  |  | 2027-02-13 | 2027-03-01 | 0% | Not Started | CHP-EQP-040 | JSW USL-CON-CHI-1030 | Equipment | Z2 | EL ±0.000
CHP-EQP-050 | Chiller CH-05 on F1-05 (Bay 5–6) – setting, levelling, alignment & grouting | Construct | 2027-02-10 | 2027-02-25 |  |  | 2027-02-23 | 2027-03-11 | 0% | Not Started | CHP-EQP-050 | JSW USL-CON-CHI-1030 | Equipment | Z3 | EL ±0.000
CHP-EQP-060 | Hoists – 2T chain pulley block on MR-1 & 10T electric hoist on MR-2 | Construct | 2027-01-02 | 2027-01-07 |  |  | 2027-01-15 | 2027-01-20 | 0% | Not Started | CHP-EQP-060 | JSW USL-CON-CHI-1030 | Equipment | All | B.O.MR +8.100 / B.O.MR +7.900
CHP-EQP-070 | Pumps P-01 to P-04 on F2-01..04 (Bays 1–3) – setting, alignment & grouting | Construct | 2027-01-14 | 2027-01-28 |  |  | 2027-01-28 | 2027-02-10 | 0% | Not Started | CHP-EQP-070 | JSW USL-CON-CHI-1030 | Equipment | Z1 | EL ±0.000
CHP-EQP-080 | Pumps P-05 to P-08 on F2-05..08 (Bays 3–5) – setting, alignment & grouting | Construct | 2027-01-23 | 2027-02-06 |  |  | 2027-02-06 | 2027-02-19 | 0% | Not Started | CHP-EQP-080 | JSW USL-CON-CHI-1030 | Equipment | Z2 | EL ±0.000
CHP-EQP-090 | Pumps P-09 & P-10 on F2-09..10 (Bay 5–6) – setting, alignment & grouting | Construct | 2027-02-03 | 2027-02-11 |  |  | 2027-02-16 | 2027-02-24 | 0% | Not Started | CHP-EQP-090 | JSW USL-CON-CHI-1030 | Equipment | Z3 | EL ±0.000
CHP-EQP-100 | Final alignment, motor/drive coupling & box-up of chillers and pumps | Construct | 2027-02-26 | 2027-03-20 |  |  | 2027-03-12 | 2027-04-03 | 0% | Not Started | CHP-EQP-100 | JSW USL-CON-CHI-1030 | Equipment | All | ±0.000
CHP-PIP-010 | Pipe supports & sleepers – chiller hall | Construct | 2027-01-27 | 2027-02-12 |  |  | 2027-02-09 | 2027-02-25 | 0% | Not Started | CHP-PIP-010 | JSW USL-CON-CHI-1040 | Piping | All | ±0.000 to +3.0
CHP-PIP-020 | CHW & CW headers (supply / return) – fabrication & erection | Construct | 2027-02-05 | 2027-03-05 |  |  | 2027-02-18 | 2027-03-19 | 0% | Not Started | CHP-PIP-020 | JSW USL-CON-CHI-1040 | Piping | All | Header elevation
CHP-PIP-030 | Chiller hook-up piping CH-01..CH-05 incl. valves, strainers & flexible connectors | Construct | 2027-02-26 | 2027-03-23 |  |  | 2027-03-12 | 2027-04-05 | 0% | Not Started | CHP-PIP-030 | JSW USL-CON-CHI-1040 | Piping | All | ±0.000 to +3.0
CHP-PIP-040 | Pump suction / discharge hook-up P-01..P-10 | Construct | 2027-02-19 | 2027-03-12 |  |  | 2027-03-04 | 2027-03-26 | 0% | Not Started | CHP-PIP-040 | JSW USL-CON-CHI-1040 | Piping | All | ±0.000 to +2.0
CHP-PIP-050 | Hydro test, flushing & reinstatement | Construct | 2027-03-24 | 2027-04-08 |  |  | 2027-04-06 | 2027-04-21 | 0% | Not Started | CHP-PIP-050 | JSW USL-CON-CHI-1040 | Piping | All | All
CHP-ELE-010 | Cable trays & supports – trenches T1/T2, cable pit & cable cellar | Construct | 2027-02-02 | 2027-02-24 |  |  | 2027-02-15 | 2027-03-10 | 0% | Not Started | CHP-ELE-010 | JSW USL-CON-CHI-1050 | Electrical | All | EL(-)1.500 to ±0.000
CHP-ELE-020 | Cable trays & supports – chiller hall, switchgear room & first floor | Construct | 2027-02-11 | 2027-03-05 |  |  | 2027-02-24 | 2027-03-19 | 0% | Not Started | CHP-ELE-020 | JSW USL-CON-CHI-1050 | Electrical | All | +0.000 to +8.0
CHP-ELE-030 | Cable laying, glanding & termination (power & control) | Construct | 2027-02-19 | 2027-03-27 |  |  | 2027-03-04 | 2027-04-09 | 0% | Not Started | CHP-ELE-030 | JSW USL-CON-CHI-1050 | Electrical | All | All
CHP-ELE-040 | Earthing & lightning protection | Construct | 2027-02-19 | 2027-03-08 |  |  | 2027-03-04 | 2027-03-23 | 0% | Not Started | CHP-ELE-040 | JSW USL-CON-CHI-1060 | Electrical | All | All
CHP-ELE-050 | Lighting fixtures, JBs & small power | Construct | 2027-02-25 | 2027-04-14 |  |  | 2027-03-11 | 2027-04-27 | 0% | Not Started | CHP-ELE-050 | JSW USL-CON-CHI-1060 | Electrical | All | All
CHP-ELE-060 | Switchgear room panels (6.6 kV SWBD, ESS6-PDB-1) – placement & termination | Construct | 2027-02-19 | 2027-03-15 |  |  | 2027-03-04 | 2027-03-29 | 0% | Not Started | CHP-ELE-060 | JSW USL-CON-CHI-1060 | Electrical | All | +4.050 FFL
CHP-INS-010 | Field instruments installation (PT / TT / FT / flow switches) | Construct | 2027-03-10 | 2027-04-08 |  |  | 2027-03-24 | 2027-04-21 | 0% | Not Started | CHP-INS-010 | JSW USL-CON-CHI-1070 | Instrumentation | All | ±0.000 to +3.0
CHP-INS-020 | Instrument cabling, impulse tubing & loop checks | Construct | 2027-03-23 | 2027-05-03 |  |  | 2027-04-05 | 2027-05-15 | 0% | Not Started | CHP-INS-020 | JSW USL-CON-CHI-1070 | Instrumentation | All | All
CHP-MS-100 | Chiller plant ready for Mechanical Completion (feeds JSW USL-COM-1110) | Construct | 2027-05-03 | 2027-05-03 |  |  | 2027-05-15 | 2027-05-15 | 0% | Not Started |  | JSW USL-CON-CHI-1070 | Milestone
CHP-ARC-010 | Brickwork 230 thk – GF Row E–D block up to lintel level | Construct | 2026-10-05 | 2026-10-17 |  |  | 2026-10-05 | 2026-10-17 | 0% | Not Started | CHP-ARC-010 | CHP.A1 | Architectural | All | EL ±0.000 to +2.100
CHP-ARC-020 | Lintels & chajjas – GF (LB1–LB6) | Construct | 2026-10-14 | 2026-10-21 |  |  | 2026-10-14 | 2026-10-21 | 0% | Not Started | CHP-ARC-020 | CHP.A1 | Architectural | All | B/O lintel +2.100 to +3.400
CHP-ARC-030 | Brickwork – GF above lintel up to first-floor soffit | Construct | 2026-10-22 | 2026-10-30 |  |  | 2026-10-22 | 2026-10-30 | 0% | Not Started | CHP-ARC-030 | CHP.A1 | Architectural | All | +2.100 to +3.400
CHP-ARC-040 | Brickwork – FF (switchgear, AC & AHU rooms, ante rooms) up to lintel | Construct | 2026-10-27 | 2026-11-06 |  |  | 2026-10-27 | 2026-11-06 | 0% | Not Started | CHP-ARC-040 | CHP.A1 | Architectural | All | +4.000 to +6.150
CHP-ARC-050 | Lintels & chajjas – FF (LB7–LB9B) | Construct | 2026-11-04 | 2026-11-10 |  |  | 2026-11-04 | 2026-11-10 | 0% | Not Started | CHP-ARC-050 | CHP.A1 | Architectural | All | B/O lintel +6.150 to +7.350
CHP-ARC-060 | Brickwork – chiller hall external walls (Row A, Grid 1 & 6) incl. LB1A lintels & monorail-door openings | Construct | 2026-10-12 | 2026-11-04 |  |  | 2026-10-12 | 2026-11-04 | 0% | Not Started | CHP-ARC-060 | CHP.A1 | Architectural | All | ±0.000 to +9.150
CHP-ARC-070 | Mumty brickwork & lintels LB10–LB12 – ST-1 & ST-2 | Construct | 2026-10-05 | 2026-10-15 |  |  | 2026-10-05 | 2026-10-15 | 0% | Not Started | CHP-ARC-070 | CHP.A1 | Architectural | All | +9.150 to +12.150
CHP-ARC-080 | Parapet wall, roof waterproofing, PCC wearing course & rainwater pipes | Construct | 2026-10-08 | 2026-10-26 |  |  | 2026-10-08 | 2026-10-26 | 0% | Not Started | CHP-ARC-080 | CHP.A1 | Architectural | All | +9.150 / +12.150
CHP-ARC-090 | Plastering – internal & external | Construct | 2026-11-11 | 2026-12-09 |  |  | 2026-11-11 | 2026-12-09 | 0% | Not Started | CHP-ARC-090 | CHP.A1 | Architectural | All | All
CHP-ARC-100 | Flooring & floor finishes (GF rooms, FF, staircases) | Construct | 2026-11-26 | 2026-12-12 |  |  | 2026-11-26 | 2026-12-12 | 0% | Not Started | CHP-ARC-100 | CHP.A1 | Architectural | All | ±0.000 / +4.050
CHP-ARC-110 | Doors, windows, rolling shutters & monorail doors | Construct | 2026-11-28 | 2026-12-15 |  |  | 2026-11-28 | 2026-12-15 | 0% | Not Started | CHP-ARC-110 | CHP.A1 | Architectural | All | All
CHP-ARC-120 | Painting – internal & external | Construct | 2026-12-10 | 2027-01-04 |  |  | 2026-12-10 | 2027-01-04 | 0% | Not Started | CHP-ARC-120 | CHP.A1 | Architectural | All | All
CHP-STL-010 | Monorail beams MR-1 (NPB 300×150, B.O.MR +8.100) & MR-2 (NPB 500×200, B.O.MR +7.900) incl. end stoppers | Construct | 2026-11-02 | 2026-11-12 |  |  | 2026-11-02 | 2026-11-12 | 0% | Not Started | CHP-STL-010 | CHP.A2 | Steel & misc. | All | +7.900 / +8.100 B.O.MR
CHP-STL-020 | Handrails – staircases ST-1/ST-2 & removable handrails at FF openings / platforms | Construct | 2026-11-17 | 2026-11-27 |  |  | 2026-11-17 | 2026-11-27 | 0% | Not Started | CHP-STL-020 | CHP.A2 | Steel & misc. | All | +1.300 to +12.150

## Gantt
GANTT – current schedule (weekly) ¦ green = completed, orange = in progress (dark = done to Data Date), blue = not started, red = milestone, pink column = Data Date week
[7 empty] | Oct-25 |  |  | Nov-25 |  |  |  | Dec-25 |  |  |  |  | Jan-26 |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  |  | Apr-26 |  |  |  | May-26 |  |  |  | Jun-26 |  |  |  |  | Jul-26 |  |  |  | Aug-26 |  |  |  |  | Sep-26 |  |  |  | Oct-26 |  |  |  | Nov-26 |  |  |  |  | Dec-26 |  |  |  | Jan-27 |  |  |  | Feb-27 |  |  |  | Mar-27 |  |  |  |  | Apr-27 |  |  |  | May-27
Activity ID | Activity Name | Type | Start | Finish | Status | % | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10
CHP | CHILLER PLANT (combined for PP-1 & PP-2) – P6 WBS: Pellet Plant-1 › Utilities › Chiller Plant | WBS | 2025-10-20 | 2027-05-03 | In Progress | 52.62%
CHP.E | ENGINEERING | WBS | 2025-10-20 | 2026-12-11 | In Progress | 45.73%
JSW USL-BE-CHI-1000 | Basic drawings from TS - Inputs | GRP | 2025-10-20 | 2025-10-20 | Completed | 100%
CHP-MS-010 | Basic drawings / technical specification inputs received | MS | 2025-10-20 | 2025-10-20 | Completed | 100%
JSW USL-DE-CHI-1000 | Pile drawings release | GRP | 2025-11-29 | 2025-12-22 | Completed | 100%
CHP-ENG-010 | Pile layout & detail drawing (19530-001) – design & preparation | Task | 2025-11-29 | 2025-12-15 | Completed | 100%
CHP-ENG-020 | Pile drawing – review, client approval & IFC issue | Task | 2025-12-16 | 2025-12-22 | Completed | 100%
CHP-MS-020 | Pile drawings released (IFC) | MS | 2025-12-22 | 2025-12-22 | Completed | 100%
JSW USL-DE-CHI-1010 | Civil drawings release | GRP | 2025-12-23 | 2026-01-07 | Completed | 100%
CHP-ENG-030 | Civil GA & RC drawings 19531-001 … 008 – preparation & checking | Task | 2025-12-23 | 2025-12-31 | Completed | 100%
CHP-ENG-040 | Civil drawings – client review & IFC release | Task | 2026-01-02 | 2026-01-07 | Completed | 100%
CHP-MS-030 | Civil drawings released (IFC) | MS | 2026-01-07 | 2026-01-07 | Completed | 100%
JSW USL-DE-CHI-1020 | Equipment drawings release | GRP | 2026-08-31 | 2026-09-24 | Completed | 100%
CHP-ENG-050 | Vendor GA drawings (centrifugal chillers & pumps) – receipt & review | Task | 2026-08-31 | 2026-09-14 | Completed | 100%
CHP-ENG-060 | Equipment layout & foundation loading data – approval & release | Task | 2026-09-15 | 2026-09-24 | Completed | 100%
CHP-MS-040 | Equipment drawings released – HOLD on chiller / pump foundations F1 & F2 lifted | MS | 2026-09-24 | 2026-09-24 | Completed | 100%
JSW USL-DE-CHI-1030 | Piping drawings release | GRP | 2026-10-03 | 2026-11-19 | Not Started | 0%
CHP-ENG-070 | Piping GA, isometric & pipe-support drawings – preparation | Task | 2026-10-03 | 2026-11-07 | Not Started | 0%
CHP-ENG-080 | Piping drawings – review, comments & IFC release | Task | 2026-11-09 | 2026-11-19 | Not Started | 0%
CHP-MS-050 | Piping drawings released (IFC) | MS | 2026-11-19 | 2026-11-19 | Not Started | 0%
JSW USL-DE-CHI-1040 | E&I drawings release | GRP | 2026-10-01 | 2026-12-11 | In Progress | 23.27%
CHP-ENG-090 | E&I layouts (cable routing, lighting, earthing, instrument locations) – preparation | Task | 2026-10-01 | 2026-10-26 | In Progress | 38%
CHP-ENG-100 | E&I drawings – coordination with piping drawings, review & IFC release | Task | 2026-11-20 | 2026-12-11 | Not Started | 0%
CHP-MS-060 | E&I drawings released (IFC) | MS | 2026-12-11 | 2026-12-11 | Not Started | 0%
CHP.P | PROCUREMENT | WBS | 2026-02-03 | 2026-12-31 | In Progress | 72.92%
JSW USL-PR-2440 | Centrifugal Chillers - PR to PO | GRP | 2026-02-03 | 2026-05-20 | Completed | 100%
CHP-PRC-010 | Centrifugal chillers – PR, RFQ, bids & technical evaluation | Task | 2026-02-03 | 2026-04-13 | Completed | 100%
CHP-PRC-020 | Centrifugal chillers – commercial negotiation & PO placement | Task | 2026-04-14 | 2026-05-20 | Completed | 100%
CHP-PRC-030 | PO placed – centrifugal chillers | MS | 2026-05-20 | 2026-05-20 | Completed | 100%
JSW USL-PR-2450 | Centrifugal Chillers - Manufacturing, Inspection & Delivery | GRP | 2026-05-22 | 2026-12-31 | In Progress | 60.1%
CHP-PRC-040 | Centrifugal chillers – manufacturing | Task | 2026-05-22 | 2026-12-03 | In Progress | 68.48%
CHP-PRC-050 | Centrifugal chillers – stage inspection & FAT | Task | 2026-12-04 | 2026-12-12 | Not Started | 0%
CHP-PRC-060 | Centrifugal chillers – dispatch & transit to site | Task | 2026-12-14 | 2026-12-31 | Not Started | 0%
CHP-MS-070 | Centrifugal chillers delivered at site | MS | 2026-12-31 | 2026-12-31 | Not Started | 0%
JSW USL-PR-2460 | Pumps - PR to PO | GRP | 2026-02-03 | 2026-04-27 | Completed | 100%
CHP-PRC-070 | Pumps – PR, RFQ, bids & technical evaluation | Task | 2026-02-03 | 2026-03-30 | Completed | 100%
CHP-PRC-080 | Pumps – commercial negotiation & PO placement | Task | 2026-03-31 | 2026-04-27 | Completed | 100%
CHP-PRC-090 | PO placed – pumps | MS | 2026-04-27 | 2026-04-27 | Completed | 100%
JSW USL-PR-2470 | Pumps - Manufacturing, Inspection & Delivery | GRP | 2026-04-29 | 2026-12-31 | In Progress | 63.77%
CHP-PRC-100 | Pumps – manufacturing | Task | 2026-04-29 | 2026-12-07 | In Progress | 70.59%
CHP-PRC-110 | Pumps – inspection & performance test | Task | 2026-12-08 | 2026-12-14 | Not Started (Late) | 0%
CHP-PRC-120 | Pumps – dispatch & transit to site | Task | 2026-12-15 | 2026-12-31 | Not Started (Late) | 0%
CHP-MS-080 | Pumps delivered at site | MS | 2026-12-31 | 2026-12-31 | Not Started (Late) | 0%
CHP.C | CONSTRUCTION | WBS | 2025-12-17 | 2027-05-03 | In Progress | 52.02%
JSW USL-CON-CHI-1000 | Piling Works | GRP | 2025-12-17 | 2026-01-19 | Completed | 100%
CHP-PIL-010 | Piles Row A (P1–P7) | Task | 2025-12-17 | 2025-12-20 | Completed | 100%
CHP-PIL-020 | Piles Row B (P8–P16) | Task | 2025-12-22 | 2025-12-27 | Completed | 100%
CHP-PIL-030 | Piles Row C (P17–P22) | Task | 2025-12-29 | 2025-12-31 | Completed | 100%
CHP-PIL-040 | Piles Row D (P23–P34) | Task | 2026-01-02 | 2026-01-08 | Completed | 100%
CHP-PIL-050 | Piles Rows D.1 & D.2 (P35–P41) | Task | 2026-01-09 | 2026-01-13 | Completed | 100%
CHP-PIL-060 | Piles Row E (P42–P53) | Task | 2026-01-14 | 2026-01-19 | Completed | 100%
JSW USL-CON-CHI-1010 | Excavation incl. pile chipping | GRP | 2026-02-18 | 2026-03-30 | Completed | 100%
CHP-EXC-010 | Excavation, pile chipping & PCC prep – Zone-1 (Grid 1–3) | Task | 2026-02-18 | 2026-03-07 | Completed | 100%
CHP-EXC-020 | Excavation, pile chipping & PCC prep – Zone-2 (Grid 3–5) | Task | 2026-03-05 | 2026-03-18 | Completed | 100%
CHP-EXC-030 | Excavation, pile chipping & PCC prep – Zone-3 (Grid 5–6) | Task | 2026-03-16 | 2026-03-30 | Completed | 100%
JSW USL-CON-CHI-1020 | Concreting - Foundations, Columns, Beams, Walls, etc. | GRP | 2026-03-08 | 2026-11-25 | In Progress | 73.74%
CHP-SUB-010 | PCC (M7.5) & pile caps – Zone-1 (17 nos: PC1 ×9, PC2 ×8) | Task | 2026-03-08 | 2026-03-25 | Completed | 100%
CHP-SUB-020 | PCC (M7.5) & pile caps – Zone-2 (10 nos: PC1 ×4, PC2 ×6) | Task | 2026-03-19 | 2026-03-31 | Completed | 100%
CHP-SUB-030 | PCC (M7.5) & pile caps – Zone-3 (8 nos: PC1 ×4, PC2 ×4) | Task | 2026-03-31 | 2026-04-08 | Completed | 100%
CHP-SUB-040 | Pile cap beams PCB1/PCB2/PCB3 & column pedestals (B.O.C -2.500 to -0.300) – Zone-1 | Task | 2026-03-26 | 2026-04-11 | Completed | 100%
CHP-SUB-050 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-2 | Task | 2026-04-04 | 2026-04-17 | Completed | 100%
CHP-SUB-060 | Pile cap beams PCB1/PCB2 & column pedestals – Zone-3 | Task | 2026-04-11 | 2026-04-22 | Completed | 100%
CHP-SUB-070 | Backfilling & compaction up to plinth level – Zone-1 | Task | 2026-04-13 | 2026-04-18 | Completed | 100%
CHP-SUB-080 | Backfilling & compaction up to plinth level – Zone-2 | Task | 2026-04-20 | 2026-04-24 | Completed | 100%
CHP-SUB-090 | Backfilling & compaction up to plinth level – Zone-3 | Task | 2026-04-25 | 2026-04-30 | Completed | 100%
CHP-SUB-100 | Plinth beams PB (TOB EL(-)0.300) – Zone-1 | Task | 2026-04-20 | 2026-05-04 | Completed | 100%
CHP-SUB-110 | Plinth beams PB (TOB EL(-)0.300) – Zone-2 | Task | 2026-04-27 | 2026-05-08 | Completed | 100%
CHP-SUB-120 | Plinth beams PB (TOB EL(-)0.300) – Zone-3 | Task | 2026-05-04 | 2026-05-14 | Completed | 100%
CHP-SUP-010 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-1 (18 nos incl. SC1) | Task | 2026-05-05 | 2026-05-20 | Completed | 100%
CHP-SUP-020 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-2 (10 nos) | Task | 2026-05-13 | 2026-05-23 | Completed | 100%
CHP-SUP-030 | Columns Lift-1 (EL -0.300 to +4.000) – Zone-3 (8 nos) | Task | 2026-05-19 | 2026-05-27 | Completed | 100%
CHP-SUP-040 | Tie beam TB1 (TOB EL +2.100) at Grid 1 | Task | 2026-05-12 | 2026-05-16 | Completed | 100%
CHP-SUP-050 | Staircase ST-2 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | Task | 2026-05-21 | 2026-06-06 | Completed | 100%
CHP-SUP-060 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-1 (Grid 1–3, Row E–D) | Task | 2026-05-21 | 2026-06-17 | Completed | 100%
CHP-SUP-070 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-2 (Grid 3–5, Row E–D) | Task | 2026-06-04 | 2026-06-29 | Completed | 100%
CHP-SUP-080 | First floor beams & 150 thk slab (TOC EL +4.000) – Zone-3 (Grid 5–6, Row E–D) | Task | 2026-06-16 | 2026-07-08 | Completed | 100%
CHP-SUP-090 | Staircase ST-1 – flights FLT-1 to FLT-3, landings +1.300/+2.650 up to +4.000 | Task | 2026-05-28 | 2026-06-13 | Completed | 100%
CHP-SUP-100 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-1 (18 nos incl. SC1) | Task | 2026-06-18 | 2026-07-08 | Completed | 100%
CHP-SUP-110 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-2 (10 nos) | Task | 2026-06-30 | 2026-07-15 | Completed | 100%
CHP-SUP-120 | Columns Lift-2 (EL +4.000 to +9.150) – Zone-3 (8 nos) | Task | 2026-07-09 | 2026-07-22 | Completed | 100%
CHP-SUP-130 | Staircase ST-2 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | Task | 2026-06-18 | 2026-07-13 | Completed | 100%
CHP-SUP-140 | Staircase ST-1 – flights FLT-4 to FLT-7, landings +5.350/+6.700/+7.900 up to +9.150 | Task | 2026-07-09 | 2026-08-03 | Completed | 100%
CHP-SUP-150 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-1 (Grid 1–3, Row E–A) | Task | 2026-07-09 | 2026-08-12 | Completed | 100%
CHP-SUP-160 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-2 (Grid 3–5, Row E–A) | Task | 2026-07-27 | 2026-08-28 | Completed | 100%
CHP-SUP-170 | Roof beams & 150 thk slab (TOC EL +9.150) – Zone-3 (Grid 5–6, Row E–A) | Task | 2026-08-12 | 2026-09-09 | Completed | 100%
CHP-SUP-180 | Mumty columns (EL +9.150 to +12.150) – ST-2 (C1 ×4) | Task | 2026-08-13 | 2026-08-22 | Completed | 100%
CHP-SUP-190 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-2 | Task | 2026-08-24 | 2026-09-05 | Completed | 100%
CHP-SUP-200 | Mumty columns (EL +9.150 to +12.150) – ST-1 (C1 ×4) | Task | 2026-09-10 | 2026-09-18 | Completed | 100%
CHP-SUP-210 | Mumty roof beams RB15/RB16 & slab (TOC EL +12.150) – ST-1 | Task | 2026-09-19 | 2026-10-03 | In Progress | 92%
CHP-GRD-010 | Cable trench T1 (1500 deep) Row D–C, Grid 6→1 incl. cable pit at Grid 6 | Task | 2026-05-15 | 2026-06-12 | Completed | 100%
CHP-GRD-020 | Cable trench T2 (1500 deep) Row B–A, Grid 6→1 | Task | 2026-05-27 | 2026-06-20 | Completed | 100%
CHP-GRD-030 | Grade slab 150 thk – Row E–D block (cable cellar, toilets, shift room, ante rooms) | Task | 2026-07-21 | 2026-08-03 | Completed | 100%
CHP-GRD-040 | Grade slab 150 thk – Row D–C strip (around trench T1) | Task | 2026-07-27 | 2026-08-06 | Completed | 100%
CHP-GRD-050 | Chiller foundations F1-01 & F1-02 (Bays 1–2, 2–3) | Task | 2026-10-03 | 2026-10-24 | Not Started (Late) | 0%
CHP-GRD-060 | Chiller foundations F1-03 & F1-04 (Bays 3–4, 4–5) | Task | 2026-10-09 | 2026-10-30 | Not Started (Late) | 0%
CHP-GRD-070 | Chiller foundation F1-05 (Bay 5–6) | Task | 2026-10-15 | 2026-10-29 | Not Started (Late) | 0%
CHP-GRD-080 | Pump foundations F2-01 to F2-04 (Bays 1–3) | Task | 2026-10-09 | 2026-10-21 | Not Started (Late) | 0%
CHP-GRD-090 | Pump foundations F2-05 to F2-08 (Bays 3–5) | Task | 2026-10-15 | 2026-10-27 | Not Started (Late) | 0%
CHP-GRD-100 | Pump foundations F2-09 & F2-10 (Bay 5–6) | Task | 2026-10-21 | 2026-10-27 | Not Started (Late) | 0%
CHP-GRD-110 | Cable slits (600 deep) between chiller foundations (5 nos) | Task | 2026-10-31 | 2026-11-09 | Not Started (Late) | 0%
CHP-GRD-120 | Grade slab 150 thk – Chiller room (Row C–B) | Task | 2026-11-10 | 2026-11-20 | Not Started (Late) | 0%
CHP-GRD-130 | Grade slab 150 thk – Pump area (Row B–A) incl. 150×100 surface drain | Task | 2026-11-13 | 2026-11-25 | Not Started | 0%
CHP-GRD-140 | Precast covers – cable trenches, cable pit & drain crossings (placement) | Task | 2026-11-12 | 2026-11-18 | Not Started | 0%
CHP-GRD-150 | Plinth protection, garland drain & 100Ø PVC drain pipes (all round) | Task | 2026-10-05 | 2026-10-22 | Not Started (Late) | 0%
CHP-MS-090 | Civil works complete (all RCC incl. grade slab & equipment foundations) | MS | 2026-11-25 | 2026-11-25 | Not Started | 0%
JSW USL-CON-CHI-1030 | Erection of Chiller Plant including Fans, Pumps, Drives, etc. | GRP | 2027-01-02 | 2027-03-20 | Not Started | 0%
CHP-EQP-010 | Chiller CH-01 on F1-01 (Bay 1–2) – setting, levelling, alignment & grouting | Task | 2027-01-02 | 2027-01-18 | Not Started | 0%
CHP-EQP-020 | Chiller CH-02 on F1-02 (Bay 2–3) – setting, levelling, alignment & grouting | Task | 2027-01-12 | 2027-01-28 | Not Started | 0%
CHP-EQP-030 | Chiller CH-03 on F1-03 (Bay 3–4) – setting, levelling, alignment & grouting | Task | 2027-01-21 | 2027-02-06 | Not Started | 0%
CHP-EQP-040 | Chiller CH-04 on F1-04 (Bay 4–5) – setting, levelling, alignment & grouting | Task | 2027-02-01 | 2027-02-16 | Not Started | 0%
CHP-EQP-050 | Chiller CH-05 on F1-05 (Bay 5–6) – setting, levelling, alignment & grouting | Task | 2027-02-10 | 2027-02-25 | Not Started | 0%
CHP-EQP-060 | Hoists – 2T chain pulley block on MR-1 & 10T electric hoist on MR-2 | Task | 2027-01-02 | 2027-01-07 | Not Started | 0%
CHP-EQP-070 | Pumps P-01 to P-04 on F2-01..04 (Bays 1–3) – setting, alignment & grouting | Task | 2027-01-14 | 2027-01-28 | Not Started | 0%
CHP-EQP-080 | Pumps P-05 to P-08 on F2-05..08 (Bays 3–5) – setting, alignment & grouting | Task | 2027-01-23 | 2027-02-06 | Not Started | 0%
CHP-EQP-090 | Pumps P-09 & P-10 on F2-09..10 (Bay 5–6) – setting, alignment & grouting | Task | 2027-02-03 | 2027-02-11 | Not Started | 0%
CHP-EQP-100 | Final alignment, motor/drive coupling & box-up of chillers and pumps | Task | 2027-02-26 | 2027-03-20 | Not Started | 0%
JSW USL-CON-CHI-1040 | Piping works incl. testing | GRP | 2027-01-27 | 2027-04-08 | Not Started | 0%
CHP-PIP-010 | Pipe supports & sleepers – chiller hall | Task | 2027-01-27 | 2027-02-12 | Not Started | 0%
CHP-PIP-020 | CHW & CW headers (supply / return) – fabrication & erection | Task | 2027-02-05 | 2027-03-05 | Not Started | 0%
CHP-PIP-030 | Chiller hook-up piping CH-01..CH-05 incl. valves, strainers & flexible connectors | Task | 2027-02-26 | 2027-03-23 | Not Started | 0%
CHP-PIP-040 | Pump suction / discharge hook-up P-01..P-10 | Task | 2027-02-19 | 2027-03-12 | Not Started | 0%
CHP-PIP-050 | Hydro test, flushing & reinstatement | Task | 2027-03-24 | 2027-04-08 | Not Started | 0%
JSW USL-CON-CHI-1050 | Cable tray erection incl. support, cable Laying | GRP | 2027-02-02 | 2027-03-27 | Not Started | 0%
CHP-ELE-010 | Cable trays & supports – trenches T1/T2, cable pit & cable cellar | Task | 2027-02-02 | 2027-02-24 | Not Started | 0%
CHP-ELE-020 | Cable trays & supports – chiller hall, switchgear room & first floor | Task | 2027-02-11 | 2027-03-05 | Not Started | 0%
CHP-ELE-030 | Cable laying, glanding & termination (power & control) | Task | 2027-02-19 | 2027-03-27 | Not Started | 0%
JSW USL-CON-CHI-1060 | Other electrical works incl. light fixtures installation | GRP | 2027-02-19 | 2027-04-14 | Not Started | 0%
CHP-ELE-040 | Earthing & lightning protection | Task | 2027-02-19 | 2027-03-08 | Not Started | 0%
CHP-ELE-050 | Lighting fixtures, JBs & small power | Task | 2027-02-25 | 2027-04-14 | Not Started | 0%
CHP-ELE-060 | Switchgear room panels (6.6 kV SWBD, ESS6-PDB-1) – placement & termination | Task | 2027-02-19 | 2027-03-15 | Not Started | 0%
JSW USL-CON-CHI-1070 | Instrument installation works | GRP | 2027-03-10 | 2027-05-03 | Not Started | 0%
CHP-INS-010 | Field instruments installation (PT / TT / FT / flow switches) | Task | 2027-03-10 | 2027-04-08 | Not Started | 0%
CHP-INS-020 | Instrument cabling, impulse tubing & loop checks | Task | 2027-03-23 | 2027-05-03 | Not Started | 0%
CHP-MS-100 | Chiller plant ready for Mechanical Completion (feeds JSW USL-COM-1110) | MS | 2027-05-03 | 2027-05-03 | Not Started | 0%
CHP.A | ADDITIONAL SCOPE – NOT IN P6 (planned by 4D team) | WBS | 2026-10-05 | 2027-01-04 | Not Started | 0%
CHP.A1 | Masonry, lintels & architectural finishes | GRP | 2026-10-05 | 2027-01-04 | Not Started | 0%
CHP-ARC-010 | Brickwork 230 thk – GF Row E–D block up to lintel level | Task | 2026-10-05 | 2026-10-17 | Not Started | 0%
CHP-ARC-020 | Lintels & chajjas – GF (LB1–LB6) | Task | 2026-10-14 | 2026-10-21 | Not Started | 0%
CHP-ARC-030 | Brickwork – GF above lintel up to first-floor soffit | Task | 2026-10-22 | 2026-10-30 | Not Started | 0%
CHP-ARC-040 | Brickwork – FF (switchgear, AC & AHU rooms, ante rooms) up to lintel | Task | 2026-10-27 | 2026-11-06 | Not Started | 0%
CHP-ARC-050 | Lintels & chajjas – FF (LB7–LB9B) | Task | 2026-11-04 | 2026-11-10 | Not Started | 0%
CHP-ARC-060 | Brickwork – chiller hall external walls (Row A, Grid 1 & 6) incl. LB1A lintels & monorail-door openings | Task | 2026-10-12 | 2026-11-04 | Not Started | 0%
CHP-ARC-070 | Mumty brickwork & lintels LB10–LB12 – ST-1 & ST-2 | Task | 2026-10-05 | 2026-10-15 | Not Started | 0%
CHP-ARC-080 | Parapet wall, roof waterproofing, PCC wearing course & rainwater pipes | Task | 2026-10-08 | 2026-10-26 | Not Started | 0%
CHP-ARC-090 | Plastering – internal & external | Task | 2026-11-11 | 2026-12-09 | Not Started | 0%
CHP-ARC-100 | Flooring & floor finishes (GF rooms, FF, staircases) | Task | 2026-11-26 | 2026-12-12 | Not Started | 0%
CHP-ARC-110 | Doors, windows, rolling shutters & monorail doors | Task | 2026-11-28 | 2026-12-15 | Not Started | 0%
CHP-ARC-120 | Painting – internal & external | Task | 2026-12-10 | 2027-01-04 | Not Started | 0%
CHP.A2 | Structural steel & miscellaneous | GRP | 2026-11-02 | 2026-11-27 | Not Started | 0%
CHP-STL-010 | Monorail beams MR-1 (NPB 300×150, B.O.MR +8.100) & MR-2 (NPB 500×200, B.O.MR +7.900) incl. end stoppers | Task | 2026-11-02 | 2026-11-12 | Not Started | 0%
CHP-STL-020 | Handrails – staircases ST-1/ST-2 & removable handrails at FF openings / platforms | Task | 2026-11-17 | 2026-11-27 | Not Started | 0%

## P6 Roll-up
P6 ROLL-UP & PROGRESS CHECK – detailed 4D schedule vs P6 (Chiller Plant)
Every P6 activity is a GROUP in the 4D Schedule. Group dates are live roll-ups of the detailed activities sequenced inside it; at the Data Date they are identical to P6 for baseline, current and actual dates (column AB).
P6 ACTIVITY | [6 empty] | P6 DATES (XER, DD 02-Oct-26) | [6 empty] | GROUP IN 4D SCHEDULE (live roll-up of detailed activities) | [8 empty] | CHECK
P6 Activity ID (= Group) | Activity Name | Phase | P6 Status | P6 OD | P6 RD | P6 % | P6 BL Start | P6 BL Finish | P6 Start | P6 Finish | P6 Actual Start | P6 Actual Finish | P6 TF (d) | No. of detailed activities | No. completed | Group BL Start | Group BL Finish | Group Start | Group Finish | Group Actual Start | Group Actual Finish | Group % (qty / dur weighted) | Δ BL Start (wd) | Δ BL Finish (wd) | Δ Start (wd) | Δ Finish (wd) | Check (BL, current & actual)
JSW USL-BE-CHI-1000 | Basic drawings from TS - Inputs | Engineering | Completed | 0 | 0 | 100% | 2026-01-21 | 2026-01-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 |  | 1 | 1 | 2026-01-20 | 2026-01-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 100% | -1 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-DE-CHI-1000 | Pile drawings release | Engineering | Completed | 20 | 0 | 100% | 2026-02-07 | 2026-03-02 | 2025-11-29 | 2025-12-22 | 2025-11-29 | 2025-12-22 |  | 3 | 3 | 2026-02-07 | 2026-03-02 | 2025-11-29 | 2025-12-22 | 2025-11-29 | 2025-12-22 | 100% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-DE-CHI-1010 | Civil drawings release | Engineering | Completed | 30 | 0 | 100% | 2026-01-20 | 2026-02-24 | 2025-12-23 | 2026-01-07 | 2025-12-23 | 2026-01-07 |  | 3 | 3 | 2026-01-20 | 2026-02-24 | 2025-12-23 | 2026-01-07 | 2025-12-23 | 2026-01-07 | 100% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-DE-CHI-1020 | Equipment drawings release | Engineering | Completed | 35 | 0 | 100% | 2026-08-31 | 2026-10-10 | 2026-08-31 | 2026-09-24 | 2026-08-31 | 2026-09-24 |  | 3 | 3 | 2026-08-31 | 2026-10-10 | 2026-08-31 | 2026-09-24 | 2026-08-31 | 2026-09-24 | 100% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-DE-CHI-1030 | Piping drawings release | Engineering | Not Started | 45 | 40 | 0% | 2026-10-12 | 2026-12-03 | 2026-10-03 | 2026-11-19 |  |  | 229 | 3 | 0 | 2026-10-12 | 2026-12-03 | 2026-10-03 | 2026-11-19 |  |  | 0% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-DE-CHI-1040 | E&I drawings release | Engineering | In Progress | 30 | 19 | 38% | 2026-12-04 | 2027-01-09 | 2026-10-01 | 2026-12-11 | 2026-10-01 |  | 229 | 3 | 0 | 2026-12-04 | 2027-01-09 | 2026-10-01 | 2026-12-11 | 2026-10-01 |  | 23.27% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-PR-2440 | Centrifugal Chillers - PR to PO | Procurement | Completed | 60 | 0 | 100% | 2026-02-28 | 2026-05-12 | 2026-02-03 | 2026-05-20 | 2026-02-03 | 2026-05-20 |  | 3 | 3 | 2026-02-28 | 2026-05-12 | 2026-02-03 | 2026-05-20 | 2026-02-03 | 2026-05-20 | 100% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-PR-2450 | Centrifugal Chillers - Manufacturing, Inspection & Delivery | Procurement | In Progress | 150 | 75 | 50% | 2026-06-30 | 2026-12-24 | 2026-05-22 | 2026-12-31 | 2026-05-22 |  | 188 | 4 | 0 | 2026-06-30 | 2026-12-24 | 2026-05-22 | 2026-12-31 | 2026-05-22 |  | 60.1% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-PR-2460 | Pumps - PR to PO | Procurement | Completed | 60 | 0 | 100% | 2026-02-28 | 2026-05-12 | 2026-02-03 | 2026-04-27 | 2026-02-03 | 2026-04-27 |  | 3 | 3 | 2026-02-28 | 2026-05-12 | 2026-02-03 | 2026-04-27 | 2026-02-03 | 2026-04-27 | 100% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-PR-2470 | Pumps - Manufacturing, Inspection & Delivery | Procurement | In Progress | 120 | 75 | 38% | 2026-04-30 | 2026-09-18 | 2026-04-29 | 2026-12-31 | 2026-04-29 |  | 188 | 4 | 0 | 2026-04-30 | 2026-09-18 | 2026-04-29 | 2026-12-31 | 2026-04-29 |  | 63.77% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-CON-CHI-1000 | Piling Works | Construction | Completed | 30 | 0 | 100% | 2026-01-20 | 2026-02-24 | 2025-12-17 | 2026-01-19 | 2025-12-17 | 2026-01-19 |  | 6 | 6 | 2026-01-20 | 2026-02-24 | 2025-12-17 | 2026-01-19 | 2025-12-17 | 2026-01-19 | 100% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-CON-CHI-1010 | Excavation incl. pile chipping | Construction | Completed | 60 | 0 | 100% | 2026-03-31 | 2026-06-09 | 2026-02-18 | 2026-03-30 | 2026-02-18 | 2026-03-30 |  | 3 | 3 | 2026-03-31 | 2026-06-09 | 2026-02-18 | 2026-03-30 | 2026-02-18 | 2026-03-30 | 100% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-CON-CHI-1020 | Concreting - Foundations, Columns, Beams, Walls, etc. | Construction | In Progress | 150 | 45 | 70% | 2026-04-17 | 2026-10-12 | 2026-03-08 | 2026-11-25 | 2026-03-08 |  | 143 | 49 | 36 | 2026-04-17 | 2026-10-12 | 2026-03-08 | 2026-11-25 | 2026-03-08 |  | 73.74% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-CON-CHI-1030 | Erection of Chiller Plant including Fans, Pumps, Drives, etc. | Construction | Not Started | 65 | 65 | 0% | 2027-01-15 | 2027-04-03 | 2027-01-02 | 2027-03-20 |  |  | 188 | 10 | 0 | 2027-01-15 | 2027-04-03 | 2027-01-02 | 2027-03-20 |  |  | 0% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-CON-CHI-1040 | Piping works incl. testing | Construction | Not Started | 60 | 60 | 0% | 2027-02-09 | 2027-04-21 | 2027-01-27 | 2027-04-08 |  |  | 193 | 5 | 0 | 2027-02-09 | 2027-04-21 | 2027-01-27 | 2027-04-08 |  |  | 0% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-CON-CHI-1050 | Cable tray erection incl. support, cable Laying | Construction | Not Started | 45 | 45 | 0% | 2027-02-15 | 2027-04-09 | 2027-02-02 | 2027-03-27 |  |  | 188 | 3 | 0 | 2027-02-15 | 2027-04-09 | 2027-02-02 | 2027-03-27 |  |  | 0% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-CON-CHI-1060 | Other electrical works incl. light fixtures installation | Construction | Not Started | 45 | 45 | 0% | 2027-03-04 | 2027-04-27 | 2027-02-19 | 2027-04-14 |  |  | 188 | 3 | 0 | 2027-03-04 | 2027-04-27 | 2027-02-19 | 2027-04-14 |  |  | 0% | 0 | 0 | 0 | 0 | ✔ Same as P6
JSW USL-CON-CHI-1070 | Instrument installation works | Construction | Not Started | 45 | 45 | 0% | 2027-03-24 | 2027-05-15 | 2027-03-10 | 2027-05-03 |  |  | 188 | 3 | 0 | 2027-03-24 | 2027-05-15 | 2027-03-10 | 2027-05-03 |  |  | 0% | 0 | 0 | 0 | 0 | ✔ Same as P6
Note: P6 BE-CHI-1000 is a finish milestone – P6 exports its BL start as the next day (21-Jan-26); for milestones only the BL finish is compared. Δ = working days (+ = group later than P6). After site updates a Δ means the P6 activity must be updated with the new dates.
PROGRESS SUMMARY @ DATA DATE
Data Date |  | 2026-10-02
P6 groups (Lvl 3) / detailed activities (Lvl 4) |  | 20 / 126
Detailed – Completed |  | 61
Detailed – In Progress |  | 4
Detailed – Not Started |  | 61
BIM elements in register |  | 411
Elements completed (shown as built in 4D) |  | 337
Elements in progress |  | 2
Elements not started |  | 72
Civil (JSW USL-CON-CHI-1020) – RCC scope in 4D schedule (m³) |  | 1171.5
Civil – RCC done (m³) |  | 863.82
Civil – progress by RCC quantity (4D schedule) |  | 73.74%
Civil – progress reported in P6 |  | 70%
Civil – forecast completion (4D group finish) |  | 2026-11-25
Note: RCC quantities are the "Approx. Concrete Qty" boxes of each drawing (001: 189, 002: 47.5, 003: 82, 004: 255, 005: 46, 007/008: 552 m³), split to activities by element proportion. Lintels (006: 15 m³) are reported under ADDITIONAL SCOPE – NOT IN P6.
BIM ELEMENTS BY CATEGORY & STATUS @ DATA DATE (what the 4D model shows as built)
Element group |  | Total | Completed | In Progress | Not Started | % built
Piles |  | 53 | 53 | 0 | 0 | 100%
Pile caps |  | 35 | 35 | 0 | 0 | 100%
Columns (segments) |  | 116 | 116 | 0 | 0 | 100%
Beams (PCB / PB / FB / RB / TB / STB) |  | 108 | 107 | 1 | 0 | 99.07%
Slabs, landings & grade slabs |  | 17 | 13 | 1 | 3 | 76.47%
Staircase flights |  | 4 | 4 | 0 | 0 | 100%
Equipment foundations F1 / F2 |  | 15 | 0 | 0 | 15 | 0%
Trenches, pits, drains, covers |  | 11 | 3 | 0 | 8 | 27.27%
Mechanical equipment, hoists & instruments |  | 19 | 0 | 0 | 19 | 0%
Steel monorails |  | 2 | 0 | 0 | 2 | 0%
Formulas:
Group BL Start = INDEX('4D Schedule'!$Y6:Y156,MATCH([P6 ACTIVITY],'4D Schedule'!$A6:A156,0))
Group BL Finish = INDEX('4D Schedule'!$Z6:Z156,MATCH([P6 ACTIVITY],'4D Schedule'!$A6:A156,0))
Group Start = INDEX('4D Schedule'!$AE6:AE156,MATCH([P6 ACTIVITY],'4D Schedule'!$A6:A156,0))
Group Finish = INDEX('4D Schedule'!$AF6:AF156,MATCH([P6 ACTIVITY],'4D Schedule'!$A6:A156,0))
Group Actual Start = INDEX('4D Schedule'!$AA6:AA156,MATCH([P6 ACTIVITY],'4D Schedule'!$A6:A156,0))
Group Actual Finish = INDEX('4D Schedule'!$AB6:AB156,MATCH([P6 ACTIVITY],'4D Schedule'!$A6:A156,0))

## Calendar
PROJECT CALENDAR – JSW USL Calender (from P6 XER)
Work week Mon–Sat (Sunday off), 10 h/day (08:00–13:00, 14:00–19:00). Holidays as defined in the XER calendar.
Column A (named range WorkDays) drives every date formula. To add a holiday: delete that date from column A (keep the list sorted).
Working days (WorkDays) | Holiday | Day
2025-09-01 | 2025-10-02 | Thu
2025-09-02 | 2025-10-20 | Mon
2025-09-03 | 2025-12-25 | Thu
2025-09-04 | 2026-01-01 | Thu
2025-09-05 | 2026-01-26 | Mon
2025-09-06 | 2026-03-04 | Wed
2025-09-08 | 2026-03-21 | Sat
2025-09-09 | 2026-05-01 | Fri
2025-09-10 | 2026-08-15 | Sat
2025-09-11 | 2026-10-02 | Fri
2025-09-12 | 2026-10-20 | Tue
2025-09-13 | 2026-12-25 | Fri
2025-09-15 | 2027-01-01 | Fri
2025-09-16 | 2027-01-26 | Tue
2025-09-17 | 2027-03-09 | Tue
2025-09-18 | 2027-03-22 | Mon
2025-09-19 | 2027-05-01 | Sat
2025-09-20 | 2027-10-02 | Sat
2025-09-22 | 2027-10-09 | Sat
2025-09-23 | 2027-10-29 | Fri
2025-09-24 | 2027-12-25 | Sat
2025-09-25 | 2028-01-01 | Sat
2025-09-26 | 2028-01-26 | Wed
2025-09-27 | 2028-02-26 | Sat
2025-09-29 | 2028-03-11 | Sat
2025-09-30 | 2028-05-01 | Mon
2025-10-01 | 2028-08-15 | Tue
2025-10-03 | 2028-09-27 | Wed
2025-10-04 | 2028-10-02 | Mon
2025-10-06 | 2028-10-17 | Tue
2025-10-07 | 2028-12-25 | Mon
2025-10-08
2025-10-09
2025-10-10
2025-10-11
2025-10-13
2025-10-14
2025-10-15
2025-10-16
2025-10-17
2025-10-18
2025-10-21
2025-10-22
2025-10-23
2025-10-24
2025-10-25
2025-10-27
2025-10-28
2025-10-29
2025-10-30
2025-10-31
2025-11-01
2025-11-03
2025-11-04
2025-11-05
2025-11-06
2025-11-07
2025-11-08
2025-11-10
2025-11-11
2025-11-12
2025-11-13
2025-11-14
2025-11-15
2025-11-17
2025-11-18
2025-11-19
2025-11-20
2025-11-21
2025-11-22
2025-11-24
2025-11-25
2025-11-26
2025-11-27
2025-11-28
2025-11-29
2025-12-01
2025-12-02
2025-12-03
2025-12-04
2025-12-05
2025-12-06
2025-12-08
2025-12-09
2025-12-10
2025-12-11
2025-12-12
2025-12-13
2025-12-15
2025-12-16
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-22
2025-12-23
2025-12-24
2025-12-26
2025-12-27
2025-12-29
2025-12-30
2025-12-31
2026-01-02
2026-01-03
2026-01-05
2026-01-06
2026-01-07
2026-01-08
2026-01-09
2026-01-10
2026-01-12
2026-01-13
2026-01-14
2026-01-15
2026-01-16
2026-01-17
2026-01-19
2026-01-20
2026-01-21
2026-01-22
2026-01-23
2026-01-24
2026-01-27
2026-01-28
2026-01-29
2026-01-30
2026-01-31
2026-02-02
2026-02-03
2026-02-04
2026-02-05
2026-02-06
2026-02-07
2026-02-09
2026-02-10
2026-02-11
2026-02-12
2026-02-13
2026-02-14
2026-02-16
2026-02-17
2026-02-18
2026-02-19
2026-02-20
2026-02-21
2026-02-23
2026-02-24
2026-02-25
2026-02-26
2026-02-27
2026-02-28
2026-03-02
2026-03-03
2026-03-05
2026-03-06
2026-03-07
2026-03-09
2026-03-10
2026-03-11
2026-03-12
2026-03-13
2026-03-14
2026-03-16
2026-03-17
2026-03-18
2026-03-19
2026-03-20
2026-03-23
2026-03-24
2026-03-25
2026-03-26
2026-03-27
2026-03-28
2026-03-30
2026-03-31
2026-04-01
2026-04-02
2026-04-03
2026-04-04
2026-04-06
2026-04-07
2026-04-08
2026-04-09
2026-04-10
2026-04-11
2026-04-13
2026-04-14
2026-04-15
2026-04-16
2026-04-17
2026-04-18
2026-04-20
2026-04-21
2026-04-22
2026-04-23
2026-04-24
2026-04-25
2026-04-27
2026-04-28
2026-04-29
2026-04-30
2026-05-02
2026-05-04
2026-05-05
2026-05-06
2026-05-07
2026-05-08
2026-05-09
2026-05-11
2026-05-12
2026-05-13
2026-05-14
2026-05-15
2026-05-16
2026-05-18
2026-05-19
2026-05-20
2026-05-21
2026-05-22
2026-05-23
2026-05-25
2026-05-26
2026-05-27
2026-05-28
2026-05-29
2026-05-30
2026-06-01
2026-06-02
2026-06-03
2026-06-04
2026-06-05
2026-06-06
2026-06-08
2026-06-09
2026-06-10
2026-06-11
2026-06-12
2026-06-13
2026-06-15
2026-06-16
2026-06-17
2026-06-18
2026-06-19
2026-06-20
2026-06-22
2026-06-23
2026-06-24
2026-06-25
2026-06-26
2026-06-27
2026-06-29
2026-06-30
2026-07-01
2026-07-02
2026-07-03
2026-07-04
2026-07-06
2026-07-07
2026-07-08
2026-07-09
2026-07-10
2026-07-11
2026-07-13
2026-07-14
2026-07-15
2026-07-16
2026-07-17
2026-07-18
2026-07-20
2026-07-21
2026-07-22
2026-07-23
2026-07-24
2026-07-25
2026-07-27
2026-07-28
2026-07-29
2026-07-30
2026-07-31
2026-08-01
2026-08-03
2026-08-04
2026-08-05
2026-08-06
2026-08-07
2026-08-08
2026-08-10
2026-08-11
2026-08-12
2026-08-13
2026-08-14
2026-08-17
2026-08-18
2026-08-19
2026-08-20
2026-08-21
2026-08-22
2026-08-24
2026-08-25
2026-08-26
2026-08-27
2026-08-28
2026-08-29
2026-08-31
2026-09-01
2026-09-02
2026-09-03
2026-09-04
2026-09-05
2026-09-07
2026-09-08
2026-09-09
2026-09-10
2026-09-11
2026-09-12
2026-09-14
2026-09-15
2026-09-16
2026-09-17
2026-09-18
2026-09-19
2026-09-21
2026-09-22
2026-09-23
2026-09-24
2026-09-25
2026-09-26
2026-09-28
2026-09-29
2026-09-30
2026-10-01
2026-10-03
2026-10-05
2026-10-06
2026-10-07
2026-10-08
2026-10-09
2026-10-10
2026-10-12
2026-10-13
2026-10-14
2026-10-15
2026-10-16
2026-10-17
2026-10-19
2026-10-21
2026-10-22
2026-10-23
2026-10-24
2026-10-26
2026-10-27
2026-10-28
2026-10-29
2026-10-30
2026-10-31
2026-11-02
2026-11-03
2026-11-04
2026-11-05
2026-11-06
2026-11-07
2026-11-09
2026-11-10
2026-11-11
2026-11-12
2026-11-13
2026-11-14
2026-11-16
2026-11-17
2026-11-18
2026-11-19
2026-11-20
2026-11-21
2026-11-23
2026-11-24
2026-11-25
2026-11-26
2026-11-27
2026-11-28
2026-11-30
2026-12-01
2026-12-02
2026-12-03
2026-12-04
2026-12-05
2026-12-07
2026-12-08
2026-12-09
2026-12-10
2026-12-11
2026-12-12
2026-12-14
2026-12-15
2026-12-16
2026-12-17
2026-12-18
2026-12-19
2026-12-21
2026-12-22
2026-12-23
2026-12-24
2026-12-26
2026-12-28
2026-12-29
2026-12-30
2026-12-31
2027-01-02
2027-01-04
2027-01-05
2027-01-06
2027-01-07
2027-01-08
2027-01-09
2027-01-11
2027-01-12
2027-01-13
2027-01-14
2027-01-15
2027-01-16
2027-01-18
2027-01-19
2027-01-20
2027-01-21
2027-01-22
2027-01-23
2027-01-25
2027-01-27
2027-01-28
2027-01-29
2027-01-30
2027-02-01
2027-02-02
2027-02-03
2027-02-04
2027-02-05
2027-02-06
2027-02-08
2027-02-09
2027-02-10
2027-02-11
2027-02-12
2027-02-13
2027-02-15
2027-02-16
2027-02-17
2027-02-18
2027-02-19
2027-02-20
2027-02-22
2027-02-23
2027-02-24
2027-02-25
2027-02-26
2027-02-27
2027-03-01
2027-03-02
2027-03-03
2027-03-04
2027-03-05
2027-03-06
2027-03-08
2027-03-10
2027-03-11
2027-03-12
2027-03-13
2027-03-15
2027-03-16
2027-03-17
2027-03-18
2027-03-19
2027-03-20
2027-03-23
2027-03-24
2027-03-25
2027-03-26
2027-03-27
2027-03-29
2027-03-30
2027-03-31
2027-04-01
2027-04-02
2027-04-03
2027-04-05
2027-04-06
2027-04-07
2027-04-08
2027-04-09
2027-04-10
2027-04-12
2027-04-13
2027-04-14
2027-04-15
2027-04-16
2027-04-17
2027-04-19
2027-04-20
2027-04-21
2027-04-22
2027-04-23
2027-04-24
2027-04-26
2027-04-27
2027-04-28
2027-04-29
2027-04-30
2027-05-03
2027-05-04
2027-05-05
2027-05-06
2027-05-07
2027-05-08
2027-05-10
2027-05-11
2027-05-12
2027-05-13
2027-05-14
2027-05-15
2027-05-17
2027-05-18
2027-05-19
2027-05-20
2027-05-21
2027-05-22
2027-05-24
2027-05-25
2027-05-26
2027-05-27
2027-05-28
2027-05-29
2027-05-31
2027-06-01
2027-06-02
2027-06-03
2027-06-04
2027-06-05
2027-06-07
2027-06-08
2027-06-09
2027-06-10
2027-06-11
2027-06-12
2027-06-14
2027-06-15
2027-06-16
2027-06-17
2027-06-18
2027-06-19
2027-06-21
2027-06-22
2027-06-23
2027-06-24
2027-06-25
2027-06-26
2027-06-28
2027-06-29
2027-06-30
2027-07-01
2027-07-02
2027-07-03
2027-07-05
2027-07-06
2027-07-07
2027-07-08
2027-07-09
2027-07-10
2027-07-12
2027-07-13
2027-07-14
2027-07-15
2027-07-16
2027-07-17
2027-07-19
2027-07-20
2027-07-21
2027-07-22
2027-07-23
2027-07-24
2027-07-26
2027-07-27
2027-07-28
2027-07-29
2027-07-30
2027-07-31
2027-08-02
2027-08-03
2027-08-04
2027-08-05
2027-08-06
2027-08-07
2027-08-09
2027-08-10
2027-08-11
2027-08-12
2027-08-13
2027-08-14
2027-08-16
2027-08-17
2027-08-18
2027-08-19
2027-08-20
2027-08-21
2027-08-23
2027-08-24
2027-08-25
2027-08-26
2027-08-27
2027-08-28
2027-08-30
2027-08-31
2027-09-01
2027-09-02
2027-09-03
2027-09-04
2027-09-06
2027-09-07
2027-09-08
2027-09-09
2027-09-10
2027-09-11
2027-09-13
2027-09-14
2027-09-15
2027-09-16
2027-09-17
2027-09-18
2027-09-20
2027-09-21
2027-09-22
2027-09-23
2027-09-24
2027-09-25
2027-09-27
2027-09-28
2027-09-29
2027-09-30
2027-10-01
2027-10-04
2027-10-05
2027-10-06
2027-10-07
2027-10-08
2027-10-11
2027-10-12
2027-10-13
2027-10-14
2027-10-15
2027-10-16
2027-10-18
2027-10-19
2027-10-20
2027-10-21
2027-10-22
2027-10-23
2027-10-25
2027-10-26
2027-10-27
2027-10-28
2027-10-30
2027-11-01
2027-11-02
2027-11-03
2027-11-04
2027-11-05
2027-11-06
2027-11-08
2027-11-09
2027-11-10
2027-11-11
2027-11-12
2027-11-13
2027-11-15
2027-11-16
2027-11-17
2027-11-18
2027-11-19
2027-11-20
2027-11-22
2027-11-23
2027-11-24
2027-11-25
2027-11-26
2027-11-27
2027-11-29
2027-11-30
2027-12-01
2027-12-02
2027-12-03
2027-12-04
2027-12-06
2027-12-07
2027-12-08
2027-12-09
2027-12-10
2027-12-11
2027-12-13
2027-12-14
2027-12-15
2027-12-16
2027-12-17
2027-12-18
2027-12-20
2027-12-21
2027-12-22
2027-12-23
2027-12-24
2027-12-27
2027-12-28
2027-12-29
2027-12-30
2027-12-31