## READ ME
JSW UTKAL STEEL — DAILY PROGRESS REPORT (consolidation workbook)
HOW THE PIECES FIT TOGETHER
1. dpr_consolidator.html — open it in Chrome/Edge. Drop in every vendor DPR you receive
(any layout, .xlsx / .xls / .csv). It auto-detects the header row, maps the vendor's
column names to this format, matches each line to your master scope, and exports the
finished DPR in exactly the format of this workbook.
2. This workbook — the approved format. Use it as (a) the master-scope source you load into
the HTML tool, and (b) the manual fallback if you would rather type the numbers in.
SHEETS
Config Project title, data date, reporting date, and the master drop-down lists.
Summary-AreaWise The printed summary. Every number is a SUMIFS() pulled from the backup
sheets. Fill only the green columns (Activity, Agency) plus the two grey
helper columns P (Area) and Q (Source sheet) - they tell the formula where
to look. Columns P and Q are outside the print area.
Piling … Panels Backup sheets, one per discipline, identical column layout.
Manpower Area / agency / category-wise deployment.
Vendor-Import Staging area - paste the consolidator's normalised output here.
Mapping Header synonyms + name aliases. Teach it once, it remembers forever.
COLOUR CODE
Yellow = you type here. Green = key / matching column (must match the master exactly).
Blue = calculated, do not overwrite.
THE ARITHMETIC (unchanged from your existing DPR)
Variance for the Day n = Plan FTD - Achieved FTD
Achieved FTM till date p = Achieved FTD + Achieved FTM till previous date
Workdone Till Date q = Achieved till last month + Achieved FTM till date
% Complete r = Workdone Till Date / Scope
Balance s = Scope - Workdone Till Date
WHAT CHANGED vs. YOUR CURRENT FILE
Formulas are pre-filled 400 rows deep on each backup sheet and 150 rows deep on the summary.
Need more? Select the last filled row and drag it down - nothing else has to change.
Two real columns - Area and Activity - were added to each backup sheet. In the current file
the area is only a bold heading row, so the Summary SUMIFS() has to hard-code row numbers
(Structural!H89:H106). Insert one row anywhere and the summary silently breaks. With Area and
Activity as columns the formulas address whole columns and never need maintenance.

## Summary-AreaWise
JSW
Data date:
Reporting date:
SI No. | Area / Activities | Agency / Contractor | Scope | Drawing Released | Front Available | Workdone Till Date | % Complete | Balance |  |  | Achieved FTD | Available Manpower | Area (helper) | Source sheet (helper)
a | b | c | d | e | f | g | h = (g/d)x100 | i = d-g | j | k | l | m

## Piling
JSW
Piling Works — Backup Sheet (UOM: Nos)
Data date:
Reporting date:
SL. | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Variance for the Day | Reason(s) for Variance | Achieved FTM till date | Workdone Till Date | % Complete | Balance | Remarks | Available Manpower
a | b | c | d | e | f | g | h | i | j | k | l | m | n = k-l | o | p = l+m | q = i+p | r = (q/f)x100 | s = f-q | t | u

## Civil
JSW
Civil Works — Backup Sheet (UOM: Cum)
Data date:
Reporting date:
SL. | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Variance for the Day | Reason(s) for Variance | Achieved FTM till date | Workdone Till Date | % Complete | Balance | Remarks | Available Manpower
a | b | c | d | e | f | g | h | i | j | k | l | m | n = k-l | o | p = l+m | q = i+p | r = (q/f)x100 | s = f-q | t | u

## Structural
JSW
Structural Supply — Backup Sheet (UOM: MT)
Data date:
Reporting date:
SL. | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Variance for the Day | Reason(s) for Variance | Achieved FTM till date | Workdone Till Date | % Complete | Balance | Remarks | Available Manpower
a | b | c | d | e | f | g | h | i | j | k | l | m | n = k-l | o | p = l+m | q = i+p | r = (q/f)x100 | s = f-q | t | u

## Equipment
JSW
Equipment Erection — Backup Sheet (UOM: MT)
Data date:
Reporting date:
SL. | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Variance for the Day | Reason(s) for Variance | Achieved FTM till date | Workdone Till Date | % Complete | Balance | Remarks | Available Manpower
a | b | c | d | e | f | g | h | i | j | k | l | m | n = k-l | o | p = l+m | q = i+p | r = (q/f)x100 | s = f-q | t | u

## Piping
JSW
Piping — Backup Sheet (UOM: Inch-Mtr)
Data date:
Reporting date:
SL. | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Variance for the Day | Reason(s) for Variance | Achieved FTM till date | Workdone Till Date | % Complete | Balance | Remarks | Available Manpower
a | b | c | d | e | f | g | h | i | j | k | l | m | n = k-l | o | p = l+m | q = i+p | r = (q/f)x100 | s = f-q | t | u

## Cable Trays (Km)
JSW
Cable Trays — Backup Sheet (UOM: Km)
Data date:
Reporting date:
SL. | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Variance for the Day | Reason(s) for Variance | Achieved FTM till date | Workdone Till Date | % Complete | Balance | Remarks | Available Manpower
a | b | c | d | e | f | g | h | i | j | k | l | m | n = k-l | o | p = l+m | q = i+p | r = (q/f)x100 | s = f-q | t | u

## Cabling (Km)
JSW
Cabling — Backup Sheet (UOM: Km)
Data date:
Reporting date:
SL. | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Variance for the Day | Reason(s) for Variance | Achieved FTM till date | Workdone Till Date | % Complete | Balance | Remarks | Available Manpower
a | b | c | d | e | f | g | h | i | j | k | l | m | n = k-l | o | p = l+m | q = i+p | r = (q/f)x100 | s = f-q | t | u

## Panels (Nos)
JSW
Panels — Backup Sheet (UOM: Nos)
Data date:
Reporting date:
SL. | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Variance for the Day | Reason(s) for Variance | Achieved FTM till date | Workdone Till Date | % Complete | Balance | Remarks | Available Manpower
a | b | c | d | e | f | g | h | i | j | k | l | m | n = k-l | o | p = l+m | q = i+p | r = (q/f)x100 | s = f-q | t | u

## Manpower
JSW
Manpower Deployment — Backup Sheet
Data date:
Reporting date:
SL. | Area | Agency / Contractor | Category | Planned (Nos) | Actual / Available (Nos) | Variance | Remarks
a | b | c | d | e | f | g = f-e | h

## Vendor-Import
VENDOR IMPORT — staging area
Paste the normalised rows exported by dpr_consolidator.html here (or paste vendor data and fix the 4 green key columns by hand). Then copy the block into the matching discipline sheet.
Discipline (sheet) | Name of the Structures | Area | Activity | Agency / Contractor | Scope | Drawing Released | Cum Front Available | Achieved till last month | Plan FTM | Plan FTD | Achieved FTD | Achieved FTM till previous date | Reason(s) for Variance | Remarks | Available Manpower

## Mapping
COLUMN SYNONYM DICTIONARY (auto-mapping of vendor headers)
Add any new header wording your vendors use, separated by ' ¦ '. The HTML consolidator reads the very same list, so keep the two in step.
Canonical field | Standard header | Accepted vendor headings (¦ separated)
structure | Name of the Structures | name of structure ¦ structure ¦ description ¦ activity description ¦ item ¦ work description ¦ particulars ¦ building ¦ location ¦ element
area | Area | area ¦ zone ¦ unit ¦ block ¦ package ¦ plant area ¦ section
activity | Activity | activity ¦ discipline ¦ work type ¦ sub head ¦ category of work
agency | Agency / Contractor | agency ¦ contractor ¦ vendor ¦ sub contractor ¦ agency/contractor ¦ executing agency ¦ party
scope | Scope | scope ¦ total scope ¦ total qty ¦ boq qty ¦ contract qty ¦ ordered qty ¦ total quantity
drawing | Drawing Released | drawing released ¦ drg released ¦ drawings issued ¦ gfc released ¦ ifc released
front | Cum Front Available | front available ¦ cum front available ¦ front ¦ fronts released ¦ work front
last_month | Achieved till last month | achieved till last month ¦ cum till last month ¦ upto last month ¦ progress till last month ¦ opening balance
plan_ftm | Plan FTM | plan ftm ¦ plan for the month ¦ monthly plan ¦ mtd plan ¦ target for month ¦ plan month
plan_ftd | Plan FTD | plan ftd ¦ plan for the day ¦ daily plan ¦ today plan ¦ dpr plan ¦ plan today
ach_ftd | Achieved FTD | achieved ftd ¦ actual ftd ¦ today achievement ¦ progress today ¦ daily progress ¦ done today ¦ qty today ¦ achievement for the day
ach_ftm_prev | Achieved FTM till previous date | achieved ftm till previous date ¦ mtd till previous day ¦ month till yesterday ¦ cum month previous
reason | Reason(s) for Variance | reason ¦ reason for variance ¦ remarks for variance ¦ constraint ¦ hold reason ¦ delay reason
remarks | Remarks | remarks ¦ comment ¦ notes ¦ observation
manpower | Available Manpower | manpower ¦ available manpower ¦ labour ¦ workmen ¦ man power ¦ manpower deployed ¦ strength
NAME ALIASES (vendor wording -> master wording)
Type (area/activity/agency/structure) | As written by the vendor | Master value to use
agency | ITD Cementation Ltd. | ITD Cementation
agency | M/s Meher Foundations Pvt Ltd | Meher Foundation
area | FILTRATION | Filtration Unit
area | WTP | Water Treatment Plant

## Config
DPR CONFIGURATION
Project title | Phase-1 Greenfield Expansion Projects, JSW Utkal Steel Limited
Report name | Daily Progress Report
Data date
Reporting date
Reporting month label
Prepared by
Reviewed by
MASTER LISTS (used by the drop-downs on every sheet)
Areas | Activities | Agencies / Contractors
Filtration Unit | Piling Works (Nos) | ITD Cementation
Water Treatment Plant | Civil Works (Cum) | Meher Foundation
Material Handling Facilities | Structural Supply (MT) | Vensar Constructions
Stacker & Reclaimer | Structural Erection (MT) | Sreehita Constructions
Substation | Equipment Supply (MT) | Surya Enterprises
Tanks & Launders (IDT) | Equipment Erection (MT) | Goel Constructions
Dump Pond & Terminal | Piping (Inch-Mtr) | SPD
Roads & Drains | Cable Trays (Km) | Vaishnavi
Plant General | Cabling (Km) | Shobha
| Panels (Nos) | Ganesh
NKS
Sri Balaji Constructions
ARDEE
VSI
Jagdamba
Rohan