## Supply
ARDEE Engineering Pvt Ltd ¦ Structural Supply ¦ JSW Utkal Phase-1
Reporting date: 11-Sep-26
Sl | Item | Zone | Qty | Drawings | Front | Cumulative | Plan | Plan | Actual | Actual | Remarks
| Description |  | Total MT | Released | Available | till last month | Month | Day | Day | Month till prev
1 | BS - Filtration Main Building | Filtration Unit | 2675 | 2443 | 1264 | 700 | 500 | 22 | 26 | 61
2 | TS - Filtration Main Building | Filtration Unit | 636 | 636 | 636 | 400 | 328 | 14 | 15 | 25
3 | BS - Junction House JH02 | Material Handling Facilities | 3622 | 3587 | 2686 | 2100 | 697 | 30 | 34 | 98
4 | BS - Conveyor Gallery J2C1 | Material Handling Facilities | 4611 | 3561 | 1863 | 900 | 588 | 26 | 28 | 72
5 | TS - Pipe Rack WTP | Water Treatment Plant | 3096 | 3096 | 2872 | 780 | 440 | 20 | 18 | 52

## Erection
ARDEE Engineering Pvt Ltd ¦ Structural Erection ¦ JSW Utkal Phase-1
Reporting date: 11-Sep-26
Sl | Item | Zone | Qty | Drawings | Front | Cumulative | Plan | Plan | Actual | Actual | Remarks
| Description |  | Total MT | Released | Available | till last month | Month | Day | Day | Month till prev
1 | BS - Filtration Main Building | Filtration Unit | 1471 | 1344 | 695 | 385 | 275 | 12 | 14 | 34
2 | TS - Filtration Main Building | Filtration Unit | 350 | 350 | 350 | 220 | 180 | 8 | 8 | 14
3 | BS - Junction House JH02 | Material Handling Facilities | 1992 | 1973 | 1477 | 1155 | 383 | 16 | 19 | 54
4 | BS - Conveyor Gallery J2C1 | Material Handling Facilities | 2536 | 1959 | 1025 | 495 | 323 | 14 | 15 | 40
5 | TS - Pipe Rack WTP | Water Treatment Plant | 1703 | 1703 | 1580 | 429 | 242 | 11 | 10 | 29