## Piling Progress
ITD CEMENTATION (INDIA) LIMITED
Daily Progress - Piling Works - JSW Utkal
Date : 11-Sep-2026
Sr No | Description of Work | Contract Qty (Nos) | GFC Released | Work Front | Cum. upto last month | Monthly Target | Today Plan | Progress Today | MTD till previous day | Remark
Filtration Unit
1 | Electrical Substation Filtration | 406 | 406 | 406 | 400 | 10 | 2 | 3 | 4
2 | Electrical Substation RMHS | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | Completed
3 | IO Terminal (terminal agitator tank) | 1576 | 1576 | 1576 | 1570 | 12 | 1 | 2 | 3
Material handling facilities
4 | Conveyor gallery J1C1 to J1C2 | 188 | 188 | 188 | 180 | 10 | 2 | 3 | 5
5 | JH02 | 151 | 151 | 151 | 140 | 14 | 2 | 4 | 6 | rebar delay
6 | JH7C1C2 | 214 | 214 | 214 | 189 | 30 | 3 | 6 | 9
Water Treatment Plant
7 | Cooling Tower | 99 | 99 | 99 | 95 | 6 | 1 | 2 | 2
8 | Cable Gallery IO RMHS Area Route 1,2,3 | 40 | 40 | 40 | 38 | 3 | 1 | 1 | 1
| Total | 2680 | 2680 | 2680 | 2618 | 85 | 12 | 21 | 30