## Items
Quantity tracker - items
Unit MT · data as on 30-Sep-2026 · Fill orange cells. % columns are formulas. Import back with Qty & Liquidation → Import Excel.
ID | Item / building | Building | WBS | EPC | Vendor | Unit | Scope | Scope note | Drawings released | Supplied till date | Erected till date | Supply last month | Erection last month | Target supply finish (mmm-yy) | Target erection finish (mmm-yy) | Status (auto / ON TRACK / AT RISK / DELAYED) | Drawings % | Supplied % | Erected % | Balance to erect
qmul33cej9ge | Additive Grinding Building | Additive Grinding Building | Pellet Plant-1 | Construction | KBL | MT | 2000 | + TS 160.9 MT (silos 132.3 + liner 28.6) | 1399 | 12 | 0 | 12 | 0 |  |  | auto
qmul33cej47p | Screen House | Screen House | Pellet Plant-2 | Construction | Samal Brothers | MT | 1019 | + TS: equipment, crane & conveyor supports | 1019 | 0 | 0 | 0 | 0 |  |  | auto
qmul33cej833 | Return Fines Building | Return Fines Building | Filtration Plant | Construction | Vrinda Bhillai (site fabrication) | MT | 393 | + TS 66.3 MT (bins, liner, weighing bins) | 393 | 0 | 0 | 0 | 0 |  |  | auto

## Plan
Monthly liquidation plan (MT)
One row per item and stage. Months start after the data-as-on month. Check turns red when the plan total does not equal the balance (scope − done).
ID | Item | Stage | Balance | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Plan total | Check
qmul33cej9ge | Additive Grinding Building | Supply |  | 250 | 300 | 500 | 520 | 430
qmul33cej9ge | Additive Grinding Building | Erection |  |  | 150 | 250 | 250 | 250 | 250 | 250 | 300 | 300
qmul33cej47p | Screen House | Supply |  | 250 | 250 | 250 | 269
qmul33cej47p | Screen House | Erection |  | 50 | 180 | 200 | 166 | 168 | 160 | 95
qmul33cej833 | Return Fines Building | Supply |  | 120 | 120 | 120 | 33
qmul33cej833 | Return Fines Building | Erection |  |  | 50 | 50 | 110 | 120 | 63

## Fronts
Work fronts (rows of the work-front table)
Category: front, supply, erection, ts, handover. Months as mmm-yy (e.g. Oct-26).
ID | Front | Category | From | To
qmul33cej9ge | Drawing / PO closure | front | Oct-26 | Nov-26
qmul33cej9ge | Fabrication & supply | supply | Oct-26 | Feb-27
qmul33cej9ge | Ground assembly | erection | Oct-26 | Jan-27
qmul33cej9ge | Main frame erection | erection | Nov-26 | Jun-27
qmul33cej9ge | Silos / liners (TS) | ts | Apr-27 | Jun-27
qmul33cej9ge | Alignment / handover | handover | May-27 | Jun-27
qmul33cej47p | Foundation release | front | Oct-26 | Oct-26
qmul33cej47p | Material receipt | supply | Oct-26 | Jan-27
qmul33cej47p | Starter bay / bracing | erection | Oct-26 | Nov-26
qmul33cej47p | Lower tiers | erection | Nov-26 | Jan-27
qmul33cej47p | Screen / crane levels | erection | Dec-26 | Mar-27
qmul33cej47p | Upper tiers / roof | erection | Feb-27 | Apr-27
qmul33cej47p | Handover | handover | Apr-27 | Apr-27
qmul33cej833 | Foundation release | front | Oct-26 | Nov-26
qmul33cej833 | Fabrication & supply | supply | Oct-26 | Jan-27
qmul33cej833 | Starter frame | erection | Nov-26 | Dec-26
qmul33cej833 | Bin support floors | erection | Dec-26 | Feb-27
qmul33cej833 | Bins / liner (TS) | ts | Dec-26 | Feb-27
qmul33cej833 | Handover | handover | Mar-27 | Mar-27

## Concerns
Your own concerns & actions (the engine adds its automatic ones)
Tag e.g. SUPPLY / DRAWINGS / ERECTION / FRONT / INTERFACE. Severity high or med.
ID | Tag | Severity | Concern | Action
qmul33cej47p | FRONT | high | Erection starts first and needs surveyed starter-bay foundations now. | Release surveyed starter-bay foundations / anchor bolts.
qmul33cej833 | INTERFACE | med | Bin-support and conveyor interface not yet frozen. | Freeze bin-support and conveyor interface.

## Engine summary
Engine summary by building
Calculated by Schedule Engine - not an input sheet.
Group | Status | Scope | Drawings | Supplied | Erected | Tag | Concern / action
Additive Grinding Building | AT RISK | 2000 | 1399 | 12 | 0 | DRAWINGS | Only 1,399 of 2,000 MT drawings released; 601 MT (30%) pending. Cumulative supply crosses 1,399 MT in Jan-27. → Close balance drawings / PO by Nov-26 to feed Jan-27 fabrication.
[6 empty] | SUPPLY | Oct-26–Feb supply plan totals 2,000 MT but the balance is 1,988 MT (12 MT already done) - quantities not reconciled against scope. → Reconcile the supply plan against scope and the Sep-26 actual.
[6 empty] | SUPPLY | Dispatch must jump from 12 MT in Sep-26 to 520 MT/month; Dec and Jan-27 alone need 1,020 MT. → Lock fabrication lot plan; weekly dispatch vs 250/300/500/520/430 MT.
[6 empty] | ERECTION | Erection starts Nov-26 and must hold 150–300 MT/month for 8 months. → Mobilise crane and erection crew before Nov-26.
Screen House | AT RISK | 1019 | 1019 | 0 | 0 | SUPPLY | Dispatch must jump from 0 MT in Sep-26 to 269 MT/month; Oct and Jan-27 alone need 519 MT. → Lock fabrication lot plan; weekly dispatch vs 250/250/250/269 MT.
[6 empty] | FRONT | Erection starts first and needs surveyed starter-bay foundations now. → Release surveyed starter-bay foundations / anchor bolts.
[6 empty] | ERECTION | Erection starts Oct-26 and must hold 50–200 MT/month for 7 months. → Mobilise crane and erection crew before Oct-26.
Return Fines Building | AT RISK | 393 | 393 | 0 | 0 | SUPPLY | Dispatch must jump from 0 MT in Sep-26 to 120 MT/month; Oct and Nov alone need 240 MT. → Lock fabrication lot plan; weekly dispatch vs 120/120/120/33 MT.
[6 empty] | ERECTION | Erection starts Nov-26 and must hold 50–120 MT/month for 5 months. → Mobilise crane and erection crew before Nov-26.
[6 empty] | INTERFACE | Bin-support and conveyor interface not yet frozen. → Freeze bin-support and conveyor interface.