## Slide 1
Additive Grinding Building
Supply vendor: KBL | 2,000 MT + TS 160.9 MT (silos 132.3 + liner 28.6) | Supply Oct-26 → Feb-27 | Erection Nov-26 → Jun-27
Data as on: 30-Sep-26
AT RISK
SCOPE
2,000 MT
+ TS 160.9 MT (silos 132.3 + liner 28.6)
DRAWINGS RELEASED
1,399 MT
70% of scope · 601 MT pending
SUPPLIED TILL SEP
12 MT
Sep actual 12 MT; plan exceeds balance by 12
OCT–DEC SUPPLY PLAN
1,050 MT
53% of scope · 250 / 300 / 500 MT
OCT–DEC ERECTION PLAN
400 MT
20% of scope · 0 erected, starts Nov-26
PEAK MONTHLY RATE (MT)
520 | 300
supply (Jan-27) | erection (May–Jun)
WORK-FRONT SEQUENCE & MONTHLY PLAN (MT)
Front / drawings
Supply
Erection
TS / bins
Handover
Work front
Oct-26
Nov
Dec
Jan-27
Feb
Mar
Apr
May
Jun
Total
Drawing / PO closure
Fabrication & supply
Ground assembly
Main frame erection
Silos / liners (TS)
Alignment / handover
Supply (MT)
250
300
500
520
430
–
–
–
–
2,000
Erection (MT)
–
150
250
250
250
250
250
300
300
2,000
Cum. erection (% of scope)
–
8%
20%
33%
45%
57%
70%
85%
100%
Oct-26
BS Supply start
Nov-26
BS Erection start
Feb-27
Supply complete
Apr → Jun
Silos / liners (TS)
Jun-27
Erection finish
Supply view: Material waiting at site builds to ≈1,112 MT by Feb-27 (supply ends 5 months before erection) - plan laydown and erection sequence.
KEY CONCERNS & ACTIONS
DRAWINGS
Only 1,399 of 2,000 MT drawings released; 601 MT (30%) pending. Cumulative supply crosses 1,399 MT in Jan-27.
Action: Close balance drawings / PO by Nov-26 to feed Jan-27 fabrication.
SUPPLY
Oct-26–Feb supply plan totals 2,000 MT but the balance is 1,988 MT (12 MT already done) - quantities not reconciled against scope.
Action: Reconcile the supply plan against scope and the Sep-26 actual.
SUPPLY
Dispatch must jump from 12 MT in Sep-26 to 520 MT/month; Dec and Jan-27 alone need 1,020 MT.
Action: Lock fabrication lot plan; weekly dispatch vs 250/300/500/520/430 MT.
ERECTION
Erection starts Nov-26 and must hold 150–300 MT/month for 8 months.
Action: Mobilise crane and erection crew before Nov-26.
SCOPE vs DRAWINGS vs SUPPLY vs ERECTION (MT)
Scope
2,000 MT
Drawings released
1,399 MT · 70%
Supplied till Sep
12 MT · 0.6%
Erected till date
0 MT · starts Nov-26
601 MT drawings pending; 0.6% supplied; erection starts Nov-26.
BS = building structure · TS = technological structure
1
Notes: TALKING POINTS - ADDITIVE GRINDING BUILDING 1. 2,000 MT scope, vendor KBL. 2. 1,399 MT drawings released (70% of scope · 601 MT pending). 3. Next three months: supply 1,050 MT, erection 400 MT. 4. DRAWINGS: Only 1,399 of 2,000 MT drawings released; 601 MT (30%) pending. Cumulative supply crosses 1,399 MT in Jan-27. Action: Close balance drawings / PO by Nov-26 to feed Jan-27 fabrication. 5. SUPPLY: Oct-26–Feb supply plan totals 2,000 MT but the balance is 1,988 MT (12 MT already done) - quantities not reconciled against scope. Action: Reconcile the supply plan against scope and the Sep-26 actual. 6. SUPPLY: Dispatch must jump from 12 MT in Sep-26 to 520 MT/month; Dec and Jan-27 alone need 1,020 MT. Action: Lock fabrication lot plan; weekly dispatch vs 250/300/500/520/430 MT. 7. ERECTION: Erection starts Nov-26 and must hold 150–300 MT/month for 8 months. Action: Mobilise crane and erection crew before Nov-26.

## Slide 2
Screen House / Building
Supply vendor: Samal Brothers | 1,019 MT + TS: equipment, crane & conveyor supports | Supply Oct-26 → Jan-27 | Erection Oct-26 → Apr-27
Data as on: 30-Sep-26
AT RISK
SCOPE
1,019 MT
+ TS: equipment, crane & conveyor supports
DRAWINGS RELEASED
1,019 MT
100% of scope · nil pending
SUPPLIED TILL SEP
Nil
Nil in Sep
OCT–DEC SUPPLY PLAN
750 MT
74% of scope · 250 / 250 / 250 MT
OCT–DEC ERECTION PLAN
430 MT
42% of scope · 0 erected, starts Oct-26
PEAK MONTHLY RATE (MT)
269 | 200
supply (Jan-27) | erection (Dec)
WORK-FRONT SEQUENCE & MONTHLY PLAN (MT)
Front / drawings
Supply
Erection
TS / bins
Handover
Work front
Oct-26
Nov
Dec
Jan-27
Feb
Mar
Apr
May
Jun
Total
Foundation release
Material receipt
Starter bay / bracing
Lower tiers
Screen / crane levels
Upper tiers / roof
Handover
Supply (MT)
250
250
250
269
–
–
–
–
–
1,019
Erection (MT)
50
180
200
166
168
160
95
–
–
1,019
Cum. erection (% of scope)
5%
23%
42%
58%
75%
91%
100%
100%
100%
Oct-26
BS Supply start
Oct-26
BS Erection start
Jan-27
Supply complete
Apr-27
Erection finish
Supply view: Material waiting at site builds to ≈423 MT by Jan-27 (supply ends 4 months before erection) - plan laydown and erection sequence.
KEY CONCERNS & ACTIONS
SUPPLY
Dispatch must jump from 0 MT in Sep-26 to 269 MT/month; Oct and Jan-27 alone need 519 MT.
Action: Lock fabrication lot plan; weekly dispatch vs 250/250/250/269 MT.
FRONT
Erection starts first and needs surveyed starter-bay foundations now.
Action: Release surveyed starter-bay foundations / anchor bolts.
ERECTION
Erection starts Oct-26 and must hold 50–200 MT/month for 7 months.
Action: Mobilise crane and erection crew before Oct-26.
SCOPE vs DRAWINGS vs SUPPLY vs ERECTION (MT)
Scope
1,019 MT
Drawings released
1,019 MT · 100%
Supplied till Sep
Nil
Erected till date
0 MT · starts Oct-26
Drawings complete; supply starts Oct-26; erection starts Oct-26.
BS = building structure · TS = technological structure
2
Notes: TALKING POINTS - SCREEN HOUSE / BUILDING 1. 1,019 MT scope, vendor Samal Brothers. 2. 1,019 MT drawings released (100% of scope · nil pending). 3. Next three months: supply 750 MT, erection 430 MT. 4. SUPPLY: Dispatch must jump from 0 MT in Sep-26 to 269 MT/month; Oct and Jan-27 alone need 519 MT. Action: Lock fabrication lot plan; weekly dispatch vs 250/250/250/269 MT. 5. FRONT: Erection starts first and needs surveyed starter-bay foundations now. Action: Release surveyed starter-bay foundations / anchor bolts. 6. ERECTION: Erection starts Oct-26 and must hold 50–200 MT/month for 7 months. Action: Mobilise crane and erection crew before Oct-26.

## Slide 3
Return Fines Building
Supply vendor: Vrinda Bhillai (site fabrication) | 393 MT + TS 66.3 MT (bins, liner, weighing bins) | Supply Oct-26 → Jan-27 | Erection Nov-26 → Mar-27
Data as on: 30-Sep-26
AT RISK
SCOPE
393 MT
+ TS 66.3 MT (bins, liner, weighing bins)
DRAWINGS RELEASED
393 MT
100% of scope · nil pending
SUPPLIED TILL SEP
Nil
Nil in Sep
OCT–DEC SUPPLY PLAN
360 MT
92% of scope · 120 / 120 / 120 MT
OCT–DEC ERECTION PLAN
100 MT
25% of scope · 0 erected, starts Nov-26
PEAK MONTHLY RATE (MT)
120 | 120
supply (Oct–Dec) | erection (Feb)
WORK-FRONT SEQUENCE & MONTHLY PLAN (MT)
Front / drawings
Supply
Erection
TS / bins
Handover
Work front
Oct-26
Nov
Dec
Jan-27
Feb
Mar
Apr
May
Jun
Total
Foundation release
Fabrication & supply
Starter frame
Bin support floors
Bins / liner (TS)
Handover
Supply (MT)
120
120
120
33
–
–
–
–
–
393
Erection (MT)
–
50
50
110
120
63
–
–
–
393
Cum. erection (% of scope)
–
13%
25%
53%
84%
100%
100%
100%
100%
Oct-26
BS Supply start
Nov-26
BS Erection start
Jan-27
Supply complete
Dec → Feb
Bins / liner (TS)
Mar-27
Erection finish
Supply view: Material waiting at site builds to ≈260 MT by Dec-26 (supply ends 3 months before erection) - plan laydown and erection sequence.
KEY CONCERNS & ACTIONS
SUPPLY
Dispatch must jump from 0 MT in Sep-26 to 120 MT/month; Oct and Nov alone need 240 MT.
Action: Lock fabrication lot plan; weekly dispatch vs 120/120/120/33 MT.
ERECTION
Erection starts Nov-26 and must hold 50–120 MT/month for 5 months.
Action: Mobilise crane and erection crew before Nov-26.
INTERFACE
Bin-support and conveyor interface not yet frozen.
Action: Freeze bin-support and conveyor interface.
SCOPE vs DRAWINGS vs SUPPLY vs ERECTION (MT)
Scope
393 MT
Drawings released
393 MT · 100%
Supplied till Sep
Nil
Erected till date
0 MT · starts Nov-26
Drawings complete; supply starts Oct-26; erection starts Nov-26.
BS = building structure · TS = technological structure
3
Notes: TALKING POINTS - RETURN FINES BUILDING 1. 393 MT scope, vendor Vrinda Bhillai (site fabrication). 2. 393 MT drawings released (100% of scope · nil pending). 3. Next three months: supply 360 MT, erection 100 MT. 4. SUPPLY: Dispatch must jump from 0 MT in Sep-26 to 120 MT/month; Oct and Nov alone need 240 MT. Action: Lock fabrication lot plan; weekly dispatch vs 120/120/120/33 MT. 5. ERECTION: Erection starts Nov-26 and must hold 50–120 MT/month for 5 months. Action: Mobilise crane and erection crew before Nov-26. 6. INTERFACE: Bin-support and conveyor interface not yet frozen. Action: Freeze bin-support and conveyor interface.

## Slide 4
Backup: combined supply and erection plan - all 3 buildings
Supply peaks at 870 MT/month in Dec-26; erection must climb from 50 to 538 MT/month by Feb-27 - Building structures status, MT
Data as on: 30-Sep-26
MONTHLY SUPPLY vs ERECTION (MT)
Chart: 
| Oct-26 | Nov | Dec | Jan-27 | Feb | Mar | Apr | May | Jun
Supply | 620 | 670 | 870 | 822 | 430 | 0 | 0 | 0 | 0
Erection | 50 | 380 | 500 | 526 | 538 | 473 | 345 | 300 | 300
CUMULATIVE SUPPLY vs ERECTION (MT)
Chart: 
| Oct-26 | Nov | Dec | Jan-27 | Feb | Mar | Apr | May | Jun
Cum. supply | 632 | 1302 | 2172 | 2994 | 3424 | 3424 | 3424 | 3424 | 3424
Cum. erection | 50 | 430 | 930 | 1456 | 1994 | 2467 | 2812 | 3112 | 3412
Scope | 3412 | 3412 | 3412 | 3412 | 3412 | 3412 | 3412 | 3412 | 3412
Dec-26: 2,172 MT supplied vs 930 erected
Peak material waiting at site: ≈1,538 MT (Jan-27)
MONTHLY PLAN BY BUILDING (MT)
Oct-26–Dec shaded · – = nil
Item
Oct-26
Nov
Dec
Jan-27
Feb
Mar
Apr
May
Jun
Total
Additive Grinding Building - supply
250
300
500
520
430
–
–
–
–
2,000
Additive Grinding Building - erection
–
150
250
250
250
250
250
300
300
2,000
Screen House / Building - supply
250
250
250
269
–
–
–
–
–
1,019
Screen House / Building - erection
50
180
200
166
168
160
95
–
–
1,019
Return Fines Building - supply
120
120
120
33
–
–
–
–
–
393
Return Fines Building - erection
–
50
50
110
120
63
–
–
–
393
Total supply
620
670
870
822
430
–
–
–
–
3,412
Total erection
50
380
500
526
538
473
345
300
300
3,412
GAPS TO CLOSE BEFORE PLAN SIGN-OFF
Additive Grinding Building: Only 1,399 of 2,000 MT drawings released; 601 MT (30%) pending. Cumulative supply crosses 1,399 MT in Jan-27.
Additive Grinding Building: Oct-26–Feb supply plan totals 2,000 MT but the balance is 1,988 MT (12 MT already done) - quantities not reconciled against scope.
Additive Grinding Building: Dispatch must jump from 12 MT in Sep-26 to 520 MT/month; Dec and Jan-27 alone need 1,020 MT.
Screen House / Building: Dispatch must jump from 0 MT in Sep-26 to 269 MT/month; Oct and Jan-27 alone need 519 MT.
Material waiting at site = cumulative supply − cumulative erection. Plan laydown for the peak, and size erection crews to the monthly erection rate.
4
Notes: Combined supply and erection plan across 3 groups.