## Dashboard
Schedule Engine ¦ Monthly Progress Dashboard
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
KEY FIGURES
Total activities |  | Completed |  | In progress |  | Not started |  | Planned % |  | Actual %
116 |  | 61 |  | 20 |  | 35 |  | 75.9% |  | 57.3%
Variance |  | Forecast finish |  | Critical |  | Late start |  | Overdue |  | Pending update
-18.59% |  | 2027-05-17 |  | 5 |  | 8 |  | 9 |  | 16
Building-wise progress
Building-wise | Activities | Not started | In progress | Completed | Planned % | Actual % | Variance | Gained this period | Late start | Overdue | Critical | Forecast finish
Project Milestones | 2 | 1 | 0 | 1 | 0% | 0% | 0% | 0% | 0 | 0 | 1 | 2027-05-17
Admin Building | 19 | 2 | 2 | 15 | 100% | 91.99% | -8.015% | 3.277% | 0 | 1 | 0 | 2026-11-10
Main Process Building | 19 | 5 | 4 | 10 | 74.7% | 57.82% | -16.88% | 8.556% | 0 | 0 | 4 | 2027-05-17
Warehouse Block | 19 | 5 | 3 | 11 | 81.6% | 68.54% | -13.06% | 5.024% | 1 | 2 | 0 | 2027-02-15
33kV Substation | 19 | 6 | 3 | 10 | 85.58% | 57.49% | -28.09% | 6.692% | 1 | 1 | 0 | 2027-01-22
Utility Building | 19 | 8 | 2 | 9 | 58.86% | 36.58% | -22.28% | 0% | 3 | 1 | 0 | 2027-05-04
STP & Pump House | 19 | 8 | 6 | 5 | 53.92% | 27.41% | -26.51% | 0% | 3 | 4 | 0 | 2027-03-04
EPC-wise progress
EPC-wise | Activities | Not started | In progress | Completed | Planned % | Actual % | Variance | Gained this period | Late start | Overdue | Critical | Forecast finish
Engineering | 24 | 0 | 2 | 22 | 100% | 99.22% | -0.7783% | 0% | 0 | 2 | 0 | 2026-10-09
Procurement | 24 | 3 | 8 | 13 | 85.19% | 59.28% | -25.91% | 8.212% | 3 | 3 | 1 | 2027-02-05
Construction | 66 | 31 | 10 | 25 | 63.09% | 42.46% | -20.63% | 3.909% | 5 | 4 | 3 | 2027-05-17
Others | 2 | 1 | 0 | 1 | 0% | 0% | 0% | 0% | 0 | 0 | 1 | 2027-05-17
ENGINE INSIGHTS
• Overall progress is 57.3% against a planned 75.9% as of 01-Oct-2026 (-18.6%). Progress gained this period: 4.4%.
• 8 activities were due to start before the Data Date but have not started.
• 9 activities are past their finish date and still open.
• 2 future activities show progress - check these were really started early.
• 16 activities still need your update this month.
• 2 activities are progressing out of sequence.
• 33kV Substation is the most behind: 57.5% vs 85.6% planned (-28.1%).
• EPC progress: Engineering 99%, Procurement 59%, Construction 42%.
• Forecast project finish: 17-May-2027 - 41 working days later than baseline.
• 7 milestones are forecast late; worst: ADM-C1190 Building handover to client (11-Sep-26 → 10-Nov-26).
• 5 activities are critical. Watch them in the look-ahead.

## Building x EPC
Progress matrix - Building x EPC (Actual % / Planned %)
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
Building | Engineering Actual | Engineering Planned | Procurement Actual | Procurement Planned | Construction Actual | Construction Planned | Others Actual | Others Planned | Overall Actual | Overall Planned
Project Milestones | [6 empty] | 0% | 0% | 0% | 0%
Admin Building | 100% | 100% | 100% | 100% | 84.95% | 100% |  |  | 91.99% | 100%
Main Process Building | 100% | 100% | 59.42% | 81.27% | 41.88% | 62.03% |  |  | 57.82% | 74.7%
Warehouse Block | 100% | 100% | 81.66% | 100% | 52.29% | 66.76% |  |  | 68.54% | 81.6%
33kV Substation | 100% | 100% | 77.84% | 100% | 32.52% | 73.12% |  |  | 57.49% | 85.58%
Utility Building | 100% | 100% | 21.17% | 62.7% | 24.33% | 43.32% |  |  | 36.58% | 58.86%
STP & Pump House | 93.03% | 100% | 9.483% | 69.83% | 16.34% | 32.65% |  |  | 27.41% | 53.92%

## Schedule
Schedule - Industrial Plant Expansion - Phase 2 (Demo)
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
Activity ID | Activity Name | Building | EPC | Status | Orig Dur | Rem Dur | % Complete | Start | Finish | Actual Start | Actual Finish | BL Start | BL Finish | Finish Var (d) | Total Float | Critical | Flags | Remarks
IPX-P2 | Industrial Plant Expansion - Phase 2 (Demo) |  |  | In Progress | 417 |  | 57.34% | 2026-01-05 | 2027-05-17 | 2026-01-05 |  | 2026-01-05 | 2027-03-30 | 41 | 0 |  | 116 activities
GEN | Project Milestones |  |  | In Progress | 417 |  | 0% | 2026-01-05 | 2027-05-17 | 2026-01-05 |  | 2026-01-05 | 2027-03-30 | 41 | 0 |  | 2 activities
MS-1000 | Notice to proceed / Project start | Project Milestones | Others | Completed | 0 | 0 | 100% | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 0
MS-9000 | Plant mechanical completion | Project Milestones | Others | Not Started | 0 | 0 | 0% | 2027-05-17 | 2027-05-17 |  |  | 2027-03-30 | 2027-03-30 | 41 | 0 | Yes | Critical
ADM | Admin Building |  |  | In Progress | 256 |  | 91.99% | 2026-01-08 | 2026-11-10 | 2026-01-08 |  | 2026-01-05 | 2026-09-11 | 48 | 158 |  | 19 activities
ADM.E | Engineering |  |  | Completed | 80 |  | 100% | 2026-01-08 | 2026-04-14 | 2026-01-08 | 2026-04-14 | 2026-01-05 | 2026-03-24 | 17 |  |  | 4 activities
ADM-E1010 | Design basis & architectural layout | Admin Building | Engineering | Completed | 19 | 0 | 100% | 2026-01-08 | 2026-02-10 | 2026-01-08 | 2026-02-10 | 2026-01-05 | 2026-01-30 | 7
ADM-E1020 | Structural design & IFC drawings | Admin Building | Engineering | Completed | 34 | 0 | 100% | 2026-01-21 | 2026-03-20 | 2026-01-21 | 2026-03-20 | 2026-01-12 | 2026-02-27 | 14
ADM-E1030 | MEP design & drawings | Admin Building | Engineering | Completed | 36 | 0 | 100% | 2026-02-17 | 2026-04-14 | 2026-02-17 | 2026-04-14 | 2026-02-02 | 2026-03-24 | 14
ADM-E1040 | Drawing approval by client | Admin Building | Engineering | Completed | 10 | 0 | 100% | 2026-03-24 | 2026-04-14 | 2026-03-24 | 2026-04-14 | 2026-03-11 | 2026-03-24 | 14
ADM.P | Procurement |  |  | Completed | 110 |  | 100% | 2026-03-25 | 2026-07-31 | 2026-03-25 | 2026-07-31 | 2026-02-28 | 2026-06-30 | 27 |  |  | 4 activities
ADM-P1050 | Structural steel - PO placement | Admin Building | Procurement | Completed | 11 | 0 | 100% | 2026-03-25 | 2026-04-07 | 2026-03-25 | 2026-04-07 | 2026-02-28 | 2026-03-13 | 20
ADM-P1060 | Structural steel - fabrication & supply to site | Admin Building | Procurement | Completed | 58 | 0 | 100% | 2026-04-13 | 2026-07-01 | 2026-04-13 | 2026-07-01 | 2026-03-14 | 2026-05-21 | 35
ADM-P1070 | MEP equipment - PO placement | Admin Building | Procurement | Completed | 13 | 0 | 100% | 2026-04-15 | 2026-04-28 | 2026-04-15 | 2026-04-28 | 2026-03-25 | 2026-04-09 | 16
ADM-P1080 | MEP equipment - manufacturing & delivery | Admin Building | Procurement | Completed | 70 | 0 | 100% | 2026-05-04 | 2026-07-31 | 2026-05-04 | 2026-07-31 | 2026-04-10 | 2026-06-30 | 27
ADM.C | Construction |  |  | In Progress | 256 |  | 84.95% | 2026-01-08 | 2026-11-10 | 2026-01-08 |  | 2026-01-05 | 2026-09-11 | 48 | 158 |  | 11 activities
ADM-C1090 | Site mobilisation & survey | Admin Building | Construction | Completed | 5 | 0 | 100% | 2026-01-08 | 2026-01-14 | 2026-01-08 | 2026-01-14 | 2026-01-05 | 2026-01-09 | 4
ADM-C1100 | Excavation | Admin Building | Construction | Completed | 17 | 0 | 100% | 2026-02-04 | 2026-02-26 | 2026-02-04 | 2026-02-26 | 2026-01-23 | 2026-02-12 | 12
ADM-C1110 | PCC & foundation concreting | Admin Building | Construction | Completed | 30 | 0 | 100% | 2026-02-14 | 2026-03-26 | 2026-02-14 | 2026-03-26 | 2026-02-02 | 2026-03-09 | 15
ADM-C1120 | Plinth beam & backfilling | Admin Building | Construction | Completed | 20 | 0 | 100% | 2026-03-28 | 2026-04-23 | 2026-03-28 | 2026-04-23 | 2026-03-10 | 2026-04-01 | 18
ADM-C1130 | Superstructure - RCC / steel erection | Admin Building | Construction | Completed | 54 | 0 | 100% | 2026-05-01 | 2026-07-13 | 2026-05-01 | 2026-07-13 | 2026-04-02 | 2026-06-04 | 33
ADM-C1150 | Masonry & plastering | Admin Building | Construction | Completed | 37 | 0 | 100% | 2026-05-29 | 2026-07-11 | 2026-05-29 | 2026-07-11 | 2026-04-27 | 2026-06-08 | 29
ADM-C1140 | Roofing & cladding | Admin Building | Construction | Completed | 21 | 0 | 100% | 2026-07-13 | 2026-08-03 | 2026-07-13 | 2026-08-03 | 2026-05-30 | 2026-06-23 | 35
ADM-C1160 | MEP installation | Admin Building | Construction | In Progress | 48 | 18 | 62% | 2026-08-04 | 2026-10-23 | 2026-08-04 |  | 2026-07-01 | 2026-08-26 | 48 | 158 |  | In progress
ADM-C1170 | Finishes - flooring & painting | Admin Building | Construction | In Progress | 40 | 11 | 73% | 2026-08-05 | 2026-10-14 | 2026-08-05 |  | 2026-06-24 | 2026-08-08 | 55 | 179 |  | Overdue, Due this period, In progress, No concern yet
ADM-C1180 | Testing & commissioning | Admin Building | Construction | Not Started | 14 | 14 | 0% | 2026-10-24 | 2026-11-10 |  |  | 2026-08-27 | 2026-09-11 | 48 | 158
ADM-C1190 | Building handover to client | Admin Building | Construction | Not Started | 0 | 0 | 0% | 2026-11-10 | 2026-11-10 |  |  | 2026-09-11 | 2026-09-11 | 48 | 158
MPB | Main Process Building |  |  | In Progress | 400 |  | 57.82% | 2026-01-24 | 2027-05-17 | 2026-01-24 |  | 2026-01-16 | 2027-03-30 | 41 | 0 |  | 19 activities
MPB.E | Engineering |  |  | Completed | 141 |  | 100% | 2026-01-30 | 2026-07-15 | 2026-01-30 | 2026-07-15 | 2026-01-19 | 2026-06-09 | 31 |  |  | 4 activities
MPB-E1010 | Design basis & architectural layout | Main Process Building | Engineering | Completed | 32 | 0 | 100% | 2026-01-30 | 2026-03-20 | 2026-01-30 | 2026-03-20 | 2026-01-19 | 2026-03-05 | 11
MPB-E1020 | Structural design & IFC drawings | Main Process Building | Engineering | Completed | 52 | 0 | 100% | 2026-02-11 | 2026-05-04 | 2026-02-11 | 2026-05-04 | 2026-01-27 | 2026-04-10 | 16
MPB-E1030 | MEP design & drawings | Main Process Building | Engineering | Completed | 67 | 0 | 100% | 2026-03-30 | 2026-07-15 | 2026-03-30 | 2026-07-15 | 2026-03-06 | 2026-06-09 | 26
MPB-E1040 | Drawing approval by client | Main Process Building | Engineering | Completed | 21 | 0 | 100% | 2026-05-22 | 2026-07-15 | 2026-05-22 | 2026-07-15 | 2026-05-12 | 2026-06-09 | 26
MPB.P | Procurement |  |  | In Progress | 213 |  | 59.42% | 2026-05-11 | 2027-01-19 | 2026-05-11 |  | 2026-04-11 | 2026-12-01 | 41 | 0 |  | 4 activities
MPB-P1050 | Structural steel - PO placement | Main Process Building | Procurement | Completed | 22 | 0 | 100% | 2026-05-11 | 2026-06-09 | 2026-05-11 | 2026-06-09 | 2026-04-11 | 2026-05-06 | 29
MPB-P1060 | Structural steel - fabrication & supply to site | Main Process Building | Procurement | In Progress | 99 | 18 | 82% | 2026-06-15 | 2026-10-23 | 2026-06-15 |  | 2026-05-07 | 2026-08-31 | 44 | 34 |  | In progress
MPB-P1070 | MEP equipment - PO placement | Main Process Building | Procurement | Completed | 22 | 0 | 100% | 2026-07-20 | 2026-08-13 | 2026-07-20 | 2026-08-13 | 2026-06-10 | 2026-07-04 | 34
MPB-P1080 | MEP equipment - manufacturing & delivery | Main Process Building | Procurement | In Progress | 124 | 91 | 27% | 2026-08-18 | 2027-01-19 | 2026-08-18 |  | 2026-07-06 | 2026-12-01 | 41 | 0 | Yes | In progress, Critical
MPB.C | Construction |  |  | In Progress | 400 |  | 41.88% | 2026-01-24 | 2027-05-17 | 2026-01-24 |  | 2026-01-16 | 2027-03-30 | 41 | 0 |  | 11 activities
MPB-C1090 | Site mobilisation & survey | Main Process Building | Construction | Completed | 10 | 0 | 100% | 2026-01-24 | 2026-02-06 | 2026-01-24 | 2026-02-06 | 2026-01-16 | 2026-01-28 | 8
MPB-C1100 | Excavation | Main Process Building | Construction | Completed | 32 | 0 | 100% | 2026-02-28 | 2026-04-09 | 2026-02-28 | 2026-04-09 | 2026-02-07 | 2026-03-17 | 19
MPB-C1110 | PCC & foundation concreting | Main Process Building | Construction | Completed | 45 | 0 | 100% | 2026-03-18 | 2026-05-12 | 2026-03-18 | 2026-05-12 | 2026-02-16 | 2026-04-10 | 27
MPB-C1120 | Plinth beam & backfilling | Main Process Building | Construction | Completed | 28 | 0 | 100% | 2026-05-22 | 2026-06-26 | 2026-05-22 | 2026-06-26 | 2026-04-11 | 2026-05-13 | 38
MPB-C1130 | Superstructure - RCC / steel erection | Main Process Building | Construction | In Progress | 102 | 49 | 52% | 2026-07-08 | 2026-11-30 | 2026-07-08 |  | 2026-05-25 | 2026-09-21 | 57 | 49 |  | In progress
MPB-C1150 | Masonry & plastering | Main Process Building | Construction | In Progress | 69 | 35 | 49% | 2026-08-06 | 2026-11-13 | 2026-08-06 |  | 2026-06-17 | 2026-09-05 | 56 | 81 |  | In progress
MPB-C1140 | Roofing & cladding | Main Process Building | Construction | Not Started | 39 | 39 | 0% | 2026-11-25 | 2027-01-09 |  |  | 2026-09-16 | 2026-11-02 | 57 | 49
MPB-C1170 | Finishes - flooring & painting | Main Process Building | Construction | Not Started | 58 | 58 | 0% | 2027-01-11 | 2027-03-19 |  |  | 2026-11-03 | 2027-01-11 | 57 | 49
MPB-C1160 | MEP installation | Main Process Building | Construction | Not Started | 78 | 78 | 0% | 2027-01-20 | 2027-04-22 |  |  | 2026-12-02 | 2027-03-04 | 41 | 0 | Yes | Critical
MPB-C1180 | Testing & commissioning | Main Process Building | Construction | Not Started | 21 | 21 | 0% | 2027-04-23 | 2027-05-17 |  |  | 2027-03-05 | 2027-03-30 | 41 | 0 | Yes | Critical
MPB-C1190 | Building handover to client | Main Process Building | Construction | Not Started | 0 | 0 | 0% | 2027-05-17 | 2027-05-17 |  |  | 2027-03-30 | 2027-03-30 | 41 | 0 | Yes | Critical
WHS | Warehouse Block |  |  | In Progress | 295 |  | 68.54% | 2026-02-27 | 2027-02-15 | 2026-02-27 |  | 2026-02-21 | 2027-01-05 | 34 | 77 |  | 19 activities
WHS.E | Engineering |  |  | Completed | 83 |  | 100% | 2026-03-06 | 2026-06-11 | 2026-03-06 | 2026-06-11 | 2026-03-03 | 2026-06-01 | 9 |  |  | 4 activities
WHS-E1010 | Design basis & architectural layout | Warehouse Block | Engineering | Completed | 21 | 0 | 100% | 2026-03-06 | 2026-04-08 | 2026-03-06 | 2026-04-08 | 2026-03-03 | 2026-04-01 | 4
WHS-E1020 | Structural design & IFC drawings | Warehouse Block | Engineering | Completed | 30 | 0 | 100% | 2026-03-18 | 2026-05-06 | 2026-03-18 | 2026-05-06 | 2026-03-11 | 2026-04-22 | 10
WHS-E1030 | MEP design & drawings | Warehouse Block | Engineering | Completed | 42 | 0 | 100% | 2026-04-15 | 2026-06-11 | 2026-04-15 | 2026-06-11 | 2026-04-02 | 2026-06-01 | 8
WHS-E1040 | Drawing approval by client | Warehouse Block | Engineering | Completed | 14 | 0 | 100% | 2026-05-15 | 2026-06-11 | 2026-05-15 | 2026-06-11 | 2026-05-13 | 2026-06-01 | 8
WHS.P | Procurement |  |  | In Progress | 157 |  | 81.66% | 2026-05-07 | 2026-11-10 | 2026-05-07 |  | 2026-04-23 | 2026-09-28 | 34 | 77 |  | 4 activities
WHS-P1050 | Structural steel - PO placement | Warehouse Block | Procurement | Completed | 13 | 0 | 100% | 2026-05-07 | 2026-05-21 | 2026-05-07 | 2026-05-21 | 2026-04-23 | 2026-05-07 | 12
WHS-P1060 | Structural steel - fabrication & supply to site | Warehouse Block | Procurement | Completed | 58 | 0 | 100% | 2026-05-28 | 2026-08-05 | 2026-05-28 | 2026-08-05 | 2026-05-08 | 2026-07-14 | 19
WHS-P1070 | MEP equipment - PO placement | Warehouse Block | Procurement | Completed | 18 | 0 | 100% | 2026-06-13 | 2026-07-08 | 2026-06-13 | 2026-07-08 | 2026-06-02 | 2026-06-22 | 14
WHS-P1080 | MEP equipment - manufacturing & delivery | Warehouse Block | Procurement | In Progress | 83 | 32 | 62% | 2026-07-09 | 2026-11-10 | 2026-07-09 |  | 2026-06-23 | 2026-09-28 | 34 | 77 |  | In progress
WHS.C | Construction |  |  | In Progress | 295 |  | 52.29% | 2026-02-27 | 2027-02-15 | 2026-02-27 |  | 2026-02-21 | 2027-01-05 | 34 | 77 |  | 11 activities
WHS-C1090 | Site mobilisation & survey | Warehouse Block | Construction | Completed | 8 | 0 | 100% | 2026-02-27 | 2026-03-09 | 2026-02-27 | 2026-03-09 | 2026-02-21 | 2026-03-02 | 5
WHS-C1100 | Excavation | Warehouse Block | Construction | Completed | 19 | 0 | 100% | 2026-03-30 | 2026-04-24 | 2026-03-30 | 2026-04-24 | 2026-03-23 | 2026-04-14 | 9
WHS-C1110 | PCC & foundation concreting | Warehouse Block | Construction | Completed | 37 | 0 | 100% | 2026-04-13 | 2026-05-25 | 2026-04-13 | 2026-05-25 | 2026-03-31 | 2026-05-13 | 10
WHS-C1120 | Plinth beam & backfilling | Warehouse Block | Construction | Completed | 20 | 0 | 100% | 2026-05-28 | 2026-06-22 | 2026-05-28 | 2026-06-22 | 2026-05-14 | 2026-06-05 | 14
WHS-C1130 | Superstructure - RCC / steel erection | Warehouse Block | Construction | In Progress | 66 | 1 | 99% | 2026-06-24 | 2026-10-01 | 2026-06-24 |  | 2026-06-06 | 2026-08-22 | 34 | 79 |  | Overdue, Due this period, In progress, No concern yet
WHS-C1150 | Masonry & plastering | Warehouse Block | Construction | In Progress | 41 | 9 | 77% | 2026-07-23 | 2026-10-12 | 2026-07-23 |  | 2026-06-30 | 2026-08-17 | 47 | 99 |  | Overdue, Due this period, In progress, No concern yet
WHS-C1140 | Roofing & cladding | Warehouse Block | Construction | Not Started | 32 | 32 | 0% | 2026-10-01 | 2026-11-10 |  |  | 2026-08-18 | 2026-09-23 | 38 | 116 |  | Late start, Due this period, Pending update, No concern yet
WHS-C1160 | MEP installation | Warehouse Block | Construction | Not Started | 63 | 63 | 0% | 2026-11-11 | 2027-01-23 |  |  | 2026-09-29 | 2026-12-14 | 34 | 77
WHS-C1170 | Finishes - flooring & painting | Warehouse Block | Construction | Not Started | 42 | 42 | 0% | 2026-11-11 | 2026-12-30 |  |  | 2026-09-24 | 2026-11-14 | 38 | 116
WHS-C1180 | Testing & commissioning | Warehouse Block | Construction | Not Started | 18 | 18 | 0% | 2027-01-25 | 2027-02-15 |  |  | 2026-12-15 | 2027-01-05 | 34 | 77
WHS-C1190 | Building handover to client | Warehouse Block | Construction | Not Started | 0 | 0 | 0% | 2027-02-15 | 2027-02-15 |  |  | 2027-01-05 | 2027-01-05 | 34 | 77
SUB | 33kV Substation |  |  | In Progress | 253 |  | 57.49% | 2026-03-27 | 2027-01-22 | 2026-03-27 |  | 2026-03-18 | 2026-12-01 | 44 | 83 |  | 19 activities
SUB.E | Engineering |  |  | Completed | 76 |  | 100% | 2026-04-10 | 2026-07-07 | 2026-04-10 | 2026-07-07 | 2026-04-01 | 2026-06-17 | 17 |  |  | 4 activities
SUB-E1010 | Design basis & architectural layout | 33kV Substation | Engineering | Completed | 20 | 0 | 100% | 2026-04-10 | 2026-05-13 | 2026-04-10 | 2026-05-13 | 2026-04-01 | 2026-04-29 | 10
SUB-E1020 | Structural design & IFC drawings | 33kV Substation | Engineering | Completed | 26 | 0 | 100% | 2026-04-27 | 2026-06-01 | 2026-04-27 | 2026-06-01 | 2026-04-09 | 2026-05-14 | 12
SUB-E1030 | MEP design & drawings | 33kV Substation | Engineering | Completed | 35 | 0 | 100% | 2026-05-22 | 2026-07-07 | 2026-05-22 | 2026-07-07 | 2026-04-30 | 2026-06-17 | 14
SUB-E1040 | Drawing approval by client | 33kV Substation | Engineering | Completed | 12 | 0 | 100% | 2026-06-12 | 2026-07-07 | 2026-06-12 | 2026-07-07 | 2026-06-02 | 2026-06-17 | 14
SUB.P | Procurement |  |  | In Progress | 128 |  | 77.84% | 2026-06-10 | 2026-11-10 | 2026-06-10 |  | 2026-05-15 | 2026-09-16 | 44 | 83 |  | 4 activities
SUB-P1050 | Structural steel - PO placement | 33kV Substation | Procurement | Completed | 12 | 0 | 100% | 2026-06-10 | 2026-06-23 | 2026-06-10 | 2026-06-23 | 2026-05-15 | 2026-05-28 | 22
SUB-P1060 | Structural steel - fabrication & supply to site | 33kV Substation | Procurement | In Progress | 59 | 1 | 98% | 2026-07-01 | 2026-10-01 | 2026-07-01 |  | 2026-05-29 | 2026-08-05 | 48 | 83 |  | Overdue, Due this period, In progress, No concern yet
SUB-P1070 | MEP equipment - PO placement | 33kV Substation | Procurement | Completed | 15 | 0 | 100% | 2026-07-14 | 2026-07-29 | 2026-07-14 | 2026-07-29 | 2026-06-18 | 2026-07-04 | 21
SUB-P1080 | MEP equipment - manufacturing & delivery | 33kV Substation | Procurement | In Progress | 62 | 32 | 49% | 2026-08-07 | 2026-11-10 | 2026-08-07 |  | 2026-07-06 | 2026-09-16 | 44 | 96 |  | In progress
SUB.C | Construction |  |  | In Progress | 253 |  | 32.52% | 2026-03-27 | 2027-01-22 | 2026-03-27 |  | 2026-03-18 | 2026-12-01 | 44 | 96 |  | 11 activities
SUB-C1090 | Site mobilisation & survey | 33kV Substation | Construction | Completed | 5 | 0 | 100% | 2026-03-27 | 2026-04-01 | 2026-03-27 | 2026-04-01 | 2026-03-18 | 2026-03-23 | 8
SUB-C1100 | Excavation | 33kV Substation | Construction | Completed | 18 | 0 | 100% | 2026-05-15 | 2026-06-09 | 2026-05-15 | 2026-06-09 | 2026-04-21 | 2026-05-11 | 25
SUB-C1110 | PCC & foundation concreting | 33kV Substation | Construction | Completed | 29 | 0 | 100% | 2026-06-03 | 2026-07-09 | 2026-06-03 | 2026-07-09 | 2026-04-29 | 2026-06-01 | 33
SUB-C1120 | Plinth beam & backfilling | 33kV Substation | Construction | Completed | 17 | 0 | 100% | 2026-07-21 | 2026-08-08 | 2026-07-21 | 2026-08-08 | 2026-06-02 | 2026-06-20 | 42
SUB-C1130 | Superstructure - RCC / steel erection | 33kV Substation | Construction | In Progress | 53 | 31 | 41% | 2026-08-19 | 2026-11-07 | 2026-08-19 |  | 2026-06-22 | 2026-08-22 | 64 | 98 |  | In progress
SUB-C1150 | Masonry & plastering | 33kV Substation | Construction | Not Started | 32 | 32 | 0% | 2026-10-01 | 2026-11-10 |  |  | 2026-07-15 | 2026-08-21 | 66 | 118 |  | Late start, Due this period, Pending update, No concern yet
SUB-C1140 | Roofing & cladding | 33kV Substation | Construction | Not Started | 23 | 23 | 0% | 2026-11-03 | 2026-11-30 |  |  | 2026-08-18 | 2026-09-12 | 64 | 101
SUB-C1160 | MEP installation | 33kV Substation | Construction | Not Started | 48 | 48 | 0% | 2026-11-11 | 2027-01-06 |  |  | 2026-09-17 | 2026-11-14 | 44 | 96
SUB-C1170 | Finishes - flooring & painting | 33kV Substation | Construction | Not Started | 40 | 40 | 0% | 2026-12-01 | 2027-01-16 |  |  | 2026-09-14 | 2026-10-31 | 64 | 101
SUB-C1180 | Testing & commissioning | 33kV Substation | Construction | Not Started | 14 | 14 | 0% | 2027-01-07 | 2027-01-22 |  |  | 2026-11-16 | 2026-12-01 | 44 | 96
SUB-C1190 | Building handover to client | 33kV Substation | Construction | Not Started | 0 | 0 | 0% | 2027-01-22 | 2027-01-22 |  |  | 2026-12-01 | 2026-12-01 | 44 | 96
UTL | Utility Building |  |  | In Progress | 314 |  | 36.58% | 2026-04-25 | 2027-05-04 | 2026-04-25 |  | 2026-04-23 | 2027-03-17 | 40 | 11 |  | 19 activities
UTL.E | Engineering |  |  | Completed | 78 |  | 100% | 2026-05-14 | 2026-08-12 | 2026-05-14 | 2026-08-12 | 2026-05-14 | 2026-08-07 | 4 |  |  | 4 activities
UTL-E1010 | Design basis & architectural layout | Utility Building | Engineering | Completed | 24 | 0 | 100% | 2026-05-14 | 2026-06-15 | 2026-05-14 | 2026-06-15 | 2026-05-14 | 2026-06-16 | -1
UTL-E1020 | Structural design & IFC drawings | Utility Building | Engineering | Completed | 35 | 0 | 100% | 2026-05-22 | 2026-07-16 | 2026-05-22 | 2026-07-16 | 2026-05-21 | 2026-07-08 | 6
UTL-E1030 | MEP design & drawings | Utility Building | Engineering | Completed | 38 | 0 | 100% | 2026-06-24 | 2026-08-12 | 2026-06-24 | 2026-08-12 | 2026-06-17 | 2026-08-07 | 3
UTL-E1040 | Drawing approval by client | Utility Building | Engineering | Completed | 13 | 0 | 100% | 2026-07-28 | 2026-08-12 | 2026-07-28 | 2026-08-12 | 2026-07-22 | 2026-08-07 | 3
UTL.P | Procurement |  |  | In Progress | 169 |  | 21.17% | 2026-07-17 | 2027-02-05 | 2026-07-17 |  | 2026-07-09 | 2026-12-18 | 40 | 11 |  | 4 activities
UTL-P1050 | Structural steel - PO placement | Utility Building | Procurement | Completed | 14 | 0 | 100% | 2026-07-17 | 2026-08-03 | 2026-07-17 | 2026-08-03 | 2026-07-09 | 2026-07-24 | 8
UTL-P1060 | Structural steel - fabrication & supply to site | Utility Building | Procurement | In Progress | 61 | 54 | 29% | 2026-08-04 | 2026-12-05 | 2026-08-04 |  | 2026-07-25 | 2026-10-06 | 50 | 46 |  | In progress, Pending update
UTL-P1070 | MEP equipment - PO placement | Utility Building | Procurement | In Progress | 17 | 12 | 44% | 2026-08-20 | 2026-10-15 | 2026-08-20 |  | 2026-08-08 | 2026-08-28 | 40 | 11 |  | Overdue, Due this period, In progress, Pending update, No concern yet
UTL-P1080 | MEP equipment - manufacturing & delivery | Utility Building | Procurement | Not Started | 93 | 93 | 0% | 2026-10-16 | 2027-02-05 |  |  | 2026-08-29 | 2026-12-18 | 40 | 11 |  | Late start, Due this period, Pending update, No concern yet
UTL.C | Construction |  |  | In Progress | 314 |  | 24.33% | 2026-04-25 | 2027-05-04 | 2026-04-25 |  | 2026-04-23 | 2027-03-17 | 40 | 11 |  | 11 activities
UTL-C1090 | Site mobilisation & survey | Utility Building | Construction | Completed | 7 | 0 | 100% | 2026-04-25 | 2026-05-02 | 2026-04-25 | 2026-05-02 | 2026-04-23 | 2026-04-30 | 2
UTL-C1100 | Excavation | Utility Building | Construction | Completed | 24 | 0 | 100% | 2026-06-04 | 2026-07-01 | 2026-06-04 | 2026-07-01 | 2026-06-02 | 2026-06-29 | 2
UTL-C1110 | PCC & foundation concreting | Utility Building | Construction | Completed | 30 | 0 | 100% | 2026-06-16 | 2026-07-27 | 2026-06-16 | 2026-07-27 | 2026-06-10 | 2026-07-14 | 11
UTL-C1120 | Plinth beam & backfilling | Utility Building | Construction | Completed | 21 | 0 | 100% | 2026-08-03 | 2026-08-27 | 2026-08-03 | 2026-08-27 | 2026-07-15 | 2026-08-07 | 16
UTL-C1130 | Superstructure - RCC / steel erection | Utility Building | Construction | Not Started | 69 | 69 | 0% | 2026-10-01 | 2026-12-23 |  |  | 2026-08-12 | 2026-11-03 | 42 | 61 |  | Late start, Due this period, Pending update, No concern yet
UTL-C1150 | Masonry & plastering | Utility Building | Construction | Not Started | 47 | 47 | 0% | 2026-10-27 | 2026-12-21 |  |  | 2026-09-05 | 2026-10-31 | 42 | 86 |  | Late start, Due this period, Pending update, No concern yet
UTL-C1140 | Roofing & cladding | Utility Building | Construction | Not Started | 29 | 29 | 0% | 2026-12-18 | 2027-01-21 |  |  | 2026-10-29 | 2026-12-02 | 42 | 61
UTL-C1170 | Finishes - flooring & painting | Utility Building | Construction | Not Started | 36 | 36 | 0% | 2027-01-22 | 2027-03-05 |  |  | 2026-12-03 | 2027-01-14 | 42 | 61
UTL-C1160 | MEP installation | Utility Building | Construction | Not Started | 59 | 59 | 0% | 2027-02-06 | 2027-04-16 |  |  | 2026-12-19 | 2027-02-27 | 40 | 11
UTL-C1180 | Testing & commissioning | Utility Building | Construction | Not Started | 15 | 15 | 0% | 2027-04-17 | 2027-05-04 |  |  | 2027-03-01 | 2027-03-17 | 40 | 11
UTL-C1190 | Building handover to client | Utility Building | Construction | Not Started | 0 | 0 | 0% | 2027-05-04 | 2027-05-04 |  |  | 2027-03-17 | 2027-03-17 | 40 | 11
STP | STP & Pump House |  |  | In Progress | 234 |  | 27.41% | 2026-05-29 | 2027-03-04 | 2026-05-29 |  | 2026-05-28 | 2027-01-19 | 37 | 51 |  | 19 activities
STP.E | Engineering |  |  | In Progress | 84 |  | 93.03% | 2026-07-02 | 2026-10-09 | 2026-07-02 |  | 2026-06-25 | 2026-08-24 | 39 | 51 |  | 4 activities
STP-E1010 | Design basis & architectural layout | STP & Pump House | Engineering | Completed | 14 | 0 | 100% | 2026-07-02 | 2026-07-23 | 2026-07-02 | 2026-07-23 | 2026-06-25 | 2026-07-14 | 7
STP-E1020 | Structural design & IFC drawings | STP & Pump House | Engineering | Completed | 21 | 0 | 100% | 2026-07-10 | 2026-08-11 | 2026-07-10 | 2026-08-11 | 2026-07-02 | 2026-07-30 | 8
STP-E1030 | MEP design & drawings | STP & Pump House | Engineering | In Progress | 29 | 6 | 84% | 2026-07-29 | 2026-10-09 | 2026-07-29 |  | 2026-07-15 | 2026-08-24 | 33 | 51 |  | Overdue, Due this period, In progress, Pending update, No concern yet
STP-E1040 | Drawing approval by client | STP & Pump House | Engineering | In Progress | 9 | 1 | 95% | 2026-08-12 | 2026-10-09 | 2026-08-12 |  | 2026-08-12 | 2026-08-24 | 33 | 151 |  | Overdue, Due this period, In progress, Pending update, No concern yet
STP.P | Procurement |  |  | In Progress | 114 |  | 9.483% | 2026-08-14 | 2026-12-30 | 2026-08-14 |  | 2026-07-31 | 2026-11-13 | 39 | 62 |  | 4 activities
STP-P1050 | Structural steel - PO placement | STP & Pump House | Procurement | Completed | 9 | 0 | 100% | 2026-08-14 | 2026-08-25 | 2026-08-14 | 2026-08-25 | 2026-07-31 | 2026-08-10 | 12
STP-P1060 | Structural steel - fabrication & supply to site | STP & Pump House | Procurement | In Progress | 40 | 42 | 5% | 2026-08-29 | 2026-11-21 | 2026-08-29 |  | 2026-08-11 | 2026-09-26 | 45 | 87 |  | In progress, Pending update
STP-P1070 | MEP equipment - PO placement | STP & Pump House | Procurement | Not Started | 11 | 11 | 0% | 2026-10-10 | 2026-10-23 |  |  | 2026-08-25 | 2026-09-05 | 39 | 62 |  | Late start, Overdue, Due this period, Pending update, No concern yet
STP-P1080 | MEP equipment - manufacturing & delivery | STP & Pump House | Procurement | Not Started | 56 | 56 | 0% | 2026-10-24 | 2026-12-30 |  |  | 2026-09-07 | 2026-11-13 | 39 | 62 |  | Late start, Due this period, Pending update, No concern yet
STP.C | Construction |  |  | In Progress | 234 |  | 16.34% | 2026-05-29 | 2027-03-04 | 2026-05-29 |  | 2026-05-28 | 2027-01-19 | 37 | 62 |  | 11 activities
STP-C1090 | Site mobilisation & survey | STP & Pump House | Construction | Completed | 5 | 0 | 100% | 2026-05-29 | 2026-06-03 | 2026-05-29 | 2026-06-03 | 2026-05-28 | 2026-06-02 | 1
STP-C1100 | Excavation | STP & Pump House | Construction | Completed | 15 | 0 | 100% | 2026-07-24 | 2026-08-10 | 2026-07-24 | 2026-08-10 | 2026-07-14 | 2026-07-30 | 9
STP-C1110 | PCC & foundation concreting | STP & Pump House | Construction | In Progress | 28 | 15 | 58% | 2026-08-06 | 2026-10-19 | 2026-08-06 |  | 2026-07-22 | 2026-08-24 | 47 | 72 |  | Overdue, Due this period, In progress, Pending update, No concern yet
STP-C1150 | Masonry & plastering | STP & Pump House | Construction | In Progress | 33 | 31 | 5% | 2026-08-26 | 2027-01-07 | 2026-08-26 |  | 2026-10-06 | 2026-11-14 | 45 | 76 |  | Future progress, In progress, Pending update, Out of sequence, No concern yet
STP-C1160 | MEP installation | STP & Pump House | Construction | In Progress | 43 | 41 | 5% | 2026-08-26 | 2027-02-17 | 2026-08-26 |  | 2026-11-14 | 2027-01-04 | 37 | 62 |  | Future progress, In progress, Pending update, Out of sequence, No concern yet
STP-C1120 | Plinth beam & backfilling | STP & Pump House | Construction | Not Started | 15 | 15 | 0% | 2026-10-21 | 2026-11-06 |  |  | 2026-08-25 | 2026-09-10 | 47 | 72 |  | Late start, Due this period, Pending update, No concern yet
STP-C1130 | Superstructure - RCC / steel erection | STP & Pump House | Construction | Not Started | 43 | 43 | 0% | 2026-11-07 | 2026-12-29 |  |  | 2026-09-11 | 2026-11-02 | 47 | 72
STP-C1140 | Roofing & cladding | STP & Pump House | Construction | Not Started | 20 | 20 | 0% | 2026-12-23 | 2027-01-15 |  |  | 2026-10-28 | 2026-11-20 | 47 | 72
STP-C1170 | Finishes - flooring & painting | STP & Pump House | Construction | Not Started | 30 | 30 | 0% | 2027-01-16 | 2027-02-20 |  |  | 2026-11-21 | 2026-12-26 | 47 | 72
STP-C1180 | Testing & commissioning | STP & Pump House | Construction | Not Started | 13 | 13 | 0% | 2027-02-18 | 2027-03-04 |  |  | 2027-01-05 | 2027-01-19 | 37 | 62
STP-C1190 | Building handover to client | STP & Pump House | Construction | Not Started | 0 | 0 | 0% | 2027-03-04 | 2027-03-04 |  |  | 2027-01-19 | 2027-01-19 | 37 | 62

## Gantt
Gantt chart - weekly timescale (dark = actual, blue = remaining, red = critical, ◆ = milestone, red line = Data Date)
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
[5 empty] | Jan-26 |  |  |  | Feb-26 |  |  |  | Mar-26 |  |  |  |  | Apr-26 |  |  |  | May-26 |  |  |  | Jun-26 |  |  |  |  | Jul-26 |  |  |  | Aug-26 |  |  |  |  | Sep-26 |  |  |  | Oct-26 |  |  |  | Nov-26 |  |  |  |  | Dec-26 |  |  |  | Jan-27 |  |  |  | Feb-27 |  |  |  | Mar-27 |  |  |  |  | Apr-27 |  |  |  | May-27
Activity ID | Activity Name | Start | Finish | % | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24
| Industrial Plant Expansion - Phase 2 (Demo) | 2026-01-05 | 2027-05-17 | 57.34%
| Project Milestones | 2026-01-05 | 2027-05-17 | 0%
MS-1000 | Notice to proceed / Project start | 2026-01-05 | 2026-01-05 | 100% | ◆
MS-9000 | Plant mechanical completion | 2027-05-17 | 2027-05-17 | 0% | [71 empty] | ◆
| Admin Building | 2026-01-08 | 2026-11-10 | 91.99%
| Engineering | 2026-01-08 | 2026-04-14 | 100%
ADM-E1010 | Design basis & architectural layout | 2026-01-08 | 2026-02-10 | 100%
ADM-E1020 | Structural design & IFC drawings | 2026-01-21 | 2026-03-20 | 100%
ADM-E1030 | MEP design & drawings | 2026-02-17 | 2026-04-14 | 100%
ADM-E1040 | Drawing approval by client | 2026-03-24 | 2026-04-14 | 100%
| Procurement | 2026-03-25 | 2026-07-31 | 100%
ADM-P1050 | Structural steel - PO placement | 2026-03-25 | 2026-04-07 | 100%
ADM-P1060 | Structural steel - fabrication & supply to site | 2026-04-13 | 2026-07-01 | 100%
ADM-P1070 | MEP equipment - PO placement | 2026-04-15 | 2026-04-28 | 100%
ADM-P1080 | MEP equipment - manufacturing & delivery | 2026-05-04 | 2026-07-31 | 100%
| Construction | 2026-01-08 | 2026-11-10 | 84.95%
ADM-C1090 | Site mobilisation & survey | 2026-01-08 | 2026-01-14 | 100%
ADM-C1100 | Excavation | 2026-02-04 | 2026-02-26 | 100%
ADM-C1110 | PCC & foundation concreting | 2026-02-14 | 2026-03-26 | 100%
ADM-C1120 | Plinth beam & backfilling | 2026-03-28 | 2026-04-23 | 100%
ADM-C1130 | Superstructure - RCC / steel erection | 2026-05-01 | 2026-07-13 | 100%
ADM-C1150 | Masonry & plastering | 2026-05-29 | 2026-07-11 | 100%
ADM-C1140 | Roofing & cladding | 2026-07-13 | 2026-08-03 | 100%
ADM-C1160 | MEP installation | 2026-08-04 | 2026-10-23 | 62%
ADM-C1170 | Finishes - flooring & painting | 2026-08-05 | 2026-10-14 | 73%
ADM-C1180 | Testing & commissioning | 2026-10-24 | 2026-11-10 | 0%
ADM-C1190 | Building handover to client | 2026-11-10 | 2026-11-10 | 0% | [44 empty] | ◆
| Main Process Building | 2026-01-24 | 2027-05-17 | 57.82%
| Engineering | 2026-01-30 | 2026-07-15 | 100%
MPB-E1010 | Design basis & architectural layout | 2026-01-30 | 2026-03-20 | 100%
MPB-E1020 | Structural design & IFC drawings | 2026-02-11 | 2026-05-04 | 100%
MPB-E1030 | MEP design & drawings | 2026-03-30 | 2026-07-15 | 100%
MPB-E1040 | Drawing approval by client | 2026-05-22 | 2026-07-15 | 100%
| Procurement | 2026-05-11 | 2027-01-19 | 59.42%
MPB-P1050 | Structural steel - PO placement | 2026-05-11 | 2026-06-09 | 100%
MPB-P1060 | Structural steel - fabrication & supply to site | 2026-06-15 | 2026-10-23 | 82%
MPB-P1070 | MEP equipment - PO placement | 2026-07-20 | 2026-08-13 | 100%
MPB-P1080 | MEP equipment - manufacturing & delivery | 2026-08-18 | 2027-01-19 | 27%
| Construction | 2026-01-24 | 2027-05-17 | 41.88%
MPB-C1090 | Site mobilisation & survey | 2026-01-24 | 2026-02-06 | 100%
MPB-C1100 | Excavation | 2026-02-28 | 2026-04-09 | 100%
MPB-C1110 | PCC & foundation concreting | 2026-03-18 | 2026-05-12 | 100%
MPB-C1120 | Plinth beam & backfilling | 2026-05-22 | 2026-06-26 | 100%
MPB-C1130 | Superstructure - RCC / steel erection | 2026-07-08 | 2026-11-30 | 52%
MPB-C1150 | Masonry & plastering | 2026-08-06 | 2026-11-13 | 49%
MPB-C1140 | Roofing & cladding | 2026-11-25 | 2027-01-09 | 0%
MPB-C1170 | Finishes - flooring & painting | 2027-01-11 | 2027-03-19 | 0%
MPB-C1160 | MEP installation | 2027-01-20 | 2027-04-22 | 0%
MPB-C1180 | Testing & commissioning | 2027-04-23 | 2027-05-17 | 0%
MPB-C1190 | Building handover to client | 2027-05-17 | 2027-05-17 | 0% | [71 empty] | ◆
| Warehouse Block | 2026-02-27 | 2027-02-15 | 68.54%
| Engineering | 2026-03-06 | 2026-06-11 | 100%
WHS-E1010 | Design basis & architectural layout | 2026-03-06 | 2026-04-08 | 100%
WHS-E1020 | Structural design & IFC drawings | 2026-03-18 | 2026-05-06 | 100%
WHS-E1030 | MEP design & drawings | 2026-04-15 | 2026-06-11 | 100%
WHS-E1040 | Drawing approval by client | 2026-05-15 | 2026-06-11 | 100%
| Procurement | 2026-05-07 | 2026-11-10 | 81.66%
WHS-P1050 | Structural steel - PO placement | 2026-05-07 | 2026-05-21 | 100%
WHS-P1060 | Structural steel - fabrication & supply to site | 2026-05-28 | 2026-08-05 | 100%
WHS-P1070 | MEP equipment - PO placement | 2026-06-13 | 2026-07-08 | 100%
WHS-P1080 | MEP equipment - manufacturing & delivery | 2026-07-09 | 2026-11-10 | 62%
| Construction | 2026-02-27 | 2027-02-15 | 52.29%
WHS-C1090 | Site mobilisation & survey | 2026-02-27 | 2026-03-09 | 100%
WHS-C1100 | Excavation | 2026-03-30 | 2026-04-24 | 100%
WHS-C1110 | PCC & foundation concreting | 2026-04-13 | 2026-05-25 | 100%
WHS-C1120 | Plinth beam & backfilling | 2026-05-28 | 2026-06-22 | 100%
WHS-C1130 | Superstructure - RCC / steel erection | 2026-06-24 | 2026-10-01 | 99%
WHS-C1150 | Masonry & plastering | 2026-07-23 | 2026-10-12 | 77%
WHS-C1140 | Roofing & cladding | 2026-10-01 | 2026-11-10 | 0%
WHS-C1160 | MEP installation | 2026-11-11 | 2027-01-23 | 0%
WHS-C1170 | Finishes - flooring & painting | 2026-11-11 | 2026-12-30 | 0%
WHS-C1180 | Testing & commissioning | 2027-01-25 | 2027-02-15 | 0%
WHS-C1190 | Building handover to client | 2027-02-15 | 2027-02-15 | 0% | [58 empty] | ◆
| 33kV Substation | 2026-03-27 | 2027-01-22 | 57.49%
| Engineering | 2026-04-10 | 2026-07-07 | 100%
SUB-E1010 | Design basis & architectural layout | 2026-04-10 | 2026-05-13 | 100%
SUB-E1020 | Structural design & IFC drawings | 2026-04-27 | 2026-06-01 | 100%
SUB-E1030 | MEP design & drawings | 2026-05-22 | 2026-07-07 | 100%
SUB-E1040 | Drawing approval by client | 2026-06-12 | 2026-07-07 | 100%
| Procurement | 2026-06-10 | 2026-11-10 | 77.84%
SUB-P1050 | Structural steel - PO placement | 2026-06-10 | 2026-06-23 | 100%
SUB-P1060 | Structural steel - fabrication & supply to site | 2026-07-01 | 2026-10-01 | 98%
SUB-P1070 | MEP equipment - PO placement | 2026-07-14 | 2026-07-29 | 100%
SUB-P1080 | MEP equipment - manufacturing & delivery | 2026-08-07 | 2026-11-10 | 49%
| Construction | 2026-03-27 | 2027-01-22 | 32.52%
SUB-C1090 | Site mobilisation & survey | 2026-03-27 | 2026-04-01 | 100%
SUB-C1100 | Excavation | 2026-05-15 | 2026-06-09 | 100%
SUB-C1110 | PCC & foundation concreting | 2026-06-03 | 2026-07-09 | 100%
SUB-C1120 | Plinth beam & backfilling | 2026-07-21 | 2026-08-08 | 100%
SUB-C1130 | Superstructure - RCC / steel erection | 2026-08-19 | 2026-11-07 | 41%
SUB-C1150 | Masonry & plastering | 2026-10-01 | 2026-11-10 | 0%
SUB-C1140 | Roofing & cladding | 2026-11-03 | 2026-11-30 | 0%
SUB-C1160 | MEP installation | 2026-11-11 | 2027-01-06 | 0%
SUB-C1170 | Finishes - flooring & painting | 2026-12-01 | 2027-01-16 | 0%
SUB-C1180 | Testing & commissioning | 2027-01-07 | 2027-01-22 | 0%
SUB-C1190 | Building handover to client | 2027-01-22 | 2027-01-22 | 0% | [54 empty] | ◆
| Utility Building | 2026-04-25 | 2027-05-04 | 36.58%
| Engineering | 2026-05-14 | 2026-08-12 | 100%
UTL-E1010 | Design basis & architectural layout | 2026-05-14 | 2026-06-15 | 100%
UTL-E1020 | Structural design & IFC drawings | 2026-05-22 | 2026-07-16 | 100%
UTL-E1030 | MEP design & drawings | 2026-06-24 | 2026-08-12 | 100%
UTL-E1040 | Drawing approval by client | 2026-07-28 | 2026-08-12 | 100%
| Procurement | 2026-07-17 | 2027-02-05 | 21.17%
UTL-P1050 | Structural steel - PO placement | 2026-07-17 | 2026-08-03 | 100%
UTL-P1060 | Structural steel - fabrication & supply to site | 2026-08-04 | 2026-12-05 | 29%
UTL-P1070 | MEP equipment - PO placement | 2026-08-20 | 2026-10-15 | 44%
UTL-P1080 | MEP equipment - manufacturing & delivery | 2026-10-16 | 2027-02-05 | 0%
| Construction | 2026-04-25 | 2027-05-04 | 24.33%
UTL-C1090 | Site mobilisation & survey | 2026-04-25 | 2026-05-02 | 100%
UTL-C1100 | Excavation | 2026-06-04 | 2026-07-01 | 100%
UTL-C1110 | PCC & foundation concreting | 2026-06-16 | 2026-07-27 | 100%
UTL-C1120 | Plinth beam & backfilling | 2026-08-03 | 2026-08-27 | 100%
UTL-C1130 | Superstructure - RCC / steel erection | 2026-10-01 | 2026-12-23 | 0%
UTL-C1150 | Masonry & plastering | 2026-10-27 | 2026-12-21 | 0%
UTL-C1140 | Roofing & cladding | 2026-12-18 | 2027-01-21 | 0%
UTL-C1170 | Finishes - flooring & painting | 2027-01-22 | 2027-03-05 | 0%
UTL-C1160 | MEP installation | 2027-02-06 | 2027-04-16 | 0%
UTL-C1180 | Testing & commissioning | 2027-04-17 | 2027-05-04 | 0%
UTL-C1190 | Building handover to client | 2027-05-04 | 2027-05-04 | 0% | [69 empty] | ◆
| STP & Pump House | 2026-05-29 | 2027-03-04 | 27.41%
| Engineering | 2026-07-02 | 2026-10-09 | 93.03%
STP-E1010 | Design basis & architectural layout | 2026-07-02 | 2026-07-23 | 100%
STP-E1020 | Structural design & IFC drawings | 2026-07-10 | 2026-08-11 | 100%
STP-E1030 | MEP design & drawings | 2026-07-29 | 2026-10-09 | 84%
STP-E1040 | Drawing approval by client | 2026-08-12 | 2026-10-09 | 95%
| Procurement | 2026-08-14 | 2026-12-30 | 9.483%
STP-P1050 | Structural steel - PO placement | 2026-08-14 | 2026-08-25 | 100%
STP-P1060 | Structural steel - fabrication & supply to site | 2026-08-29 | 2026-11-21 | 5%
STP-P1070 | MEP equipment - PO placement | 2026-10-10 | 2026-10-23 | 0%
STP-P1080 | MEP equipment - manufacturing & delivery | 2026-10-24 | 2026-12-30 | 0%
| Construction | 2026-05-29 | 2027-03-04 | 16.34%
STP-C1090 | Site mobilisation & survey | 2026-05-29 | 2026-06-03 | 100%
STP-C1100 | Excavation | 2026-07-24 | 2026-08-10 | 100%
STP-C1110 | PCC & foundation concreting | 2026-08-06 | 2026-10-19 | 58%
STP-C1150 | Masonry & plastering | 2026-08-26 | 2027-01-07 | 5%
STP-C1160 | MEP installation | 2026-08-26 | 2027-02-17 | 5%
STP-C1120 | Plinth beam & backfilling | 2026-10-21 | 2026-11-06 | 0%
STP-C1130 | Superstructure - RCC / steel erection | 2026-11-07 | 2026-12-29 | 0%
STP-C1140 | Roofing & cladding | 2026-12-23 | 2027-01-15 | 0%
STP-C1170 | Finishes - flooring & painting | 2027-01-16 | 2027-02-20 | 0%
STP-C1180 | Testing & commissioning | 2027-02-18 | 2027-03-04 | 0%
STP-C1190 | Building handover to client | 2027-03-04 | 2027-03-04 | 0% | [60 empty] | ◆

## Update Sheet
UPDATE SHEET - fill the orange columns, then File > Import Update Sheet in Schedule Engine
Data Date 01-Oct-2026: actual dates must be BEFORE 01-Oct-2026. % is 0-100. Leave a cell blank to keep the current value. Qty % = Done ÷ Scope (use it to decide the % complete).
Activity ID | Activity Name | Building | EPC | Status | Flags | Planned Start | Planned Finish | Current Actual Start | Current Actual Finish | Current % | Current Rem Dur | New Actual Start | New Actual Finish | New % Complete | New Remaining Dur | Expected Finish | Unit | Scope Qty | Done Qty | Qty % | Remarks | Check
MS-9000 | Plant mechanical completion | Project Milestones | Others | Not Started | Critical | 2027-05-31 | 2027-05-31 |  |  | 0% | 0
ADM-C1160 | MEP installation | Admin Building | Construction | In Progress | In progress | 2026-08-04 | 2026-10-03 | 2026-08-04 |  | 62% | 18 | [5 empty] | Nos | 288 | 121
ADM-C1170 | Finishes - flooring & painting | Admin Building | Construction | In Progress | Overdue, Due this period, In progress, No concern yet | 2026-08-05 | 2026-09-28 | 2026-08-05 |  | 73% | 11
ADM-C1180 | Testing & commissioning | Admin Building | Construction | Not Started |  | 2026-10-05 | 2026-10-21 |  |  | 0% | 14
ADM-C1190 | Building handover to client | Admin Building | Construction | Not Started |  | 2026-10-21 | 2026-10-21 |  |  | 0% | 0
MPB-P1060 | Structural steel - fabrication & supply to site | Main Process Building | Procurement | In Progress | In progress | 2026-06-15 | 2026-10-24 | 2026-06-15 |  | 82% | 18 | [5 empty] | MT | 840 | 521
MPB-C1130 | Superstructure - RCC / steel erection | Main Process Building | Construction | In Progress | In progress | 2026-07-08 | 2026-12-15 | 2026-07-08 |  | 52% | 49 | [5 empty] | MT | 840 | 269
MPB-C1150 | Masonry & plastering | Main Process Building | Construction | In Progress | In progress | 2026-08-06 | 2026-10-29 | 2026-08-06 |  | 49% | 35
MPB-P1080 | MEP equipment - manufacturing & delivery | Main Process Building | Procurement | In Progress | In progress, Critical | 2026-08-18 | 2027-02-03 | 2026-08-18 |  | 27% | 91
MPB-C1140 | Roofing & cladding | Main Process Building | Construction | Not Started |  | 2026-12-10 | 2027-01-25 |  |  | 0% | 39
MPB-C1170 | Finishes - flooring & painting | Main Process Building | Construction | Not Started |  | 2027-01-27 | 2027-04-05 |  |  | 0% | 58
MPB-C1160 | MEP installation | Main Process Building | Construction | Not Started | Critical | 2027-02-04 | 2027-05-06 |  |  | 0% | 78 | [5 empty] | Nos | 468 | 0
MPB-C1180 | Testing & commissioning | Main Process Building | Construction | Not Started | Critical | 2027-05-07 | 2027-05-31 |  |  | 0% | 21
MPB-C1190 | Building handover to client | Main Process Building | Construction | Not Started | Critical | 2027-05-31 | 2027-05-31 |  |  | 0% | 0
WHS-C1130 | Superstructure - RCC / steel erection | Warehouse Block | Construction | In Progress | Overdue, Due this period, In progress, No concern yet | 2026-06-24 | 2026-09-10 | 2026-06-24 |  | 99% | 1 | [5 empty] | MT | 590 | 525
WHS-P1080 | MEP equipment - manufacturing & delivery | Warehouse Block | Procurement | In Progress | In progress | 2026-07-09 | 2026-10-30 | 2026-07-09 |  | 62% | 32
WHS-C1150 | Masonry & plastering | Warehouse Block | Construction | In Progress | Overdue, Due this period, In progress, No concern yet | 2026-07-23 | 2026-09-22 | 2026-07-23 |  | 77% | 9
WHS-C1140 | Roofing & cladding | Warehouse Block | Construction | Not Started | Late start, Due this period, Pending update, No concern yet | 2026-09-05 | 2026-10-13 |  |  | 0% | 32
WHS-C1160 | MEP installation | Warehouse Block | Construction | Not Started |  | 2026-10-31 | 2027-01-14 |  |  | 0% | 63 | [5 empty] | Nos | 378 | 0
WHS-C1170 | Finishes - flooring & painting | Warehouse Block | Construction | Not Started |  | 2026-10-14 | 2026-12-03 |  |  | 0% | 42
WHS-C1180 | Testing & commissioning | Warehouse Block | Construction | Not Started |  | 2027-01-15 | 2027-02-05 |  |  | 0% | 18
WHS-C1190 | Building handover to client | Warehouse Block | Construction | Not Started |  | 2027-02-05 | 2027-02-05 |  |  | 0% | 0
SUB-P1060 | Structural steel - fabrication & supply to site | 33kV Substation | Procurement | In Progress | Overdue, Due this period, In progress, No concern yet | 2026-07-01 | 2026-09-17 | 2026-07-01 |  | 98% | 1 | [5 empty] | MT | 500 | 390
SUB-P1080 | MEP equipment - manufacturing & delivery | 33kV Substation | Procurement | In Progress | In progress | 2026-08-07 | 2026-10-31 | 2026-08-07 |  | 49% | 32
SUB-C1130 | Superstructure - RCC / steel erection | 33kV Substation | Construction | In Progress | In progress | 2026-08-19 | 2026-10-24 | 2026-08-19 |  | 41% | 31 | [5 empty] | MT | 500 | 105
SUB-C1150 | Masonry & plastering | 33kV Substation | Construction | Not Started | Late start, Due this period, Pending update, No concern yet | 2026-09-11 | 2026-10-19 |  |  | 0% | 32
SUB-C1140 | Roofing & cladding | 33kV Substation | Construction | Not Started |  | 2026-10-19 | 2026-11-16 |  |  | 0% | 23
SUB-C1160 | MEP installation | 33kV Substation | Construction | Not Started |  | 2026-11-02 | 2026-12-29 |  |  | 0% | 48 | [5 empty] | Nos | 288 | 0
SUB-C1170 | Finishes - flooring & painting | 33kV Substation | Construction | Not Started |  | 2026-11-17 | 2027-01-02 |  |  | 0% | 40
SUB-C1180 | Testing & commissioning | 33kV Substation | Construction | Not Started |  | 2026-12-30 | 2027-01-14 |  |  | 0% | 14
SUB-C1190 | Building handover to client | 33kV Substation | Construction | Not Started |  | 2027-01-14 | 2027-01-14 |  |  | 0% | 0
UTL-P1060 | Structural steel - fabrication & supply to site | Utility Building | Procurement | In Progress | In progress, Pending update | 2026-08-04 | 2026-11-04 | 2026-08-04 |  | 29% | 54 | [5 empty] | MT | 590 | 171
UTL-P1070 | MEP equipment - PO placement | Utility Building | Procurement | In Progress | Overdue, Due this period, In progress, Pending update, No concern yet | 2026-08-20 | 2026-09-14 | 2026-08-20 |  | 44% | 12
UTL-C1130 | Superstructure - RCC / steel erection | Utility Building | Construction | Not Started | Late start, Due this period, Pending update, No concern yet | 2026-09-01 | 2026-11-23 |  |  | 0% | 69 | [5 empty] | MT | 590 | 0
UTL-P1080 | MEP equipment - manufacturing & delivery | Utility Building | Procurement | Not Started | Late start, Due this period, Pending update, No concern yet | 2026-09-15 | 2027-01-05 |  |  | 0% | 93
UTL-C1150 | Masonry & plastering | Utility Building | Construction | Not Started | Late start, Due this period, Pending update, No concern yet | 2026-09-24 | 2026-11-20 |  |  | 0% | 47
UTL-C1140 | Roofing & cladding | Utility Building | Construction | Not Started |  | 2026-11-18 | 2026-12-21 |  |  | 0% | 29
UTL-C1170 | Finishes - flooring & painting | Utility Building | Construction | Not Started |  | 2026-12-22 | 2027-02-03 |  |  | 0% | 36
UTL-C1160 | MEP installation | Utility Building | Construction | Not Started |  | 2027-01-06 | 2027-03-16 |  |  | 0% | 59 | [5 empty] | Nos | 354 | 0
UTL-C1180 | Testing & commissioning | Utility Building | Construction | Not Started |  | 2027-03-17 | 2027-04-03 |  |  | 0% | 15
UTL-C1190 | Building handover to client | Utility Building | Construction | Not Started |  | 2027-04-03 | 2027-04-03 |  |  | 0% | 0
STP-E1030 | MEP design & drawings | STP & Pump House | Engineering | In Progress | Overdue, Due this period, In progress, Pending update, No concern yet | 2026-07-29 | 2026-09-08 | 2026-07-29 |  | 84% | 6
STP-C1110 | PCC & foundation concreting | STP & Pump House | Construction | In Progress | Overdue, Due this period, In progress, Pending update, No concern yet | 2026-08-06 | 2026-09-17 | 2026-08-06 |  | 58% | 15 | [5 empty] | Cum | 1120 | 650
STP-E1040 | Drawing approval by client | STP & Pump House | Engineering | In Progress | Overdue, Due this period, In progress, Pending update, No concern yet | 2026-08-12 | 2026-09-08 | 2026-08-12 |  | 95% | 1
STP-C1150 | Masonry & plastering | STP & Pump House | Construction | In Progress | Future progress, In progress, Pending update, Out of sequence, No concern yet | 2026-08-26 | 2026-12-07 | 2026-08-26 |  | 5% | 31
STP-C1160 | MEP installation | STP & Pump House | Construction | In Progress | Future progress, In progress, Pending update, Out of sequence, No concern yet | 2026-08-26 | 2027-01-16 | 2026-08-26 |  | 5% | 41 | [5 empty] | Nos | 258 | 0
STP-P1060 | Structural steel - fabrication & supply to site | STP & Pump House | Procurement | In Progress | In progress, Pending update | 2026-08-29 | 2026-10-21 | 2026-08-29 |  | 5% | 42 | [5 empty] | MT | 420 | 21
STP-P1070 | MEP equipment - PO placement | STP & Pump House | Procurement | Not Started | Late start, Overdue, Due this period, Pending update, No concern yet | 2026-09-09 | 2026-09-21 |  |  | 0% | 11
STP-C1120 | Plinth beam & backfilling | STP & Pump House | Construction | Not Started | Late start, Due this period, Pending update, No concern yet | 2026-09-18 | 2026-10-06 |  |  | 0% | 15
STP-P1080 | MEP equipment - manufacturing & delivery | STP & Pump House | Procurement | Not Started | Late start, Due this period, Pending update, No concern yet | 2026-09-22 | 2026-11-28 |  |  | 0% | 56
STP-C1130 | Superstructure - RCC / steel erection | STP & Pump House | Construction | Not Started |  | 2026-10-07 | 2026-11-27 |  |  | 0% | 43 | [5 empty] | MT | 420 | 0
STP-C1140 | Roofing & cladding | STP & Pump House | Construction | Not Started |  | 2026-11-23 | 2026-12-15 |  |  | 0% | 20
STP-C1170 | Finishes - flooring & painting | STP & Pump House | Construction | Not Started |  | 2026-12-16 | 2027-01-20 |  |  | 0% | 30
STP-C1180 | Testing & commissioning | STP & Pump House | Construction | Not Started |  | 2027-01-18 | 2027-02-02 |  |  | 0% | 13
STP-C1190 | Building handover to client | STP & Pump House | Construction | Not Started |  | 2027-02-02 | 2027-02-02 |  |  | 0% | 0

## Look-ahead
8-week look-ahead from 01-Oct-2026
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
Activity ID | Activity Name | Building | EPC | Status | Start | Finish | Rem Dur | % Complete | Total Float | Window
MPB-P1060 | Structural steel - fabrication & supply to site | Main Process Building | Procurement | In Progress | 2026-06-15 | 2026-10-23 | 18 | 82% | 34 | Ongoing
WHS-C1130 | Superstructure - RCC / steel erection | Warehouse Block | Construction | In Progress | 2026-06-24 | 2026-10-01 | 1 | 99% | 79 | Ongoing
SUB-P1060 | Structural steel - fabrication & supply to site | 33kV Substation | Procurement | In Progress | 2026-07-01 | 2026-10-01 | 1 | 98% | 83 | Ongoing
MPB-C1130 | Superstructure - RCC / steel erection | Main Process Building | Construction | In Progress | 2026-07-08 | 2026-11-30 | 49 | 52% | 49 | Ongoing
WHS-P1080 | MEP equipment - manufacturing & delivery | Warehouse Block | Procurement | In Progress | 2026-07-09 | 2026-11-10 | 32 | 62% | 77 | Ongoing
WHS-C1150 | Masonry & plastering | Warehouse Block | Construction | In Progress | 2026-07-23 | 2026-10-12 | 9 | 77% | 99 | Ongoing
STP-E1030 | MEP design & drawings | STP & Pump House | Engineering | In Progress | 2026-07-29 | 2026-10-09 | 6 | 84% | 51 | Ongoing
ADM-C1160 | MEP installation | Admin Building | Construction | In Progress | 2026-08-04 | 2026-10-23 | 18 | 62% | 158 | Ongoing
UTL-P1060 | Structural steel - fabrication & supply to site | Utility Building | Procurement | In Progress | 2026-08-04 | 2026-12-05 | 54 | 29% | 46 | Ongoing
ADM-C1170 | Finishes - flooring & painting | Admin Building | Construction | In Progress | 2026-08-05 | 2026-10-14 | 11 | 73% | 179 | Ongoing
MPB-C1150 | Masonry & plastering | Main Process Building | Construction | In Progress | 2026-08-06 | 2026-11-13 | 35 | 49% | 81 | Ongoing
STP-C1110 | PCC & foundation concreting | STP & Pump House | Construction | In Progress | 2026-08-06 | 2026-10-19 | 15 | 58% | 72 | Ongoing
SUB-P1080 | MEP equipment - manufacturing & delivery | 33kV Substation | Procurement | In Progress | 2026-08-07 | 2026-11-10 | 32 | 49% | 96 | Ongoing
STP-E1040 | Drawing approval by client | STP & Pump House | Engineering | In Progress | 2026-08-12 | 2026-10-09 | 1 | 95% | 151 | Ongoing
MPB-P1080 | MEP equipment - manufacturing & delivery | Main Process Building | Procurement | In Progress | 2026-08-18 | 2027-01-19 | 91 | 27% | 0 | Ongoing
SUB-C1130 | Superstructure - RCC / steel erection | 33kV Substation | Construction | In Progress | 2026-08-19 | 2026-11-07 | 31 | 41% | 98 | Ongoing
UTL-P1070 | MEP equipment - PO placement | Utility Building | Procurement | In Progress | 2026-08-20 | 2026-10-15 | 12 | 44% | 11 | Ongoing
STP-C1150 | Masonry & plastering | STP & Pump House | Construction | In Progress | 2026-08-26 | 2027-01-07 | 31 | 5% | 76 | Ongoing
STP-C1160 | MEP installation | STP & Pump House | Construction | In Progress | 2026-08-26 | 2027-02-17 | 41 | 5% | 62 | Ongoing
STP-P1060 | Structural steel - fabrication & supply to site | STP & Pump House | Procurement | In Progress | 2026-08-29 | 2026-11-21 | 42 | 5% | 87 | Ongoing
SUB-C1150 | Masonry & plastering | 33kV Substation | Construction | Not Started | 2026-10-01 | 2026-11-10 | 32 | 0% | 118 | 0-2 weeks
UTL-C1130 | Superstructure - RCC / steel erection | Utility Building | Construction | Not Started | 2026-10-01 | 2026-12-23 | 69 | 0% | 61 | 0-2 weeks
WHS-C1140 | Roofing & cladding | Warehouse Block | Construction | Not Started | 2026-10-01 | 2026-11-10 | 32 | 0% | 116 | 0-2 weeks
STP-P1070 | MEP equipment - PO placement | STP & Pump House | Procurement | Not Started | 2026-10-10 | 2026-10-23 | 11 | 0% | 62 | 0-2 weeks
UTL-P1080 | MEP equipment - manufacturing & delivery | Utility Building | Procurement | Not Started | 2026-10-16 | 2027-02-05 | 93 | 0% | 11 | 2-4 weeks
STP-C1120 | Plinth beam & backfilling | STP & Pump House | Construction | Not Started | 2026-10-21 | 2026-11-06 | 15 | 0% | 72 | 2-4 weeks
ADM-C1180 | Testing & commissioning | Admin Building | Construction | Not Started | 2026-10-24 | 2026-11-10 | 14 | 0% | 158 | 2-4 weeks
STP-P1080 | MEP equipment - manufacturing & delivery | STP & Pump House | Procurement | Not Started | 2026-10-24 | 2026-12-30 | 56 | 0% | 62 | 2-4 weeks
UTL-C1150 | Masonry & plastering | Utility Building | Construction | Not Started | 2026-10-27 | 2026-12-21 | 47 | 0% | 86 | 2-4 weeks
SUB-C1140 | Roofing & cladding | 33kV Substation | Construction | Not Started | 2026-11-03 | 2026-11-30 | 23 | 0% | 101 | 4-8 weeks
STP-C1130 | Superstructure - RCC / steel erection | STP & Pump House | Construction | Not Started | 2026-11-07 | 2026-12-29 | 43 | 0% | 72 | 4-8 weeks
ADM-C1190 | Building handover to client | Admin Building | Construction | Not Started | 2026-11-10 | 2026-11-10 | 0 | 0% | 158 | 4-8 weeks
SUB-C1160 | MEP installation | 33kV Substation | Construction | Not Started | 2026-11-11 | 2027-01-06 | 48 | 0% | 96 | 4-8 weeks
WHS-C1160 | MEP installation | Warehouse Block | Construction | Not Started | 2026-11-11 | 2027-01-23 | 63 | 0% | 77 | 4-8 weeks
WHS-C1170 | Finishes - flooring & painting | Warehouse Block | Construction | Not Started | 2026-11-11 | 2026-12-30 | 42 | 0% | 116 | 4-8 weeks
MPB-C1140 | Roofing & cladding | Main Process Building | Construction | Not Started | 2026-11-25 | 2027-01-09 | 39 | 0% | 49 | 4-8 weeks

## Attention
Activities needing attention (flag + concern raised)
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
Flag | Activity ID | Activity Name | Building | EPC | Status | Ref Start | Ref Finish | Start | Finish | % | TF | Concern category | Concern | Action | Owner
Overdue | ADM-C1170 | Finishes - flooring & painting | Admin Building | Construction | In Progress | 2026-08-05 | 2026-09-28 | 2026-08-05 | 2026-10-14 | 73% | 179 |  | NOT RAISED
Overdue | WHS-C1130 | Superstructure - RCC / steel erection | Warehouse Block | Construction | In Progress | 2026-06-24 | 2026-09-10 | 2026-06-24 | 2026-10-01 | 99% | 79 |  | NOT RAISED
Late start | WHS-C1140 | Roofing & cladding | Warehouse Block | Construction | Not Started | 2026-09-05 | 2026-10-13 | 2026-10-01 | 2026-11-10 | 0% | 116 |  | NOT RAISED
Overdue | WHS-C1150 | Masonry & plastering | Warehouse Block | Construction | In Progress | 2026-07-23 | 2026-09-22 | 2026-07-23 | 2026-10-12 | 77% | 99 |  | NOT RAISED
Overdue | SUB-P1060 | Structural steel - fabrication & supply to site | 33kV Substation | Procurement | In Progress | 2026-07-01 | 2026-09-17 | 2026-07-01 | 2026-10-01 | 98% | 83 |  | NOT RAISED
Late start | SUB-C1150 | Masonry & plastering | 33kV Substation | Construction | Not Started | 2026-09-11 | 2026-10-19 | 2026-10-01 | 2026-11-10 | 0% | 118 |  | NOT RAISED
Overdue | UTL-P1070 | MEP equipment - PO placement | Utility Building | Procurement | In Progress | 2026-08-20 | 2026-09-14 | 2026-08-20 | 2026-10-15 | 44% | 11 |  | NOT RAISED
Late start | UTL-P1080 | MEP equipment - manufacturing & delivery | Utility Building | Procurement | Not Started | 2026-09-15 | 2027-01-05 | 2026-10-16 | 2027-02-05 | 0% | 11 |  | NOT RAISED
Late start | UTL-C1130 | Superstructure - RCC / steel erection | Utility Building | Construction | Not Started | 2026-09-01 | 2026-11-23 | 2026-10-01 | 2026-12-23 | 0% | 61 |  | NOT RAISED
Late start | UTL-C1150 | Masonry & plastering | Utility Building | Construction | Not Started | 2026-09-24 | 2026-11-20 | 2026-10-27 | 2026-12-21 | 0% | 86 |  | NOT RAISED
Overdue | STP-E1030 | MEP design & drawings | STP & Pump House | Engineering | In Progress | 2026-07-29 | 2026-09-08 | 2026-07-29 | 2026-10-09 | 84% | 51 |  | NOT RAISED
Overdue | STP-E1040 | Drawing approval by client | STP & Pump House | Engineering | In Progress | 2026-08-12 | 2026-09-08 | 2026-08-12 | 2026-10-09 | 95% | 151 |  | NOT RAISED
Overdue | STP-P1070 | MEP equipment - PO placement | STP & Pump House | Procurement | Not Started | 2026-09-09 | 2026-09-21 | 2026-10-10 | 2026-10-23 | 0% | 62 |  | NOT RAISED
Late start | STP-P1070 | MEP equipment - PO placement | STP & Pump House | Procurement | Not Started | 2026-09-09 | 2026-09-21 | 2026-10-10 | 2026-10-23 | 0% | 62 |  | NOT RAISED
Late start | STP-P1080 | MEP equipment - manufacturing & delivery | STP & Pump House | Procurement | Not Started | 2026-09-22 | 2026-11-28 | 2026-10-24 | 2026-12-30 | 0% | 62 |  | NOT RAISED
Overdue | STP-C1110 | PCC & foundation concreting | STP & Pump House | Construction | In Progress | 2026-08-06 | 2026-09-17 | 2026-08-06 | 2026-10-19 | 58% | 72 |  | NOT RAISED
Late start | STP-C1120 | Plinth beam & backfilling | STP & Pump House | Construction | Not Started | 2026-09-18 | 2026-10-06 | 2026-10-21 | 2026-11-06 | 0% | 72 |  | NOT RAISED
Future progress | STP-C1150 | Masonry & plastering | STP & Pump House | Construction | In Progress | 2026-08-26 | 2026-12-07 | 2026-08-26 | 2027-01-07 | 5% | 76 |  | NOT RAISED
Out of sequence | STP-C1150 | Masonry & plastering | STP & Pump House | Construction | In Progress | 2026-08-26 | 2026-12-07 | 2026-08-26 | 2027-01-07 | 5% | 76 |  | NOT RAISED
Future progress | STP-C1160 | MEP installation | STP & Pump House | Construction | In Progress | 2026-08-26 | 2027-01-16 | 2026-08-26 | 2027-02-17 | 5% | 62 |  | NOT RAISED
Out of sequence | STP-C1160 | MEP installation | STP & Pump House | Construction | In Progress | 2026-08-26 | 2027-01-16 | 2026-08-26 | 2027-02-17 | 5% | 62 |  | NOT RAISED

## Concerns
Concerns register - 0 concerns as of 01-Oct-2026
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
Building | EPC | Activity ID | Activity Name | Flags | Category | Concern | Action | Owner | Target date | Raised | Finish | TF

## Health Check
Schedule health check - score 46%
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
Check | Result | Count | Of | % | Guideline
Missing logic (open ends) | PASS | 0 | 55 | 0 | Activities without a predecessor or a successor (first/last milestones excepted). Target ≤ 5%.
Leads (negative lags) | FAIL | 6 | 156 | 3.8 | Relationships with a negative lag hide logic. Target 0.
Positive lags | FAIL | 46 | 156 | 29.5 | Lags should be replaced with activities where possible. Target ≤ 5%.
Relationship types (FS ≥ 90%) | FAIL | 48 | 156 | 69.2 | Finish-to-Start should dominate. Shows the share of FS links.
Hard constraints | PASS | 0 | 55 | 0 | Must/finish-on or before constraints block logic. Target ≤ 5%.
High float (> 44 days) | FAIL | 44 | 55 | 80 | Usually means missing successors. Target ≤ 5%.
Negative float | PASS | 0 | 55 | 0 | Project is late against a constraint / must-finish date. Target 0.
High duration (> 44 days) | FAIL | 20 | 55 | 36.4 | Break long activities down for better control. Target ≤ 5%.
Invalid dates | PASS | 0 | 116 | 0 | Actuals after the Data Date or forecasts before it. Target 0.
Missed activities (finished late vs baseline) | FAIL | 82 | 84 | 97.6 | Planned to finish by the Data Date but finished late or not at all. Target ≤ 5%.
Critical path exists | PASS | 5 | 55 | 9.1 | A continuous critical path should drive the finish.
Baseline Execution Index (BEI ≥ 0.95) | FAIL | 61 | 84 | 72.6 | Activities completed ÷ activities that should have been completed. 0.73
Logic loops | PASS | 0 | 116 | 0 | No circular logic.

## Change Log
Changes vs previous update (01-Sep-2026 → 01-Oct-2026)
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
Activity ID | Activity Name | Building | Changes this period | Finish movement (d)
MS-9000 | Plant mechanical completion | Project Milestones |  | -12
ADM-C1160 | MEP installation | Admin Building | % 42 → 62 | 16
ADM-C1170 | Finishes - flooring & painting | Admin Building | % 53 → 73 | 13
ADM-C1180 | Testing & commissioning | Admin Building |  | 16
ADM-C1190 | Building handover to client | Admin Building |  | 16
MPB-P1060 | Structural steel - fabrication & supply to site | Main Process Building | % 62 → 82 | -1
MPB-P1080 | MEP equipment - manufacturing & delivery | Main Process Building | % 7 → 27 | -12
MPB-C1130 | Superstructure - RCC / steel erection | Main Process Building | % 32 → 52 | -13
MPB-C1140 | Roofing & cladding | Main Process Building |  | -13
MPB-C1150 | Masonry & plastering | Main Process Building | % 29 → 49 | 12
MPB-C1160 | MEP installation | Main Process Building |  | -12
MPB-C1170 | Finishes - flooring & painting | Main Process Building |  | -13
MPB-C1180 | Testing & commissioning | Main Process Building |  | -12
MPB-C1190 | Building handover to client | Main Process Building |  | -12
WHS-P1080 | MEP equipment - manufacturing & delivery | Warehouse Block | % 42 → 62 | 8
WHS-C1130 | Superstructure - RCC / steel erection | Warehouse Block | % 89 → 99 | 18
WHS-C1140 | Roofing & cladding | Warehouse Block |  | 22
WHS-C1150 | Masonry & plastering | Warehouse Block | % 57 → 77 | 16
WHS-C1160 | MEP installation | Warehouse Block |  | 8
WHS-C1170 | Finishes - flooring & painting | Warehouse Block |  | 22
WHS-C1180 | Testing & commissioning | Warehouse Block |  | 8
WHS-C1190 | Building handover to client | Warehouse Block |  | 8
SUB-P1060 | Structural steel - fabrication & supply to site | 33kV Substation | % 78 → 98 | 12
SUB-P1080 | MEP equipment - manufacturing & delivery | 33kV Substation | % 29 → 49 | 7
SUB-C1130 | Superstructure - RCC / steel erection | 33kV Substation | % 21 → 41 | 12
SUB-C1140 | Roofing & cladding | 33kV Substation |  | 12
SUB-C1150 | Masonry & plastering | 33kV Substation |  | 17
SUB-C1160 | MEP installation | 33kV Substation |  | 7
SUB-C1170 | Finishes - flooring & painting | 33kV Substation |  | 12
SUB-C1180 | Testing & commissioning | 33kV Substation |  | 7
SUB-C1190 | Building handover to client | 33kV Substation |  | 7
UTL-P1060 | Structural steel - fabrication & supply to site | Utility Building |  | 26
UTL-P1070 | MEP equipment - PO placement | Utility Building |  | 26
UTL-P1080 | MEP equipment - manufacturing & delivery | Utility Building |  | 26
UTL-C1130 | Superstructure - RCC / steel erection | Utility Building |  | 26
UTL-C1140 | Roofing & cladding | Utility Building |  | 26
UTL-C1150 | Masonry & plastering | Utility Building |  | 26
UTL-C1160 | MEP installation | Utility Building |  | 26
UTL-C1170 | Finishes - flooring & painting | Utility Building |  | 26
UTL-C1180 | Testing & commissioning | Utility Building |  | 26
UTL-C1190 | Building handover to client | Utility Building |  | 26
STP-E1030 | MEP design & drawings | STP & Pump House |  | 22
STP-E1040 | Drawing approval by client | STP & Pump House |  | 22
STP-P1060 | Structural steel - fabrication & supply to site | STP & Pump House |  | 26
STP-P1070 | MEP equipment - PO placement | STP & Pump House |  | 26
STP-P1080 | MEP equipment - manufacturing & delivery | STP & Pump House |  | 26
STP-C1110 | PCC & foundation concreting | STP & Pump House |  | 26
STP-C1120 | Plinth beam & backfilling | STP & Pump House |  | 26
STP-C1130 | Superstructure - RCC / steel erection | STP & Pump House |  | 26
STP-C1140 | Roofing & cladding | STP & Pump House |  | 26
STP-C1150 | Masonry & plastering | STP & Pump House |  | 26
STP-C1160 | MEP installation | STP & Pump House |  | 26
STP-C1170 | Finishes - flooring & painting | STP & Pump House |  | 26
STP-C1180 | Testing & commissioning | STP & Pump House |  | 26
STP-C1190 | Building handover to client | STP & Pump House |  | 26

## Relationships
Relationships
Industrial Plant Expansion - Phase 2 (Demo) ¦ Data Date: 01-Oct-2026 ¦ Generated 28/9/2026, 9:07:00 am by Schedule Engine
Predecessor | Predecessor Name | Type | Lag (d) | Successor | Successor Name
MS-1000 | Notice to proceed / Project start | FS | 0 | ADM-E1010 | Design basis & architectural layout
ADM-E1010 | Design basis & architectural layout | SS | 5 | ADM-E1020 | Structural design & IFC drawings
ADM-E1010 | Design basis & architectural layout | FS | 0 | ADM-E1030 | MEP design & drawings
ADM-E1020 | Structural design & IFC drawings | FS | 0 | ADM-E1040 | Drawing approval by client
ADM-E1030 | MEP design & drawings | FF | 0 | ADM-E1040 | Drawing approval by client
ADM-E1020 | Structural design & IFC drawings | FS | 0 | ADM-P1050 | Structural steel - PO placement
ADM-P1050 | Structural steel - PO placement | FS | 0 | ADM-P1060 | Structural steel - fabrication & supply to site
ADM-E1030 | MEP design & drawings | FS | 0 | ADM-P1070 | MEP equipment - PO placement
ADM-P1070 | MEP equipment - PO placement | FS | 0 | ADM-P1080 | MEP equipment - manufacturing & delivery
MS-1000 | Notice to proceed / Project start | FS | 0 | ADM-C1090 | Site mobilisation & survey
ADM-C1090 | Site mobilisation & survey | FS | 0 | ADM-C1100 | Excavation
ADM-E1020 | Structural design & IFC drawings | SS | 10 | ADM-C1100 | Excavation
ADM-C1100 | Excavation | SS | 7 | ADM-C1110 | PCC & foundation concreting
ADM-C1110 | PCC & foundation concreting | FS | 0 | ADM-C1120 | Plinth beam & backfilling
ADM-C1120 | Plinth beam & backfilling | FS | 0 | ADM-C1130 | Superstructure - RCC / steel erection
ADM-P1060 | Structural steel - fabrication & supply to site | SS | 15 | ADM-C1130 | Superstructure - RCC / steel erection
ADM-C1130 | Superstructure - RCC / steel erection | FS | -5 | ADM-C1140 | Roofing & cladding
ADM-C1130 | Superstructure - RCC / steel erection | SS | 20 | ADM-C1150 | Masonry & plastering
ADM-C1150 | Masonry & plastering | SS | 10 | ADM-C1160 | MEP installation
ADM-P1080 | MEP equipment - manufacturing & delivery | FS | 0 | ADM-C1160 | MEP installation
ADM-C1150 | Masonry & plastering | FS | 0 | ADM-C1170 | Finishes - flooring & painting
ADM-C1140 | Roofing & cladding | FS | 0 | ADM-C1170 | Finishes - flooring & painting
ADM-C1160 | MEP installation | FS | 0 | ADM-C1180 | Testing & commissioning
ADM-C1170 | Finishes - flooring & painting | FF | 0 | ADM-C1180 | Testing & commissioning
ADM-C1180 | Testing & commissioning | FS | 0 | ADM-C1190 | Building handover to client
ADM-C1190 | Building handover to client | FS | 0 | MS-9000 | Plant mechanical completion
MS-1000 | Notice to proceed / Project start | FS | 10 | MPB-E1010 | Design basis & architectural layout
MPB-E1010 | Design basis & architectural layout | SS | 5 | MPB-E1020 | Structural design & IFC drawings
MPB-E1010 | Design basis & architectural layout | FS | 0 | MPB-E1030 | MEP design & drawings
MPB-E1020 | Structural design & IFC drawings | FS | 0 | MPB-E1040 | Drawing approval by client
MPB-E1030 | MEP design & drawings | FF | 0 | MPB-E1040 | Drawing approval by client
MPB-E1020 | Structural design & IFC drawings | FS | 0 | MPB-P1050 | Structural steel - PO placement
MPB-P1050 | Structural steel - PO placement | FS | 0 | MPB-P1060 | Structural steel - fabrication & supply to site
MPB-E1030 | MEP design & drawings | FS | 0 | MPB-P1070 | MEP equipment - PO placement
MPB-P1070 | MEP equipment - PO placement | FS | 0 | MPB-P1080 | MEP equipment - manufacturing & delivery
MS-1000 | Notice to proceed / Project start | FS | 10 | MPB-C1090 | Site mobilisation & survey
MPB-C1090 | Site mobilisation & survey | FS | 0 | MPB-C1100 | Excavation
MPB-E1020 | Structural design & IFC drawings | SS | 10 | MPB-C1100 | Excavation
MPB-C1100 | Excavation | SS | 7 | MPB-C1110 | PCC & foundation concreting
MPB-C1110 | PCC & foundation concreting | FS | 0 | MPB-C1120 | Plinth beam & backfilling
MPB-C1120 | Plinth beam & backfilling | FS | 0 | MPB-C1130 | Superstructure - RCC / steel erection
MPB-P1060 | Structural steel - fabrication & supply to site | SS | 15 | MPB-C1130 | Superstructure - RCC / steel erection
MPB-C1130 | Superstructure - RCC / steel erection | FS | -5 | MPB-C1140 | Roofing & cladding
MPB-C1130 | Superstructure - RCC / steel erection | SS | 20 | MPB-C1150 | Masonry & plastering
MPB-C1150 | Masonry & plastering | SS | 10 | MPB-C1160 | MEP installation
MPB-P1080 | MEP equipment - manufacturing & delivery | FS | 0 | MPB-C1160 | MEP installation
MPB-C1150 | Masonry & plastering | FS | 0 | MPB-C1170 | Finishes - flooring & painting
MPB-C1140 | Roofing & cladding | FS | 0 | MPB-C1170 | Finishes - flooring & painting
MPB-C1160 | MEP installation | FS | 0 | MPB-C1180 | Testing & commissioning
MPB-C1170 | Finishes - flooring & painting | FF | 0 | MPB-C1180 | Testing & commissioning
MPB-C1180 | Testing & commissioning | FS | 0 | MPB-C1190 | Building handover to client
MPB-C1190 | Building handover to client | FS | 0 | MS-9000 | Plant mechanical completion
MS-1000 | Notice to proceed / Project start | FS | 40 | WHS-E1010 | Design basis & architectural layout
WHS-E1010 | Design basis & architectural layout | SS | 5 | WHS-E1020 | Structural design & IFC drawings
WHS-E1010 | Design basis & architectural layout | FS | 0 | WHS-E1030 | MEP design & drawings
WHS-E1020 | Structural design & IFC drawings | FS | 0 | WHS-E1040 | Drawing approval by client
WHS-E1030 | MEP design & drawings | FF | 0 | WHS-E1040 | Drawing approval by client
WHS-E1020 | Structural design & IFC drawings | FS | 0 | WHS-P1050 | Structural steel - PO placement
WHS-P1050 | Structural steel - PO placement | FS | 0 | WHS-P1060 | Structural steel - fabrication & supply to site
WHS-E1030 | MEP design & drawings | FS | 0 | WHS-P1070 | MEP equipment - PO placement
WHS-P1070 | MEP equipment - PO placement | FS | 0 | WHS-P1080 | MEP equipment - manufacturing & delivery
MS-1000 | Notice to proceed / Project start | FS | 40 | WHS-C1090 | Site mobilisation & survey
WHS-C1090 | Site mobilisation & survey | FS | 0 | WHS-C1100 | Excavation
WHS-E1020 | Structural design & IFC drawings | SS | 10 | WHS-C1100 | Excavation
WHS-C1100 | Excavation | SS | 7 | WHS-C1110 | PCC & foundation concreting
WHS-C1110 | PCC & foundation concreting | FS | 0 | WHS-C1120 | Plinth beam & backfilling
WHS-C1120 | Plinth beam & backfilling | FS | 0 | WHS-C1130 | Superstructure - RCC / steel erection
WHS-P1060 | Structural steel - fabrication & supply to site | SS | 15 | WHS-C1130 | Superstructure - RCC / steel erection
WHS-C1130 | Superstructure - RCC / steel erection | FS | -5 | WHS-C1140 | Roofing & cladding
WHS-C1130 | Superstructure - RCC / steel erection | SS | 20 | WHS-C1150 | Masonry & plastering
WHS-C1150 | Masonry & plastering | SS | 10 | WHS-C1160 | MEP installation
WHS-P1080 | MEP equipment - manufacturing & delivery | FS | 0 | WHS-C1160 | MEP installation
WHS-C1150 | Masonry & plastering | FS | 0 | WHS-C1170 | Finishes - flooring & painting
WHS-C1140 | Roofing & cladding | FS | 0 | WHS-C1170 | Finishes - flooring & painting
WHS-C1160 | MEP installation | FS | 0 | WHS-C1180 | Testing & commissioning
WHS-C1170 | Finishes - flooring & painting | FF | 0 | WHS-C1180 | Testing & commissioning
WHS-C1180 | Testing & commissioning | FS | 0 | WHS-C1190 | Building handover to client
WHS-C1190 | Building handover to client | FS | 0 | MS-9000 | Plant mechanical completion
MS-1000 | Notice to proceed / Project start | FS | 60 | SUB-E1010 | Design basis & architectural layout
SUB-E1010 | Design basis & architectural layout | SS | 5 | SUB-E1020 | Structural design & IFC drawings
SUB-E1010 | Design basis & architectural layout | FS | 0 | SUB-E1030 | MEP design & drawings
SUB-E1020 | Structural design & IFC drawings | FS | 0 | SUB-E1040 | Drawing approval by client
SUB-E1030 | MEP design & drawings | FF | 0 | SUB-E1040 | Drawing approval by client
SUB-E1020 | Structural design & IFC drawings | FS | 0 | SUB-P1050 | Structural steel - PO placement
SUB-P1050 | Structural steel - PO placement | FS | 0 | SUB-P1060 | Structural steel - fabrication & supply to site
SUB-E1030 | MEP design & drawings | FS | 0 | SUB-P1070 | MEP equipment - PO placement
SUB-P1070 | MEP equipment - PO placement | FS | 0 | SUB-P1080 | MEP equipment - manufacturing & delivery
MS-1000 | Notice to proceed / Project start | FS | 60 | SUB-C1090 | Site mobilisation & survey
SUB-C1090 | Site mobilisation & survey | FS | 0 | SUB-C1100 | Excavation
SUB-E1020 | Structural design & IFC drawings | SS | 10 | SUB-C1100 | Excavation
SUB-C1100 | Excavation | SS | 7 | SUB-C1110 | PCC & foundation concreting
SUB-C1110 | PCC & foundation concreting | FS | 0 | SUB-C1120 | Plinth beam & backfilling
SUB-C1120 | Plinth beam & backfilling | FS | 0 | SUB-C1130 | Superstructure - RCC / steel erection
SUB-P1060 | Structural steel - fabrication & supply to site | SS | 15 | SUB-C1130 | Superstructure - RCC / steel erection
SUB-C1130 | Superstructure - RCC / steel erection | FS | -5 | SUB-C1140 | Roofing & cladding
SUB-C1130 | Superstructure - RCC / steel erection | SS | 20 | SUB-C1150 | Masonry & plastering
SUB-C1150 | Masonry & plastering | SS | 10 | SUB-C1160 | MEP installation
SUB-P1080 | MEP equipment - manufacturing & delivery | FS | 0 | SUB-C1160 | MEP installation
SUB-C1150 | Masonry & plastering | FS | 0 | SUB-C1170 | Finishes - flooring & painting
SUB-C1140 | Roofing & cladding | FS | 0 | SUB-C1170 | Finishes - flooring & painting
SUB-C1160 | MEP installation | FS | 0 | SUB-C1180 | Testing & commissioning
SUB-C1170 | Finishes - flooring & painting | FF | 0 | SUB-C1180 | Testing & commissioning
SUB-C1180 | Testing & commissioning | FS | 0 | SUB-C1190 | Building handover to client
SUB-C1190 | Building handover to client | FS | 0 | MS-9000 | Plant mechanical completion
MS-1000 | Notice to proceed / Project start | FS | 90 | UTL-E1010 | Design basis & architectural layout
UTL-E1010 | Design basis & architectural layout | SS | 5 | UTL-E1020 | Structural design & IFC drawings
UTL-E1010 | Design basis & architectural layout | FS | 0 | UTL-E1030 | MEP design & drawings
UTL-E1020 | Structural design & IFC drawings | FS | 0 | UTL-E1040 | Drawing approval by client
UTL-E1030 | MEP design & drawings | FF | 0 | UTL-E1040 | Drawing approval by client
UTL-E1020 | Structural design & IFC drawings | FS | 0 | UTL-P1050 | Structural steel - PO placement
UTL-P1050 | Structural steel - PO placement | FS | 0 | UTL-P1060 | Structural steel - fabrication & supply to site
UTL-E1030 | MEP design & drawings | FS | 0 | UTL-P1070 | MEP equipment - PO placement
UTL-P1070 | MEP equipment - PO placement | FS | 0 | UTL-P1080 | MEP equipment - manufacturing & delivery
MS-1000 | Notice to proceed / Project start | FS | 90 | UTL-C1090 | Site mobilisation & survey
UTL-C1090 | Site mobilisation & survey | FS | 0 | UTL-C1100 | Excavation
UTL-E1020 | Structural design & IFC drawings | SS | 10 | UTL-C1100 | Excavation
UTL-C1100 | Excavation | SS | 7 | UTL-C1110 | PCC & foundation concreting
UTL-C1110 | PCC & foundation concreting | FS | 0 | UTL-C1120 | Plinth beam & backfilling
UTL-C1120 | Plinth beam & backfilling | FS | 0 | UTL-C1130 | Superstructure - RCC / steel erection
UTL-P1060 | Structural steel - fabrication & supply to site | SS | 15 | UTL-C1130 | Superstructure - RCC / steel erection
UTL-C1130 | Superstructure - RCC / steel erection | FS | -5 | UTL-C1140 | Roofing & cladding
UTL-C1130 | Superstructure - RCC / steel erection | SS | 20 | UTL-C1150 | Masonry & plastering
UTL-C1150 | Masonry & plastering | SS | 10 | UTL-C1160 | MEP installation
UTL-P1080 | MEP equipment - manufacturing & delivery | FS | 0 | UTL-C1160 | MEP installation
UTL-C1150 | Masonry & plastering | FS | 0 | UTL-C1170 | Finishes - flooring & painting
UTL-C1140 | Roofing & cladding | FS | 0 | UTL-C1170 | Finishes - flooring & painting
UTL-C1160 | MEP installation | FS | 0 | UTL-C1180 | Testing & commissioning
UTL-C1170 | Finishes - flooring & painting | FF | 0 | UTL-C1180 | Testing & commissioning
UTL-C1180 | Testing & commissioning | FS | 0 | UTL-C1190 | Building handover to client
UTL-C1190 | Building handover to client | FS | 0 | MS-9000 | Plant mechanical completion
MS-1000 | Notice to proceed / Project start | FS | 120 | STP-E1010 | Design basis & architectural layout
STP-E1010 | Design basis & architectural layout | SS | 5 | STP-E1020 | Structural design & IFC drawings
STP-E1010 | Design basis & architectural layout | FS | 0 | STP-E1030 | MEP design & drawings
STP-E1020 | Structural design & IFC drawings | FS | 0 | STP-E1040 | Drawing approval by client
STP-E1030 | MEP design & drawings | FF | 0 | STP-E1040 | Drawing approval by client
STP-E1020 | Structural design & IFC drawings | FS | 0 | STP-P1050 | Structural steel - PO placement
STP-P1050 | Structural steel - PO placement | FS | 0 | STP-P1060 | Structural steel - fabrication & supply to site
STP-E1030 | MEP design & drawings | FS | 0 | STP-P1070 | MEP equipment - PO placement
STP-P1070 | MEP equipment - PO placement | FS | 0 | STP-P1080 | MEP equipment - manufacturing & delivery
MS-1000 | Notice to proceed / Project start | FS | 120 | STP-C1090 | Site mobilisation & survey
STP-C1090 | Site mobilisation & survey | FS | 0 | STP-C1100 | Excavation
STP-E1020 | Structural design & IFC drawings | SS | 10 | STP-C1100 | Excavation
STP-C1100 | Excavation | SS | 7 | STP-C1110 | PCC & foundation concreting
STP-C1110 | PCC & foundation concreting | FS | 0 | STP-C1120 | Plinth beam & backfilling
STP-C1120 | Plinth beam & backfilling | FS | 0 | STP-C1130 | Superstructure - RCC / steel erection
STP-P1060 | Structural steel - fabrication & supply to site | SS | 15 | STP-C1130 | Superstructure - RCC / steel erection
STP-C1130 | Superstructure - RCC / steel erection | FS | -5 | STP-C1140 | Roofing & cladding
STP-C1130 | Superstructure - RCC / steel erection | SS | 20 | STP-C1150 | Masonry & plastering
STP-C1150 | Masonry & plastering | SS | 10 | STP-C1160 | MEP installation
STP-P1080 | MEP equipment - manufacturing & delivery | FS | 0 | STP-C1160 | MEP installation
STP-C1150 | Masonry & plastering | FS | 0 | STP-C1170 | Finishes - flooring & painting
STP-C1140 | Roofing & cladding | FS | 0 | STP-C1170 | Finishes - flooring & painting
STP-C1160 | MEP installation | FS | 0 | STP-C1180 | Testing & commissioning
STP-C1170 | Finishes - flooring & painting | FF | 0 | STP-C1180 | Testing & commissioning
STP-C1180 | Testing & commissioning | FS | 0 | STP-C1190 | Building handover to client
STP-C1190 | Building handover to client | FS | 0 | MS-9000 | Plant mechanical completion